PROJECT ADAG

IIB INDIA

Internship Intelligence Bot India

100-Day Product Development Sprint Plan

Team ADAG

Gaurav Bhosale  •  Amey Nadkar  •  Dheeraj Sarfare  •  Aditee Talekar

SaaS Job & Internship Intelligence Platform

Master Execution Document — Engineering Blueprint

# About the Project

IIB India is a SaaS-based Job & Internship Intelligence Platform — not another internship finder. The platform serves three major stakeholders: Students, Colleges, and Companies, connecting them through intelligent filtering, resume-based recommendations, AI-powered career assistance, and centralized company insights.

Unlike traditional job portals, IIB India also automates college placement data management and gives recruiters a modern, analytics-driven hiring dashboard. The platform collects, organizes, filters, normalizes, de-duplicates, and tracks expiry of opportunity data — while all final verification and approval of listings is performed exclusively by human Placement Coordinators. Company reviews aggregated from Glassdoor, AmbitionBox, and Indeed are displayed strictly as insights.

# Core Modules

- Student Portal

- College Portal

- Company Portal

- Resume Intelligence

- AI Recommendation Engine

- Company Insights

- Excel Automation Engine

- Google Sheets Synchronization

- Analytics Dashboard

- Notification System

- Role-Based Access Control

- Admin Dashboard

- Premium AI Features

# User Roles

SUPER ADMIN

- Platform owner — manages colleges, companies, students, recruiters, admins, data sources, and platform-wide moderation.

COLLEGE

- College Admin — manages departments, coordinators, branding, and settings.

- Placement Coordinator — reviews/approves listings, tracks students, generates reports. Sole human-verification authority.

- College Student — discovers jobs/internships, builds profile, applies, tracks applications.

COMPANY

- Company Admin — manages company profile, branches, recruiters, and hiring analytics.

- Recruiter — manages job postings, candidates, interviews, and offers.

PUBLIC USER

- External Student — public self-registered user with AI-powered discovery and premium career tools.

IMPORTANT — All listing verification is performed exclusively by Placement Coordinators. There is NO AI-based approval anywhere in the platform. AI is used only for collection, filtering, normalization, deduplication, expiry tracking, and recommendation — never for final decision-making.

# 100-Day Sprint Overview

| Week(s) | Days | Focus | Milestone |
| --- | --- | --- | --- |
| Week 1 | Days 1-5 (Jul 6 – Jul 10) | Repos, Backend Skeleton & Frontend Shell | All 4 repos live with CI, FastAPI + Postgres + Redis running, React shell navigable, AI service parsing resumes in POC, testing frameworks configured, README and CONTRIBUTING published. |
| Week 2 | Days 6-10 (Jul 11 – Jul 15) | CI/CD, Shared UI Kit & Data Contracts | CI/CD pipeline green on every PR, shared UI kit in use, core DB models migrated, API contracts agreed and documented, RBAC matrix complete, coverage reporting active. |
| Week 3 | Days 11-15 (Jul 16 – Jul 20) | Authentication Core | Registration, login, email verification, and token refresh all working end-to-end with tests passing and a documented security review. |
| Week 4 | Days 16-20 (Jul 21 – Jul 25) | Role-Based Access Control (RBAC) | All 7 roles enforced end-to-end with passing integration tests, role-specific dashboard shells live, invite flows working for colleges and companies, RBAC matrix finalized. |
| Week 5 | Days 21-25 (Jul 26 – Jul 30) | Student Portal - Profile & Discovery | Students can build a profile, search and filter jobs/internships, and see personalized recommendations, dashboard sections and closing-soon alerts, all covered by tests. |
| Week 6 | Days 26-30 (Jul 31 – Aug 4) | Student Portal - Applications & Career Tools | Students can apply, bookmark and track applications with full history, view company insights and salary data, and receive feedback-aware recommendations. |
| Week 7 | Days 31-35 (Aug 5 – Aug 9) | Company Portal - Profile & Job Management | Company Admins can manage profile, branches and recruiters, and create/edit/archive job listings. |
| Week 8 | Days 36-40 (Aug 10 – Aug 14) | Company Portal - Recruiter Workflow | Recruiters can view, rank, shortlist, interview and offer candidates end-to-end, with fit-scoring, notifications, and full test coverage. |
| Week 9 | Days 41-45 (Aug 15 – Aug 19) | College Portal - Admin & Coordinator Core | College Admins manage departments and coordinators; Placement Coordinators review, approve, reject, pin and archive listings. |
| Week 10 | Days 46-50 (Aug 20 – Aug 24) | College Portal - Student Tracking & Reports | Student tracking, Excel/CSV reports, monthly/annual aggregation, College Admin settings and notifications all working and verified for accuracy. |
| Week 11 | Days 51-55 (Aug 25 – Aug 29) | Resume Intelligence - Upload & Parsing | Resumes upload, version, parse and score reliably against a 30-resume test corpus, with ATS checks and profile auto-fill all functioning and documented. |
| Week 12 | Days 56-60 (Aug 30 – Sep 3) | Resume Intelligence - Builder & Premium Tools | Resume Builder, templates, export, premium gating, AI optimization and cover-letter generation are all working with verified output quality. |
| Week 13 | Days 61-65 (Sep 4 – Sep 8) | AI Recommendation Engine - Core | Unified recommendation engine live across all dashboards with caching, feedback tracking, cold-start handling, skill-gap analysis and measured precision/recall. |
| Week 14 | Days 66-70 (Sep 9 – Sep 13) | AI Career Assistant & Premium Intelligence | AI Career Roadmap, Cover Letter Generator, Career Coach, and premium analytics all live and quality-checked. |
| Week 15 | Days 71-75 (Sep 14 – Sep 18) | Excel Automation - Export & Sync | Excel export, Google Sheets auto-sync, sync-status tracking and conflict handling all working, with data integrity validated end-to-end. |
| Week 16 | Days 76-80 (Sep 19 – Sep 23) | Excel Automation - Backup & Archive System | Automated backups, safe restore, and a working archive system are all verified, including a simulated disaster-recovery drill. |
| Week 17 | Days 81-85 (Sep 24 – Sep 28) | Analytics Dashboard | All 4 role-specific analytics dashboards are live, accurate against raw data, performant under load, and include predictive insight generation. |
| Week 18 | Days 86-90 (Sep 29 – Oct 3) | Full-Platform Testing & Hardening | Full regression, security, performance and accessibility testing complete. |
| Week 19 | Days 91-95 (Oct 4 – Oct 8) | Production Deployment | IIB India is live in production with CI/CD, monitoring, alerting, rollback procedures and a verified incident-response runbook. |
| Week 20 | Days 96-100 (Oct 9 – Oct 13) | Final Demo & Project Closure | All code merged to main and tagged v1. |

# Team Responsibilities

| Team Member | Role | Primary Responsibilities |
| --- | --- | --- |
| Gaurav Bhosale | Project Lead & Backend Architecture | Project leadership, backend architecture, database design, authentication & RBAC, FastAPI services, production deployment & infrastructure. |
| Amey Nadkar | Frontend Lead & UI/UX | React frontend, UI/UX design system, all portal dashboards, animations and interaction design, overall user experience. |
| Dheeraj Sarfare | AI & Resume Intelligence | Resume parsing & scoring, AI recommendation engine, career-intelligence features, search intelligence, analytics modeling. |
| Aditee Talekar | Testing, Documentation & QA | Test strategy, QA, documentation, RBAC verification, security & performance validation, reporting and research. |

# WEEK 1

Days 1-5 (Jul 6 – Jul 10)  —  Repos, Backend Skeleton & Frontend Shell

SPRINT GOAL Every module (backend, frontend, AI, QA) has a running skeleton. GitHub org is live with branch protection, and the team agrees on architecture.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 1 (Jul 6) | Create GitHub org & 4 repos (backend, frontend, ai, docs) with branch protection | Repos live with protected main branch | Org structured, README stubs committed | Repos cloneable, PR template enforced |
| Day 2 (Jul 7) | Build FastAPI project skeleton with app factory pattern and pydantic-settings config | Running FastAPI app with health check | fastapi-app skeleton committed | GET /health returns 200 locally |
| Day 3 (Jul 8) | Provision PostgreSQL via docker-compose, configure SQLAlchemy + Alembic migrations | DB container running, first migration applied | docker-compose.yml, alembic init committed | alembic upgrade head succeeds cleanly |
| Day 4 (Jul 9) | Design initial ER diagram covering users, roles, colleges, companies, jobs | ER diagram documented and shared | ER diagram added to docs/ | Diagram reviewed and approved by team |
| Day 5 (Jul 10) | Set up Redis for caching/session store and connect it to FastAPI Also run the weekly team sync: review Week 1 backend progress, finalize architecture decisions | Redis connected, test key set/get working Architecture decision record written | Redis client integration committed; ADR-001 committed to docs/ | Cache read/write verified in logs Team sign-off recorded in GitHub Discussions |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 1 (Jul 6) | Initialize React + Vite project, configure ESLint/Prettier and folder structure | React app boots on localhost | vite-react skeleton committed | npm run dev renders blank shell |
| Day 2 (Jul 7) | Set up TailwindCSS with design tokens for color, typography and spacing | Design system tokens file ready | tailwind.config.js with tokens committed | Tokens visible and applied on sample page |
| Day 3 (Jul 8) | Build base layout components - Navbar, Sidebar, Footer, PageContainer | Reusable layout shell working | Layout components committed | Layout renders across 3 sample pages |
| Day 4 (Jul 9) | Set up React Router with route structure for all 4 portals | Routing skeleton navigable | Router config committed | All placeholder routes reachable in browser |
| Day 5 (Jul 10) | Set up Axios API client with interceptors for auth token and errors Also run the weekly team sync: demo frontend shell navigation to the team | API client wrapper ready Frontend shell demo delivered | api/client.js committed; Demo notes logged in Wiki | Mock request/response cycle verified Team confirms navigation works end-to-end |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 1 (Jul 6) | Set up separate Python AI microservice repo on FastAPI | AI service skeleton running | iib-ai repo committed | GET /ai/health returns 200 |
| Day 2 (Jul 7) | Research resume parsing approaches - spaCy, pyresparser, LLM extraction | Comparison report written | AI_Library_Comparison.md committed | Decision logged with pros/cons |
| Day 3 (Jul 8) | Set up spaCy NLP pipeline, test entity extraction on a sample resume | Entities extracted from test resume | POC script committed | Extracts name, email, skills correctly |
| Day 4 (Jul 9) | Design initial recommendation engine architecture - content-based vs collaborative filtering | Architecture proposal documented | recommendation_engine_design.md committed | Approach approved by project lead |
| Day 5 (Jul 10) | Set up sentence-transformers embedding pipeline for skill matching POC Also run the weekly team sync: present AI service architecture and parsing POC | Embeddings generated for sample skills AI POC demo delivered | embedding_poc.py committed; Demo recorded for reference | Cosine similarity scores look sensible Team approves parsing approach |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 1 (Jul 6) | Set up pytest for backend and Jest for frontend with test conventions | Test frameworks scaffolded | testing_conventions.md committed | Sample test passes in both frameworks |
| Day 2 (Jul 7) | Draft project README - vision, architecture overview, setup instructions | README v1 published | README.md committed | New developer can follow setup steps |
| Day 3 (Jul 8) | Research GDPR/data-privacy considerations for storing resumes and student data | Privacy research notes written | privacy_notes.md added to Wiki | Notes reviewed by project lead |
| Day 4 (Jul 9) | Set up GitHub Projects board with all 20 weeks as milestones | Project board live | GitHub Projects configured | All weeks visible as milestone columns |
| Day 5 (Jul 10) | Write CONTRIBUTING.md - branching strategy, PR review process, commit conventions Also run the weekly team sync: consolidate Week 1 retrospective notes from all members | Contributor guide published Week 1 retro completed | CONTRIBUTING.md committed; retro-week1.md committed | Team confirms process is clear All blockers logged as GitHub Issues |

✅ WEEK COMPLETED WHEN All 4 repos live with CI, FastAPI + Postgres + Redis running, React shell navigable, AI service parsing resumes in POC, testing frameworks configured, README and CONTRIBUTING published.

# WEEK 2

Days 6-10 (Jul 11 – Jul 15)  —  CI/CD, Shared UI Kit & Data Contracts

SPRINT GOAL Automated pipelines are live, a shared component library exists, and API contracts between frontend/backend/AI are agreed and documented.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 6 (Jul 11) | Set up GitHub Actions CI - lint, test, build on every PR | CI pipeline green on sample PR | ci.yml committed | PR blocked automatically on failing tests |
| Day 7 (Jul 12) | Design and implement core SQLAlchemy models - User, Role, College, Company | Core models migrated to DB | models/ committed with migrations | Tables visible via psql, relations correct |
| Day 8 (Jul 13) | Build OpenAPI schema conventions and shared Pydantic response envelope | Standard API response format defined | schemas/base.py committed | Sample endpoint returns consistent envelope |
| Day 9 (Jul 14) | Set up staging environment on cloud provider (droplet/VM + docker) | Staging server reachable | Staging deployment documented | curl to staging /health succeeds |
| Day 10 (Jul 15) | Write API contract doc for Student, College, Company, Admin endpoints Also run the weekly team sync: review CI pipeline and API contracts with team | API contract v1 published CI + contracts demo delivered | api_contracts.md committed; Demo notes in Wiki | Frontend and AI leads sign off Team agrees contracts are implementable |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 6 (Jul 11) | Set up Jest + React Testing Library, write first component test | First test passing in CI | Test config committed | npm test passes locally and in CI |
| Day 7 (Jul 12) | Build shared UI kit - Button, Input, Card, Modal, Badge components | UI kit v1 usable across app | components/ui/ committed | Storybook or preview shows all variants |
| Day 8 (Jul 13) | Build authentication context (React Context/Zustand) for token/session state | Auth state management working | AuthContext committed | Token persists across page refresh |
| Day 9 (Jul 14) | Wire up environment-based API base URLs (dev/staging/prod) | Env-aware API config | .env handling committed | App points to staging when configured |
| Day 10 (Jul 15) | Build loading/error/empty state components for data-driven views Also run the weekly team sync: demo UI kit and auth context to team | Reusable state components UI kit demo delivered | StateViews components committed; Demo notes in Wiki | Used consistently in 2 sample pages Team approves component API design |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 6 (Jul 11) | Formalize resume parsing output schema (skills, education, experience, projects) | Parsing schema documented | resume_schema.json committed | Schema reviewed and approved by team |
| Day 7 (Jul 12) | Build resume text extraction from PDF/DOCX using pdfplumber/python-docx | Raw text extracted from sample files | extract_text.py committed | Extracts clean text from 5 test resumes |
| Day 8 (Jul 13) | Prototype skill-taxonomy list (technical skills, domains, tools) for tagging | Skill taxonomy v1 drafted | skill_taxonomy.json committed | Covers top 100 tech/domain skills |
| Day 9 (Jul 14) | Set up model/version management approach for AI service (config-driven) | Model config system working | ai_config.py committed | Switching models via config verified |
| Day 10 (Jul 15) | Build simple keyword-based job-skill matching POC Also run the weekly team sync: present resume schema and matching POC | Matching POC returns ranked scores AI progress demo delivered | match_poc.py committed; Demo notes in Wiki | Produces sensible ranking on test data Team approves schema for backend integration |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 6 (Jul 11) | Write test plan template covering unit/integration/e2e coverage expectations | Test plan template published | test_plan_template.md committed | Template usable by all 4 members |
| Day 7 (Jul 12) | Set up code coverage reporting (pytest-cov, Jest coverage) | Coverage reports generated locally | Coverage config committed | Coverage % visible in CI output |
| Day 8 (Jul 13) | Draft RBAC matrix - all roles vs all permitted actions | RBAC matrix v1 documented | rbac_matrix.md committed | Matrix covers all 7 roles |
| Day 9 (Jul 14) | Write onboarding doc for new contributors joining mid-sprint | Onboarding guide published | ONBOARDING.md committed | Doc covers setup, structure, workflow |
| Day 10 (Jul 15) | Review Week 1-2 GitHub Issues, triage and prioritize backlog Also run the weekly team sync: present RBAC matrix and coverage setup to team | Backlog triaged and labeled RBAC + coverage demo delivered | Issues labeled by priority/module; Demo notes in Wiki | No unlabeled open issues remain Team confirms RBAC matrix is complete |

✅ WEEK COMPLETED WHEN CI/CD pipeline green on every PR, shared UI kit in use, core DB models migrated, API contracts agreed and documented, RBAC matrix complete, coverage reporting active.

# WEEK 3

Days 11-15 (Jul 16 – Jul 20)  —  Authentication Core

SPRINT GOAL Users can register, log in, and receive secure JWT tokens. Password handling, refresh tokens, and session security are production-grade.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 11 (Jul 16) | Implement user registration endpoint with email verification token generation | POST /auth/register working end-to-end | Registration endpoint committed | New user row created, verification email queued |
| Day 12 (Jul 17) | Implement login endpoint with JWT access + refresh token issuance | POST /auth/login returns valid tokens | Login endpoint committed | Tokens verified via jwt.io decode |
| Day 13 (Jul 18) | Implement password hashing with bcrypt/argon2 and password policy validation | Passwords hashed, weak passwords rejected | Password utils committed | Plain-text password never persisted |
| Day 14 (Jul 19) | Build refresh-token rotation endpoint with revocation on reuse detection | POST /auth/refresh rotates tokens safely | Refresh flow committed | Reused old token is rejected |
| Day 15 (Jul 20) | Implement email verification confirm endpoint and account activation logic Also run the weekly team sync: demo full registration-to-login flow to team | Account activates only after verification Auth flow demo delivered | Verify-email endpoint committed; Demo notes in Wiki | Unverified accounts blocked from login Team completes signup+login live |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 11 (Jul 16) | Build Sign Up page with form validation (email, password strength) | Sign Up page functional | SignUp.jsx committed | Invalid inputs show inline errors |
| Day 12 (Jul 17) | Build Login page with remember-me and forgot-password entry point | Login page functional | Login.jsx committed | Successful login redirects to dashboard |
| Day 13 (Jul 18) | Wire login/signup forms to backend auth endpoints via API client | Forms submit and handle responses | Auth API integration committed | Error and success states both handled |
| Day 14 (Jul 19) | Build protected route wrapper redirecting unauthenticated users to login | Protected routes enforce auth | ProtectedRoute component committed | Unauthenticated access redirects correctly |
| Day 15 (Jul 20) | Build token refresh interceptor - silently refresh expired access tokens Also run the weekly team sync: demo full auth UI flow including token refresh | Silent refresh working Auth UI demo delivered | Axios interceptor updated; Demo notes in Wiki | Expired token triggers refresh, not logout Team confirms smooth login experience |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 11 (Jul 16) | Design user-skill and user-preference data schema for future recommendations | User preference schema documented | user_preference_schema.json committed | Schema approved for backend integration |
| Day 12 (Jul 17) | Research OAuth/social-login feasibility (Google) for external students | Feasibility report written | oauth_feasibility.md committed | Decision logged - build now or defer |
| Day 13 (Jul 18) | Build skill-taxonomy tagging function to auto-tag user-entered skills | Skill tagging function working | tag_skills.py committed | Correctly tags 20 test skill inputs |
| Day 14 (Jul 19) | Prototype resume-to-skill extraction using the parsing pipeline from Week 2 | Skills extracted from real resumes | resume_to_skills.py committed | Extracts skills from 5 sample resumes |
| Day 15 (Jul 20) | Document AI service authentication approach (service-to-service token) Also run the weekly team sync: present skill tagging progress to team | AI auth approach documented Skill tagging demo delivered | ai_auth_design.md committed; Demo notes in Wiki | Approved by backend lead Team reviews tagging accuracy |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 11 (Jul 16) | Write unit tests for registration, login, and password hashing logic | Auth unit tests passing | test_auth.py committed | 10+ auth test cases passing in CI |
| Day 12 (Jul 17) | Write RBAC-focused test matrix execution for auth endpoints | RBAC auth tests documented | rbac_auth_tests.md committed | Each role's access verified against matrix |
| Day 13 (Jul 18) | Security review - check for JWT secret handling, token expiry settings | Security checklist completed | security_review_auth.md committed | No secrets in repo, expiry configured correctly |
| Day 14 (Jul 19) | Write frontend tests for Login/SignUp form validation | Frontend auth tests passing | Login.test.jsx, SignUp.test.jsx committed | Validation edge cases covered |
| Day 15 (Jul 20) | Document password reset and account recovery user flow Also run the weekly team sync: present auth test coverage and security review | Recovery flow documented Test coverage demo delivered | password_recovery_flow.md committed; Demo notes in Wiki | Flow diagram reviewed by team Team signs off on auth security |

✅ WEEK COMPLETED WHEN Registration, login, email verification, and token refresh all working end-to-end with tests passing and a documented security review.

# WEEK 4

Days 16-20 (Jul 21 – Jul 25)  —  Role-Based Access Control (RBAC)

SPRINT GOAL All 7 roles (Super Admin, College Admin, Placement Coordinator, College Student, Company Admin, Recruiter, External Student) have enforced, tested permission boundaries.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 16 (Jul 21) | Implement role and permission tables with many-to-many mapping | Role/permission schema migrated | roles, permissions tables committed | Query returns correct permissions per role |
| Day 17 (Jul 22) | Build FastAPI dependency for role-based endpoint protection | require_role() dependency working | rbac_dependency.py committed | Unauthorized role receives 403 |
| Day 18 (Jul 23) | Implement Super Admin bootstrap script for initial platform setup | Super Admin account creatable via CLI | bootstrap_admin.py committed | First admin account created successfully |
| Day 19 (Jul 24) | Build College Admin invite flow for Placement Coordinator accounts | Invite + accept flow working | College invite endpoints committed | Invited coordinator can activate account |
| Day 20 (Jul 25) | Build Company Admin invite flow for Recruiter accounts Also run the weekly team sync: demo full RBAC enforcement across all 7 roles | Recruiter invite flow working RBAC demo delivered | Company invite endpoints committed; Demo notes in Wiki | Invited recruiter can activate account Each role tested live against matrix |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 16 (Jul 21) | Build role-aware navigation - sidebar/menu changes based on logged-in role | Role-based nav rendering correctly | RoleNav component committed | Each of 7 roles sees correct menu |
| Day 17 (Jul 22) | Build College Admin dashboard shell with placement coordinator management UI | College Admin shell functional | CollegeAdminDashboard.jsx committed | Admin can view/invite coordinators |
| Day 18 (Jul 23) | Build Company Admin dashboard shell with recruiter management UI | Company Admin shell functional | CompanyAdminDashboard.jsx committed | Admin can view/invite recruiters |
| Day 19 (Jul 24) | Build Super Admin shell - platform-wide college/company management view | Super Admin shell functional | SuperAdminDashboard.jsx committed | Admin can list all colleges/companies |
| Day 20 (Jul 25) | Build access-denied / 403 UI page with helpful messaging Also run the weekly team sync: demo all role-specific dashboard shells | 403 page implemented Dashboard shells demo delivered | AccessDenied.jsx committed; Demo notes in Wiki | Unauthorized route shows friendly message Team confirms UI matches role matrix |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 16 (Jul 21) | Design department-wise data model to support college analytics later | Department schema documented | department_schema.json committed | Supports multi-department colleges |
| Day 17 (Jul 22) | Research approach for company review aggregation (Glassdoor/AmbitionBox/Indeed) | Aggregation approach documented | review_aggregation_design.md committed | Legal/ToS considerations noted |
| Day 18 (Jul 23) | Build data normalization utility for inconsistent job title/skill naming | Normalization function working | normalize_data.py committed | Normalizes 20 test variants correctly |
| Day 19 (Jul 24) | Build duplicate-detection logic for job/internship listings | Duplicate detection POC working | dedupe_poc.py committed | Correctly flags 5 duplicate test listings |
| Day 20 (Jul 25) | Document AI service role-awareness (what each role can request from AI) Also run the weekly team sync: present data normalization and dedup progress | AI-role permission doc written Normalization demo delivered | ai_role_permissions.md committed; Demo notes in Wiki | Reviewed and approved by team Team reviews accuracy on sample data |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 16 (Jul 21) | Write RBAC integration tests covering all 7 roles against all endpoints | Full RBAC test suite passing | test_rbac.py committed | All role/endpoint combinations verified |
| Day 17 (Jul 22) | Write test cases for invite/accept flows (college and company) | Invite flow tests passing | test_invites.py committed | Edge cases - expired invite, reused token |
| Day 18 (Jul 23) | Perform manual QA pass on all 4 role-specific dashboard shells | QA report on dashboards | qa_report_dashboards.md committed | All bugs logged as GitHub Issues |
| Day 19 (Jul 24) | Update RBAC matrix doc with any changes discovered during implementation | RBAC matrix v2 published | rbac_matrix.md updated | Matches actual implemented behavior |
| Day 20 (Jul 25) | Write documentation - How Roles Work in IIB India (for stakeholders) Also run the weekly team sync: present full RBAC test results and sign-off | Roles documentation published RBAC sign-off demo delivered | ROLES.md committed; Demo notes in Wiki | Reviewed by project lead Team formally signs off on RBAC |

✅ WEEK COMPLETED WHEN All 7 roles enforced end-to-end with passing integration tests, role-specific dashboard shells live, invite flows working for colleges and companies, RBAC matrix finalized.

# WEEK 5

Days 21-25 (Jul 26 – Jul 30)  —  Student Portal - Profile & Discovery

SPRINT GOAL College and external students can build a profile and discover jobs/internships through search and filters.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 21 (Jul 26) | Build student profile API - skills, education, projects, certificates, interests | CRUD endpoints for student profile | student_profile router committed | Profile persists and returns correctly |
| Day 22 (Jul 27) | Build job/internship listing model and CRUD API (draft state) | Listings CRUD working | listings router committed | Create/read/update/archive all functional |
| Day 23 (Jul 28) | Build search API with keyword search across jobs/internships/companies | Search endpoint returning ranked results | search router committed | Keyword search returns relevant results |
| Day 24 (Jul 29) | Build filter API - domain, location, salary, stipend, experience, work mode | Filter query params supported | Filter logic committed | Combined filters return correct subset |
| Day 25 (Jul 30) | Add pagination and sorting to listings endpoints Also run the weekly team sync: demo listings, search and filter APIs | Paginated responses working API demo delivered | Pagination utility committed; Demo notes in Wiki | Page size and sort order respected Team validates search relevance |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 21 (Jul 26) | Build student profile page - editable sections for skills/education/projects | Profile page functional | StudentProfile.jsx committed | Edits save and persist on reload |
| Day 22 (Jul 27) | Build personalized student dashboard - recommended, recently added, closing soon | Dashboard sections rendering | StudentDashboard.jsx committed | All 3 sections show live data |
| Day 23 (Jul 28) | Build job/internship search page with keyword search bar | Search page functional | SearchPage.jsx committed | Typing query returns matching results |
| Day 24 (Jul 29) | Build filter sidebar - domain, location, salary, stipend, experience, mode | Filter sidebar functional | FilterSidebar.jsx committed | Selecting filters updates result list |
| Day 25 (Jul 30) | Build job/internship listing card component with key details Also run the weekly team sync: demo student dashboard and search experience | Listing card reusable component Student UI demo delivered | ListingCard.jsx committed; Demo notes in Wiki | Card shows title, company, salary, deadline Team confirms UX is intuitive |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 21 (Jul 26) | Build skill-based recommendation scoring using Week 1-4 embedding POC | Recommendation scores generated per student | skill_recommender.py committed | Top-5 recommendations look relevant on test data |
| Day 22 (Jul 27) | Integrate recommendation scoring into a callable AI service endpoint | POST /ai/recommend/jobs working | recommend endpoint committed | Returns ranked job IDs with scores |
| Day 23 (Jul 28) | Build closing-soon and trending logic (deadline proximity + view count) | Trending/closing-soon logic working | trending_logic.py committed | Correctly ranks test listings by urgency |
| Day 24 (Jul 29) | Build resume-based recommendation stub (feeds resume skills into recommender) | Resume-based recommendations stubbed | resume_recommend_stub.py committed | Accepts resume ID, returns job matches |
| Day 25 (Jul 30) | Write evaluation script comparing recommendation quality across test profiles Also run the weekly team sync: present recommendation scoring results to team | Evaluation report generated Recommendation demo delivered | eval_recommendations.py committed; Demo notes in Wiki | Report shared with team for review Team reviews relevance and approves |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 21 (Jul 26) | Write API tests for student profile CRUD and listings endpoints | Profile/listings tests passing | test_student_api.py committed | All CRUD paths covered including edge cases |
| Day 22 (Jul 27) | Write frontend tests for StudentProfile and SearchPage components | Frontend tests passing | StudentProfile.test.jsx committed | Form validation and search rendering covered |
| Day 23 (Jul 28) | Manual QA pass on filter combinations across all filter types | Filter QA report written | qa_report_filters.md committed | All bugs logged as GitHub Issues |
| Day 24 (Jul 29) | Write test cases validating recommendation endpoint response structure | Recommendation API tests passing | test_recommend_api.py committed | Response schema validated automatically |
| Day 25 (Jul 30) | Document Student Portal feature set for USAGE.md Also run the weekly team sync: present Week 5 test coverage summary | Student portal docs published Test summary demo delivered | USAGE.md updated; Demo notes in Wiki | Covers profile, search, filters, recommendations Coverage % shared with team |

✅ WEEK COMPLETED WHEN Students can build a profile, search and filter jobs/internships, and see personalized recommendations, dashboard sections and closing-soon alerts, all covered by tests.

# WEEK 6

Days 26-30 (Jul 31 – Aug 4)  —  Student Portal - Applications & Career Tools

SPRINT GOAL Students can apply, bookmark, and track applications, and access company insights and career tools.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 26 (Jul 31) | Build apply-to-job/internship API with duplicate application prevention | POST /applications working | applications router committed | Duplicate apply attempt is rejected |
| Day 27 (Aug 1) | Build bookmark/save-for-later API for jobs and internships | Bookmark CRUD working | bookmarks router committed | Bookmarks persist per user |
| Day 28 (Aug 2) | Build application status tracking API - applied, shortlisted, selected, rejected | Status tracking working | application_status endpoint committed | Status updates reflect in history |
| Day 29 (Aug 3) | Build application history endpoint with timeline of status changes | History endpoint returning timeline | application_history endpoint committed | Timeline ordered correctly by date |
| Day 30 (Aug 4) | Build company profile API - reviews, salary insights aggregation fields Also run the weekly team sync: demo apply/bookmark/tracking flow end-to-end | Company profile API working Applications demo delivered | company_profile router committed; Demo notes in Wiki | Returns aggregated review/salary data Team completes an application live |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 26 (Jul 31) | Build Apply button + application confirmation modal on listing pages | Apply flow functional | ApplyModal.jsx committed | Successful apply shows confirmation |
| Day 27 (Aug 1) | Build Save/Bookmark toggle on listing cards and detail pages | Bookmark toggle functional | BookmarkToggle.jsx committed | State persists across sessions |
| Day 28 (Aug 2) | Build Application Tracker page - grouped by status with timeline view | Tracker page functional | ApplicationTracker.jsx committed | Applications grouped and timelined correctly |
| Day 29 (Aug 3) | Build Company Profile page - reviews, salary insights, interview experiences | Company profile page functional | CompanyProfile.jsx committed | All sections render live data |
| Day 30 (Aug 4) | Build Career section - company reviews and salary insights UI Also run the weekly team sync: demo full student application journey to team | Career tools UI functional Full journey demo delivered | CareerInsights.jsx committed; Demo notes in Wiki | Reviews and insights display correctly Team walks through apply-to-track flow |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 26 (Jul 31) | Build company review aggregation pipeline from configured public sources | Aggregation pipeline working on sample data | review_aggregator.py committed | Aggregates reviews from 3 sources correctly |
| Day 27 (Aug 1) | Build salary insights computation - average/range per role and company | Salary insights computed correctly | salary_insights.py committed | Matches manually verified sample data |
| Day 28 (Aug 2) | Improve recommendation ranking using application/bookmark signals as feedback | Feedback-aware ranking implemented | feedback_ranking.py committed | Ranking shifts appropriately with new signals |
| Day 29 (Aug 3) | Build skill-gap analysis stub - compares student skills to target roles | Skill-gap stub working | skill_gap_stub.py committed | Returns missing-skill list for test profile |
| Day 30 (Aug 4) | Write data quality checks for aggregated review/salary data Also run the weekly team sync: present company insights and skill-gap progress | Data quality checks passing AI insights demo delivered | data_quality_checks.py committed; Demo notes in Wiki | Flags malformed/outlier records Team reviews data accuracy |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 26 (Jul 31) | Write tests for apply/bookmark/status-tracking endpoints | Application API tests passing | test_applications_api.py committed | Duplicate-apply and status-flow cases covered |
| Day 27 (Aug 1) | Write frontend tests for ApplyModal and ApplicationTracker | Frontend tests passing | ApplyModal.test.jsx committed | Apply and tracking flows verified |
| Day 28 (Aug 2) | Manual QA - full student journey from signup to application tracking | End-to-end QA report written | qa_report_student_journey.md committed | All bugs logged with severity |
| Day 29 (Aug 3) | Write tests validating company review/salary aggregation accuracy | Aggregation tests passing | test_review_aggregation.py committed | Matches expected sample outputs |
| Day 30 (Aug 4) | Update USAGE.md with application tracking and career tools sections Also run the weekly team sync: Week 6 retrospective and Student Portal sign-off | Docs updated Student Portal sign-off | USAGE.md updated; retro-week6.md committed | Reviewed by project lead Team formally signs off on Student Portal MVP |

✅ WEEK COMPLETED WHEN Students can apply, bookmark and track applications with full history, view company insights and salary data, and receive feedback-aware recommendations. Student Portal MVP signed off.

# WEEK 7

Days 31-35 (Aug 5 – Aug 9)  —  Company Portal - Profile & Job Management

SPRINT GOAL Company Admins can manage their company profile, branches, and recruiters, and create job/internship listings.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 31 (Aug 5) | Build company profile management API - branding, verification documents | Company profile CRUD working | company_admin router committed | Profile updates persist correctly |
| Day 32 (Aug 6) | Build branch management API for multi-branch companies | Branch CRUD working | branches router committed | Branches linked correctly to parent company |
| Day 33 (Aug 7) | Build recruiter management API - add/remove/permissions | Recruiter management working | recruiter_management endpoints committed | Admin can add/remove recruiters |
| Day 34 (Aug 8) | Build job/internship creation API with validation (salary, deadline, requirements) | Job creation API working | job_creation endpoint committed | Invalid listings rejected with clear errors |
| Day 35 (Aug 9) | Build listing edit/archive/delete API with audit trail Also run the weekly team sync: demo company profile and job creation flow | Listing lifecycle API working Company API demo delivered | listing_lifecycle endpoints committed; Demo notes in Wiki | Audit log records every change Team creates a job listing live |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 31 (Aug 5) | Build Company Profile management page - branding, documents, branches | Company profile page functional | CompanyProfilePage.jsx committed | Admin can edit and save profile |
| Day 32 (Aug 6) | Build Branch Management UI - add/edit/remove branches | Branch management functional | BranchManagement.jsx committed | Branches list updates in real time |
| Day 33 (Aug 7) | Build Recruiter Management UI - invite, remove, assign permissions | Recruiter management functional | RecruiterManagement.jsx committed | Admin can manage recruiter list |
| Day 34 (Aug 8) | Build Job/Internship creation form with validation and preview | Job creation form functional | JobCreationForm.jsx committed | Form validates before submission, shows preview |
| Day 35 (Aug 9) | Build listings management table - edit, archive, delete actions Also run the weekly team sync: demo Company Portal management screens | Listings table functional Company Portal demo delivered | ListingsTable.jsx committed; Demo notes in Wiki | Actions update listing state correctly Team walks through full job posting flow |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 31 (Aug 5) | Design company analytics data pipeline - views, applicants, shortlisted, selected | Analytics pipeline design documented | company_analytics_design.md committed | Approved by project lead |
| Day 32 (Aug 6) | Build view/impression tracking for job/internship listings | View tracking working | view_tracking.py committed | View counts increment correctly on access |
| Day 33 (Aug 7) | Build applicant funnel computation - applied to shortlisted to selected | Funnel computation working | applicant_funnel.py committed | Funnel numbers match test data |
| Day 34 (Aug 8) | Build hiring trend computation across time periods for a company | Hiring trend data generated | hiring_trends.py committed | Trend chart data matches manual calculation |
| Day 35 (Aug 9) | Integrate skill-taxonomy tagging into job creation for better matching Also run the weekly team sync: present company analytics pipeline progress | Job listings auto-tagged with skills Analytics demo delivered | job_auto_tagging.py committed; Demo notes in Wiki | Tags match manually reviewed sample jobs Team reviews funnel accuracy |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 31 (Aug 5) | Write tests for company profile, branch, and recruiter management APIs | Company API tests passing | test_company_api.py committed | CRUD and permission edge cases covered |
| Day 32 (Aug 6) | Write tests for job creation, validation, and lifecycle endpoints | Job API tests passing | test_job_api.py committed | Invalid listing rejection verified |
| Day 33 (Aug 7) | Write frontend tests for JobCreationForm and RecruiterManagement | Frontend tests passing | JobCreationForm.test.jsx committed | Validation and submission flows covered |
| Day 34 (Aug 8) | Manual QA - company admin journey from signup to job posted | Company journey QA report written | qa_report_company_journey.md committed | All bugs logged with severity |
| Day 35 (Aug 9) | Document Company Portal feature set in USAGE.md Also run the weekly team sync: Week 7 retrospective on Company Portal progress | Docs updated Week 7 retro completed | USAGE.md updated; retro-week7.md committed | Reviewed by project lead Blockers logged as GitHub Issues |

✅ WEEK COMPLETED WHEN Company Admins can manage profile, branches and recruiters, and create/edit/archive job listings. View, funnel and hiring-trend analytics are computing correctly.

# WEEK 8

Days 36-40 (Aug 10 – Aug 14)  —  Company Portal - Recruiter Workflow

SPRINT GOAL Recruiters can manage candidates end-to-end - view applicants, schedule interviews, and communicate - with clean analytics for admins.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 36 (Aug 10) | Build applicant listing API for recruiters - filter by job/status | Applicant listing API working | recruiter_applicants router committed | Filters return correct applicant subsets |
| Day 37 (Aug 11) | Build resume download API with access-controlled signed URLs | Resume download working securely | resume_download endpoint committed | Only authorized recruiter can download |
| Day 38 (Aug 12) | Build shortlist/reject candidate API with status transition rules | Shortlist/reject API working | candidate_status endpoint committed | Invalid transitions blocked (e.g. rejected to selected) |
| Day 39 (Aug 13) | Build interview scheduling API - date, time, mode, interviewer | Interview scheduling API working | interviews router committed | Interview record created and retrievable |
| Day 40 (Aug 14) | Build offer/selection status API - mark selected, offer released, PPO Also run the weekly team sync: demo full recruiter candidate management flow | Offer status API working Recruiter flow demo delivered | offer_status endpoint committed; Demo notes in Wiki | Status changes reflected in student's tracker Team completes shortlist-to-offer flow live |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 36 (Aug 10) | Build Applicants view for recruiters - list with filters and search | Applicants view functional | ApplicantsView.jsx committed | Filter/search returns correct results |
| Day 37 (Aug 11) | Build candidate detail panel - resume preview, profile summary | Candidate detail panel functional | CandidateDetail.jsx committed | Resume preview renders correctly |
| Day 38 (Aug 12) | Build Shortlist/Reject action buttons with confirmation dialogs | Shortlist/reject actions functional | CandidateActions.jsx committed | Actions update status and list instantly |
| Day 39 (Aug 13) | Build Interview Scheduler UI - calendar picker, mode, interviewer selection | Interview scheduler functional | InterviewScheduler.jsx committed | Scheduled interview appears in candidate timeline |
| Day 40 (Aug 14) | Build Communication panel - send message/email to candidate, bulk notify Also run the weekly team sync: demo recruiter candidate management UI | Communication panel functional Recruiter UI demo delivered | CommunicationPanel.jsx committed; Demo notes in Wiki | Message send confirms and logs correctly Team validates recruiter workflow usability |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 36 (Aug 10) | Build candidate-job fit scoring for recruiters (skills match %) | Fit scoring working per candidate | candidate_fit_score.py committed | Scores align with manual review on test set |
| Day 37 (Aug 11) | Build applicant ranking API sorted by fit score for a job | Ranked applicant list API working | rank_applicants endpoint committed | Top candidates match expected ranking |
| Day 38 (Aug 12) | Build notification content generation for status-change emails (templated) | Notification templates generated | notification_templates.py committed | Templates render correctly with real data |
| Day 39 (Aug 13) | Improve hiring-trend analytics with company-hiring seasonality patterns | Seasonality analytics added | hiring_seasonality.py committed | Trend chart reflects seasonal pattern on test data |
| Day 40 (Aug 14) | Write documentation on candidate fit-scoring methodology for transparency Also run the weekly team sync: present candidate fit-scoring results to team | Fit-scoring methodology documented Fit-scoring demo delivered | fit_scoring_methodology.md committed; Demo notes in Wiki | Reviewed and approved by project lead Team reviews scoring fairness and accuracy |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 36 (Aug 10) | Write tests for applicant listing, shortlist/reject, and status transition APIs | Recruiter API tests passing | test_recruiter_api.py committed | Invalid status transitions verified as blocked |
| Day 37 (Aug 11) | Write tests for interview scheduling and offer status APIs | Scheduling/offer tests passing | test_interviews_api.py committed | Edge cases - overlapping interviews handled |
| Day 38 (Aug 12) | Write frontend tests for ApplicantsView and InterviewScheduler | Frontend tests passing | ApplicantsView.test.jsx committed | Filtering and scheduling flows covered |
| Day 39 (Aug 13) | Manual QA - full recruiter journey from applicant list to offer | Recruiter journey QA report written | qa_report_recruiter_journey.md committed | All bugs logged with severity |
| Day 40 (Aug 14) | Update USAGE.md and RBAC matrix with recruiter workflow details Also run the weekly team sync: Week 8 retrospective, Company Portal sign-off | Docs updated Company Portal sign-off | USAGE.md, rbac_matrix.md updated; retro-week8.md committed | Reviewed by project lead Team formally signs off on Company Portal MVP |

✅ WEEK COMPLETED WHEN Recruiters can view, rank, shortlist, interview and offer candidates end-to-end, with fit-scoring, notifications, and full test coverage. Company Portal MVP signed off.

# WEEK 9

Days 41-45 (Aug 15 – Aug 19)  —  College Portal - Admin & Coordinator Core

SPRINT GOAL College Admins can manage departments and coordinators, and Placement Coordinators can review and approve listings - the core human-verification workflow.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 41 (Aug 15) | Build department management API - create/edit departments per college | Department CRUD working | departments router committed | Departments correctly scoped per college |
| Day 42 (Aug 16) | Build Placement Coordinator account creation API (by College Admin) | Coordinator creation API working | coordinator_management endpoint committed | New coordinator can activate and log in |
| Day 43 (Aug 17) | Build listing review queue API - pending jobs/internships for approval | Review queue API working | review_queue endpoint committed | Only unapproved listings appear in queue |
| Day 44 (Aug 18) | Build approve/reject/edit listing API restricted to Placement Coordinator role | Approval API working with RBAC | listing_approval endpoint committed | Only Placement Coordinator role can approve |
| Day 45 (Aug 19) | Build pin/archive listing API for coordinators Also run the weekly team sync: demo department setup and coordinator approval flow | Pin/archive API working College Portal demo delivered | listing_pin endpoint committed; Demo notes in Wiki | Pinned listings sort to top of student view Team approves a test listing live |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 41 (Aug 15) | Build Department Management UI for College Admin | Department management functional | DepartmentManagement.jsx committed | Admin can create/edit departments |
| Day 42 (Aug 16) | Build Placement Coordinator account creation UI for College Admin | Coordinator creation UI functional | CoordinatorManagement.jsx committed | Admin can invite and view coordinators |
| Day 43 (Aug 17) | Build Listing Review Queue UI for Placement Coordinator | Review queue UI functional | ReviewQueue.jsx committed | Pending listings display with detail preview |
| Day 44 (Aug 18) | Build Approve/Reject/Edit action UI with reason/comment field | Approval actions functional | ApprovalActions.jsx committed | Reject requires a reason before submitting |
| Day 45 (Aug 19) | Build Pin/Archive toggle controls on listing cards for coordinators Also run the weekly team sync: demo College Portal review workflow to team | Pin/archive controls functional Review workflow demo delivered | PinArchiveControls.jsx committed; Demo notes in Wiki | Pinned listings show a visual badge Team validates coordinator UX |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 41 (Aug 15) | Build department-wise student search index for Placement Coordinators | Department search index working | department_search_index.py committed | Search returns correct department subset |
| Day 42 (Aug 16) | Build department performance metrics (placement rate, avg package) | Department metrics computed | department_metrics.py committed | Metrics match manually verified sample data |
| Day 43 (Aug 17) | Build auto-flagging for suspicious/spam listings before human review | Auto-flagging POC working | spam_flagging_poc.py committed | Flags 3 seeded spam listings correctly |
| Day 44 (Aug 18) | Note: flagging is advisory only - final approval always by Placement Coordinator | Advisory-only behavior documented and enforced | Flag confidence never bypasses human review | Verified flagged listings still require manual approval |
| Day 45 (Aug 19) | Build search intelligence improvements for coordinator student search (fuzzy match) Also run the weekly team sync: present department metrics and spam-flagging to team | Fuzzy search working for student search AI progress demo delivered | fuzzy_search.py committed; Demo notes in Wiki | Handles common name misspellings correctly Team confirms human-verification-only policy is respected |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 41 (Aug 15) | Write tests for department management and coordinator creation APIs | Department/coordinator tests passing | test_department_api.py committed | RBAC boundaries verified for College Admin |
| Day 42 (Aug 16) | Write tests for review queue, approval, and pin/archive APIs | Review workflow tests passing | test_review_workflow.py committed | Only coordinator role can approve, verified |
| Day 43 (Aug 17) | Write frontend tests for ReviewQueue and ApprovalActions | Frontend tests passing | ReviewQueue.test.jsx committed | Approve/reject flows covered |
| Day 44 (Aug 18) | Manual QA - full College Admin to Coordinator approval journey | College journey QA report written | qa_report_college_journey.md committed | All bugs logged with severity |
| Day 45 (Aug 19) | Update RBAC matrix and USAGE.md with College Portal details Also run the weekly team sync: Week 9 retrospective on College Portal progress | Docs updated Week 9 retro completed | rbac_matrix.md, USAGE.md updated; retro-week9.md committed | Reviewed by project lead Blockers logged as GitHub Issues |

✅ WEEK COMPLETED WHEN College Admins manage departments and coordinators; Placement Coordinators review, approve, reject, pin and archive listings. Human verification confirmed as the only approval path.

# WEEK 10

Days 46-50 (Aug 20 – Aug 24)  —  College Portal - Student Tracking & Reports

SPRINT GOAL Placement Coordinators can track students and generate reports; College Admins get platform-level reporting and settings control.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 46 (Aug 20) | Build student tracking API for coordinators - placement/internship status | Student tracking API working | student_tracking endpoint committed | Status reflects real application data |
| Day 47 (Aug 21) | Build department-wise and college-wide report generation API (Excel/CSV) | Report generation API working | reports router committed | Generated file opens correctly with expected columns |
| Day 48 (Aug 22) | Build monthly and annual report scheduling/aggregation API | Scheduled report aggregation working | report_scheduler.py committed | Monthly report matches manually summed data |
| Day 49 (Aug 23) | Build College Admin settings API - branding, notifications, access control | College settings API working | college_settings endpoint committed | Settings persist and apply correctly |
| Day 50 (Aug 24) | Build notification API - student selected, internship started events Also run the weekly team sync: demo student tracking and report generation | Notification triggers working Reports demo delivered | notifications router committed; Demo notes in Wiki | Event triggers correct notification record Team generates a sample report live |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 46 (Aug 20) | Build Student Tracking dashboard for Placement Coordinators | Student tracking UI functional | StudentTracking.jsx committed | Status badges reflect live data |
| Day 47 (Aug 21) | Build Reports page - export Excel/CSV, department and time-range filters | Reports UI functional | ReportsPage.jsx committed | Export button downloads correctly filtered file |
| Day 48 (Aug 22) | Build College Admin Settings page - branding, notifications, access control | Settings page functional | CollegeSettings.jsx committed | Changes save and reflect across portal |
| Day 49 (Aug 23) | Build Notification Center UI for coordinators and students | Notification center functional | NotificationCenter.jsx committed | New events appear without page refresh |
| Day 50 (Aug 24) | Build resume view access for coordinators within student tracking Also run the weekly team sync: demo College Admin settings and notifications | Resume view functional Settings demo delivered | ResumeViewPanel.jsx committed; Demo notes in Wiki | Coordinator can preview student resume Team validates notification delivery |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 46 (Aug 20) | Build placement-rate and package analytics for department reports | Analytics feeding into reports correctly | placement_analytics.py committed | Numbers match manual verification |
| Day 47 (Aug 21) | Build data export formatting logic - clean Excel with proper headers | Formatted Excel export working | excel_export_formatter.py committed | Exported file has correct headers and formatting |
| Day 48 (Aug 22) | Build anomaly detection for reporting data (missing/duplicate records) | Anomaly detection POC working | report_anomaly_detection.py committed | Flags 3 seeded anomalies correctly |
| Day 49 (Aug 23) | Support Aditee with cross-platform data validation for report accuracy | Validation script shared with QA | report_validation_helper.py committed | QA confirms validation logic is correct |
| Day 50 (Aug 24) | Document data pipeline from raw application data to final report Also run the weekly team sync: present report analytics accuracy results | Data pipeline documented Analytics demo delivered | report_data_pipeline.md committed; Demo notes in Wiki | Diagram reviewed by team Team confirms report numbers are trustworthy |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 46 (Aug 20) | Write tests for student tracking and report generation APIs | Tracking/report tests passing | test_reports_api.py committed | Generated report content verified against fixtures |
| Day 47 (Aug 21) | Write tests for College Admin settings and notification APIs | Settings/notification tests passing | test_college_settings.py committed | Settings persistence verified |
| Day 48 (Aug 22) | Manual QA - verify Excel/CSV report content matches actual DB data | Report accuracy QA completed | qa_report_accuracy.md committed | Spot-checked 10 records match exactly |
| Day 49 (Aug 23) | Write frontend tests for ReportsPage and NotificationCenter | Frontend tests passing | ReportsPage.test.jsx committed | Export and notification flows covered |
| Day 50 (Aug 24) | Update USAGE.md with reporting and notification features Also run the weekly team sync: Week 10 retrospective, College Portal sign-off | Docs updated College Portal sign-off | USAGE.md updated; retro-week10.md committed | Reviewed by project lead Team formally signs off on College Portal MVP |

✅ WEEK COMPLETED WHEN Student tracking, Excel/CSV reports, monthly/annual aggregation, College Admin settings and notifications all working and verified for accuracy. College Portal MVP signed off.

# WEEK 11

Days 51-55 (Aug 25 – Aug 29)  —  Resume Intelligence - Upload & Parsing

SPRINT GOAL Students can upload resumes and receive accurate parsing, scoring, and structured profile extraction in production quality.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 51 (Aug 25) | Build resume upload API with file-type/size validation and storage | Resume upload API working | resume_upload endpoint committed | Only PDF/DOCX under size limit accepted |
| Day 52 (Aug 26) | Build resume versioning API - store and list multiple versions per student | Resume versioning API working | resume_versions endpoint committed | Multiple versions retrievable in order |
| Day 53 (Aug 27) | Build API to trigger AI parsing service on upload and store results | Parsing trigger + storage working | resume_parse_trigger endpoint committed | Parsed data saved against correct resume version |
| Day 54 (Aug 28) | Build resume score storage and retrieval API | Resume score API working | resume_score endpoint committed | Score persists and returns with resume |
| Day 55 (Aug 29) | Build endpoint to fetch structured resume data for profile auto-fill Also run the weekly team sync: demo resume upload-to-parsing-to-score pipeline | Auto-fill API working Pipeline demo delivered | resume_autofill endpoint committed; Demo notes in Wiki | Profile fields populate from parsed resume Team uploads a real resume live |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 51 (Aug 25) | Build Resume Upload UI with drag-and-drop and progress indicator | Upload UI functional | ResumeUpload.jsx committed | Upload shows progress and success state |
| Day 52 (Aug 26) | Build Resume Version History UI - view/switch between versions | Version history UI functional | ResumeVersions.jsx committed | Switching versions updates displayed data |
| Day 53 (Aug 27) | Build Resume Score display - visual breakdown of scoring factors | Score display functional | ResumeScoreCard.jsx committed | Score and factors render clearly |
| Day 54 (Aug 28) | Build profile auto-fill review screen after resume parsing | Auto-fill review UI functional | AutoFillReview.jsx committed | Student can confirm/edit parsed fields |
| Day 55 (Aug 29) | Build Resume Templates gallery UI (selection screen) Also run the weekly team sync: demo resume upload and scoring experience | Templates gallery functional Resume UX demo delivered | ResumeTemplates.jsx committed; Demo notes in Wiki | Templates preview correctly before selection Team validates upload flow smoothness |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 51 (Aug 25) | Productionize resume parsing pipeline - robust error handling for malformed files | Production-grade parser deployed | resume_parser_v2.py committed | Handles 10 malformed test files gracefully |
| Day 52 (Aug 26) | Build resume scoring algorithm - completeness, keyword relevance, formatting | Scoring algorithm working | resume_scoring.py committed | Scores align with manual review on test set |
| Day 53 (Aug 27) | Build resume-to-profile field mapping (skills, education, experience, projects) | Field mapping working accurately | resume_field_mapping.py committed | Maps correctly on 10 diverse test resumes |
| Day 54 (Aug 28) | Build ATS-compatibility check logic (formatting/parsing risk detection) | ATS check logic working | ats_check.py committed | Correctly flags 5 seeded ATS-risk resumes |
| Day 55 (Aug 29) | Optimize parsing pipeline performance for concurrent uploads Also run the weekly team sync: present resume scoring and ATS check accuracy | Parsing performance improved AI accuracy demo delivered | Performance benchmark documented; Demo notes in Wiki | Handles 20 concurrent uploads under target latency Team reviews scoring fairness |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 51 (Aug 25) | Write tests for resume upload, versioning, and parsing-trigger APIs | Resume API tests passing | test_resume_api.py committed | Invalid file types rejected in tests |
| Day 52 (Aug 26) | Build a test corpus of 30 diverse resumes for parsing accuracy testing | Test resume corpus assembled | test_resumes/ committed | Corpus covers varied formats and layouts |
| Day 53 (Aug 27) | Run parsing accuracy evaluation against test corpus, report results | Parsing accuracy report generated | parsing_accuracy_report.md committed | Accuracy % documented per field type |
| Day 54 (Aug 28) | Write frontend tests for ResumeUpload and ResumeScoreCard | Frontend tests passing | ResumeUpload.test.jsx committed | Upload and score display flows covered |
| Day 55 (Aug 29) | Update USAGE.md with Resume Intelligence features Also run the weekly team sync: Week 11 retrospective on parsing accuracy | Docs updated Week 11 retro completed | USAGE.md updated; retro-week11.md committed | Reviewed by project lead Accuracy gaps logged as GitHub Issues |

✅ WEEK COMPLETED WHEN Resumes upload, version, parse and score reliably against a 30-resume test corpus, with ATS checks and profile auto-fill all functioning and documented.

# WEEK 12

Days 56-60 (Aug 30 – Sep 3)  —  Resume Intelligence - Builder & Premium Tools

SPRINT GOAL Students can build resumes from templates, access premium AI optimization, and manage multiple resume versions confidently.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 56 (Aug 30) | Build resume builder save/draft API - structured sections stored as JSON | Resume builder draft API working | resume_builder endpoint committed | Draft saves and reloads correctly |
| Day 57 (Aug 31) | Build resume export API - generate PDF/DOCX from builder data | Resume export API working | resume_export endpoint committed | Exported file matches builder content |
| Day 58 (Sep 1) | Build premium feature gating middleware (subscription/entitlement check) | Premium gating working | premium_gate dependency committed | Non-premium users blocked from premium endpoints |
| Day 59 (Sep 2) | Build AI Resume Optimization request/response API (premium) | Optimization API working | resume_optimize endpoint committed | Returns improved resume suggestions |
| Day 60 (Sep 3) | Build resume template metadata API - list, preview, categories Also run the weekly team sync: demo resume builder and premium optimization flow | Template metadata API working Builder demo delivered | resume_templates endpoint committed; Demo notes in Wiki | Templates filterable by category Team builds and exports a resume live |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 56 (Aug 30) | Build Resume Builder UI - section-by-section editable form | Resume builder UI functional | ResumeBuilder.jsx committed | Sections save incrementally without data loss |
| Day 57 (Aug 31) | Build live resume preview pane synced with builder input | Live preview functional | ResumePreview.jsx committed | Preview updates in real time as user types |
| Day 58 (Sep 1) | Build template selection and switching within the builder | Template switching functional | TemplateSwitcher.jsx committed | Switching preserves entered content |
| Day 59 (Sep 2) | Build Premium upsell UI - paywall screen for AI optimization | Premium upsell UI functional | PremiumUpsell.jsx committed | Non-premium users see clear upgrade path |
| Day 60 (Sep 3) | Build AI Resume Optimization results UI - before/after comparison Also run the weekly team sync: demo full resume builder and premium experience | Optimization results UI functional Premium UX demo delivered | OptimizationResults.jsx committed; Demo notes in Wiki | Before/after shown side-by-side clearly Team validates premium upgrade flow |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 56 (Aug 30) | Build AI resume optimization logic - suggest phrasing, quantify achievements | Optimization logic working | resume_optimizer.py committed | Suggestions improve clarity on 10 test resumes |
| Day 57 (Aug 31) | Build resume-template content mapping (fill template with structured data) | Template mapping working | template_mapper.py committed | Maps correctly across 5 template types |
| Day 58 (Sep 1) | Build resume comparison scoring - before/after optimization score delta | Comparison scoring working | optimization_score_delta.py committed | Score improves consistently after optimization |
| Day 59 (Sep 2) | Build AI Cover Letter Generator - resume + job description to cover letter | Cover letter generator working | cover_letter_generator.py committed | Generates coherent letter from test inputs |
| Day 60 (Sep 3) | Write prompt engineering documentation for resume optimization prompts Also run the weekly team sync: present AI optimization and cover letter generator results | Prompt docs published AI feature demo delivered | resume_prompts.md committed; Demo notes in Wiki | Reviewed and approved by project lead Team reviews output quality |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 56 (Aug 30) | Write tests for resume builder save/draft and export APIs | Builder API tests passing | test_resume_builder_api.py committed | Draft persistence verified across sessions |
| Day 57 (Aug 31) | Write tests for premium gating middleware across all premium endpoints | Premium gating tests passing | test_premium_gate.py committed | Non-premium access correctly blocked in all cases |
| Day 58 (Sep 1) | Write frontend tests for ResumeBuilder and OptimizationResults | Frontend tests passing | ResumeBuilder.test.jsx committed | Section editing and preview sync covered |
| Day 59 (Sep 2) | Evaluate AI-optimized resumes for quality/tone consistency across 10 samples | Optimization quality report written | optimization_quality_report.md committed | Findings shared with Dheeraj for tuning |
| Day 60 (Sep 3) | Update USAGE.md with Resume Builder and Premium feature docs Also run the weekly team sync: Week 12 retrospective, Resume Intelligence sign-off | Docs updated Resume Intelligence sign-off | USAGE.md updated; retro-week12.md committed | Reviewed by project lead Team formally signs off on Resume Intelligence MVP |

✅ WEEK COMPLETED WHEN Resume Builder, templates, export, premium gating, AI optimization and cover-letter generation are all working with verified output quality. Resume Intelligence MVP signed off.

# WEEK 13

Days 61-65 (Sep 4 – Sep 8)  —  AI Recommendation Engine - Core

SPRINT GOAL The unified recommendation engine serves job/internship recommendations across student, external-student, and dashboard surfaces.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 61 (Sep 4) | Build unified recommendation API gateway - single endpoint for all surfaces | Recommendation gateway API working | recommendation_gateway endpoint committed | Serves student, external, and dashboard requests consistently |
| Day 62 (Sep 5) | Build caching layer for recommendation results (Redis-backed) | Recommendation caching working | recommendation_cache.py committed | Cache hit reduces response time measurably |
| Day 63 (Sep 6) | Build recommendation feedback API - track click-through and apply-through | Feedback tracking API working | recommendation_feedback endpoint committed | Feedback events recorded correctly |
| Day 64 (Sep 7) | Build A/B testing scaffold for comparing recommendation strategies | A/B testing scaffold working | ab_testing.py committed | Requests split correctly between variants |
| Day 65 (Sep 8) | Integrate recommendation engine with notification triggers (new match alerts) Also run the weekly team sync: demo unified recommendation gateway across all surfaces | Match-alert notifications working Gateway demo delivered | match_alert_trigger.py committed; Demo notes in Wiki | New strong match triggers a notification Team validates consistent results across surfaces |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 61 (Sep 4) | Build Recommended Jobs/Internships section for College Student dashboard | Recommended section functional | RecommendedJobs.jsx committed | Section populates with live recommendation data |
| Day 62 (Sep 5) | Build Recommended section for External Student dashboard | External recommendations functional | ExternalRecommended.jsx committed | Section shows AI-recommended and trending items |
| Day 63 (Sep 6) | Build Trending Jobs/Internships widget for dashboards | Trending widget functional | TrendingWidget.jsx committed | Widget reflects live trending data |
| Day 64 (Sep 7) | Build recommendation feedback capture (click, apply) wired to backend | Feedback capture functional | Feedback tracking wired in UI | Click/apply events recorded correctly in backend |
| Day 65 (Sep 8) | Build empty/loading states for recommendation sections Also run the weekly team sync: demo recommendation sections across dashboards | Empty/loading states functional Recommendations UI demo delivered | RecommendationStates.jsx committed; Demo notes in Wiki | New users see helpful empty-state messaging Team confirms sections load correctly for all roles |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 61 (Sep 4) | Consolidate skill-based, resume-based, and feedback-based scoring into one engine | Unified scoring engine implemented | unified_recommender.py committed | Single call returns blended score per listing |
| Day 62 (Sep 5) | Tune recommendation weighting using Week 5-8 feedback signal data | Weighting tuned and validated | recommender_weights.json committed | Precision improves on held-out test set |
| Day 63 (Sep 6) | Build cold-start recommendation strategy for brand-new users | Cold-start strategy working | cold_start_recommender.py committed | New users receive reasonable recommendations immediately |
| Day 64 (Sep 7) | Build AI Skill Gap Analysis feature - target role vs current skills | Skill gap analysis working | skill_gap_analysis.py committed | Returns accurate missing-skill list for test profiles |
| Day 65 (Sep 8) | Build AI Learning Suggestions - courses/resources for skill gaps Also run the weekly team sync: present unified engine performance and skill-gap results | Learning suggestions working Engine performance demo delivered | learning_suggestions.py committed; Demo notes in Wiki | Suggestions relevant to identified skill gaps Team reviews precision/recall metrics |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 61 (Sep 4) | Write tests for the unified recommendation gateway and caching layer | Gateway/cache tests passing | test_recommendation_gateway.py committed | Cache hit/miss behavior verified |
| Day 62 (Sep 5) | Build evaluation harness measuring recommendation precision/recall on test set | Evaluation harness built and running | eval_harness.py committed | Metrics reproducible across runs |
| Day 63 (Sep 6) | Write frontend tests for RecommendedJobs and TrendingWidget | Frontend tests passing | RecommendedJobs.test.jsx committed | Data rendering and empty states covered |
| Day 64 (Sep 7) | Manual QA - verify recommendations are relevant across 10 diverse test profiles | Relevance QA report written | qa_report_recommendations.md committed | Findings shared with Dheeraj for tuning |
| Day 65 (Sep 8) | Update USAGE.md with Recommendation Engine documentation Also run the weekly team sync: Week 13 retrospective on recommendation quality | Docs updated Week 13 retro completed | USAGE.md updated; retro-week13.md committed | Reviewed by project lead Quality gaps logged as GitHub Issues |

✅ WEEK COMPLETED WHEN Unified recommendation engine live across all dashboards with caching, feedback tracking, cold-start handling, skill-gap analysis and measured precision/recall.

# WEEK 14

Days 66-70 (Sep 9 – Sep 13)  —  AI Career Assistant & Premium Intelligence

SPRINT GOAL External students get a full AI Career Assistant - roadmap, cover letters, and career coaching - as premium differentiators.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 66 (Sep 9) | Build AI Career Roadmap API - stores and serves generated roadmaps per user | Career roadmap API working | career_roadmap endpoint committed | Roadmap persists and retrieves correctly |
| Day 67 (Sep 10) | Build AI Cover Letter API - generate and store cover letters per application | Cover letter API working | cover_letter endpoint committed | Generated letter linked to correct application |
| Day 68 (Sep 11) | Build premium entitlement management API - upgrade/downgrade, feature flags | Entitlement API working | entitlements endpoint committed | Feature access updates immediately on upgrade |
| Day 69 (Sep 12) | Build AI Career Coach conversational API - session-based Q&A | Career coach API working | career_coach endpoint committed | Multi-turn conversation context preserved |
| Day 70 (Sep 13) | Build priority-recommendation and advanced-analytics premium endpoints Also run the weekly team sync: demo AI Career Assistant premium feature set | Premium endpoints working Career Assistant demo delivered | premium_features router committed; Demo notes in Wiki | Only premium users receive advanced data Team walks through full premium journey |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 66 (Sep 9) | Build AI Career Roadmap UI - visual timeline of suggested steps | Career roadmap UI functional | CareerRoadmap.jsx committed | Timeline renders roadmap steps clearly |
| Day 67 (Sep 10) | Build AI Cover Letter Generator UI - input job, generate, edit, download | Cover letter UI functional | CoverLetterGenerator.jsx committed | Generated letter editable and downloadable |
| Day 68 (Sep 11) | Build AI Career Coach chat UI - conversational interface | Career coach chat UI functional | CareerCoachChat.jsx committed | Messages send/receive with conversation history |
| Day 69 (Sep 12) | Build Premium Features hub page - overview of all premium tools | Premium hub page functional | PremiumHub.jsx committed | All premium features accessible from one place |
| Day 70 (Sep 13) | Build unlimited job alerts settings UI (premium) Also run the weekly team sync: demo full AI Career Assistant UI experience | Job alerts settings functional Career Assistant UX demo delivered | JobAlertsSettings.jsx committed; Demo notes in Wiki | Alert preferences save and apply correctly Team validates premium UX quality |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 66 (Sep 9) | Build AI Career Roadmap generation logic - milestones based on target role | Roadmap generation working | career_roadmap_generator.py committed | Roadmap logically sequenced for test target roles |
| Day 67 (Sep 10) | Refine AI Cover Letter Generator with job-specific tone/keyword alignment | Cover letter quality improved | cover_letter_generator_v2.py committed | Letters align to job keywords on test set |
| Day 68 (Sep 11) | Build AI Career Coach conversational logic with context/session memory | Career coach logic working | career_coach_engine.py committed | Maintains context across 5-turn test conversation |
| Day 69 (Sep 12) | Build priority-recommendation logic - boosted relevance for premium users | Priority recommendation logic working | priority_recommender.py committed | Premium users see measurably better-ranked results |
| Day 70 (Sep 13) | Build advanced analytics computation for premium external students Also run the weekly team sync: present AI Career Assistant output quality | Advanced analytics working AI quality demo delivered | advanced_analytics.py committed; Demo notes in Wiki | Metrics computed correctly on test accounts Team reviews roadmap and coach output quality |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 66 (Sep 9) | Write tests for career roadmap, cover letter, and entitlement APIs | Premium API tests passing | test_premium_api.py committed | Entitlement checks verified across endpoints |
| Day 67 (Sep 10) | Write tests for AI Career Coach session/context handling | Career coach tests passing | test_career_coach.py committed | Multi-turn context verified in test conversation |
| Day 68 (Sep 11) | Write frontend tests for CareerRoadmap and CareerCoachChat | Frontend tests passing | CareerRoadmap.test.jsx committed | Rendering and chat interaction covered |
| Day 69 (Sep 12) | Manual QA - evaluate roadmap/cover-letter/coach quality across 10 personas | Quality QA report written | qa_report_ai_assistant.md committed | Findings shared with Dheeraj for tuning |
| Day 70 (Sep 13) | Update USAGE.md with full Premium/AI Career Assistant documentation Also run the weekly team sync: Week 14 retrospective, Recommendation Engine sign-off | Docs updated Recommendation Engine sign-off | USAGE.md updated; retro-week14.md committed | Reviewed by project lead Team formally signs off on full AI feature set |

✅ WEEK COMPLETED WHEN AI Career Roadmap, Cover Letter Generator, Career Coach, and premium analytics all live and quality-checked. Full Recommendation Engine and AI Career Assistant MVP signed off.

# WEEK 15

Days 71-75 (Sep 14 – Sep 18)  —  Excel Automation - Export & Sync

SPRINT GOAL Placement Coordinators can export, auto-sync, and back up placement data across Excel and Google Sheets reliably.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 71 (Sep 14) | Build Excel export API using openpyxl with formatted headers/styling | Excel export API working | excel_export endpoint committed | Exported file opens cleanly in Excel with formatting |
| Day 72 (Sep 15) | Build Google Sheets API integration - OAuth setup and write access | Google Sheets integration working | google_sheets_client.py committed | Test data writes successfully to a live sheet |
| Day 73 (Sep 16) | Build auto-sync scheduler - periodic push of data to linked Google Sheet | Auto-sync scheduler working | auto_sync_scheduler.py committed | Sheet updates automatically on schedule |
| Day 74 (Sep 17) | Build sync-status tracking API - last synced time, success/failure state | Sync status API working | sync_status endpoint committed | Status accurately reflects last sync attempt |
| Day 75 (Sep 18) | Build conflict handling for manual edits made directly in Google Sheets Also run the weekly team sync: demo Excel export and Google Sheets auto-sync | Conflict handling logic working Sync demo delivered | sync_conflict_handler.py committed; Demo notes in Wiki | Manual edits are not silently overwritten Team verifies data appears correctly in live sheet |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 71 (Sep 14) | Build Excel/Sheets export settings UI - choose format, columns, filters | Export settings UI functional | ExportSettings.jsx committed | Selected options reflected in exported file |
| Day 72 (Sep 15) | Build Google Sheets connection UI - OAuth consent, link/unlink sheet | Sheets connection UI functional | GoogleSheetsConnect.jsx committed | Coordinator can link and unlink a sheet |
| Day 73 (Sep 16) | Build Sync Status Dashboard - last sync time, success/failure indicators | Sync dashboard functional | SyncStatusDashboard.jsx committed | Dashboard reflects real sync status live |
| Day 74 (Sep 17) | Build manual Sync Now trigger button with progress feedback | Manual sync trigger functional | SyncNowButton.jsx committed | Triggering sync shows progress and completion |
| Day 75 (Sep 18) | Build backup/restore UI - list backups, restore to a selected point Also run the weekly team sync: demo sync status dashboard and manual sync controls | Backup/restore UI functional Sync UI demo delivered | BackupRestore.jsx committed; Demo notes in Wiki | Restoring a backup updates data correctly Team validates sync status accuracy |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 71 (Sep 14) | Build data transformation layer - normalize DB records into Excel/Sheets rows | Transformation layer working | excel_data_transformer.py committed | Output rows match expected schema on test data |
| Day 72 (Sep 15) | Build deduplication logic before export to prevent duplicate rows | Dedup-before-export working | export_dedup.py committed | No duplicate rows in exported test file |
| Day 73 (Sep 16) | Build data-integrity validation comparing DB source vs exported/synced data | Data integrity validation working | data_integrity_check.py committed | Validation catches 3 seeded mismatch cases |
| Day 74 (Sep 17) | Support Gaurav with conflict-resolution logic for concurrent sheet edits | Conflict-resolution logic reviewed and improved | sync_conflict_handler.py updated | Handles simultaneous edit test case correctly |
| Day 75 (Sep 18) | Document the full Excel/Sheets sync architecture for maintainability Also run the weekly team sync: present data integrity validation results | Sync architecture documented Integrity demo delivered | excel_sync_architecture.md committed; Demo notes in Wiki | Reviewed and approved by project lead Team confirms confidence in synced data accuracy |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 71 (Sep 14) | Write tests for Excel export API - verify structure, formatting, content | Excel export tests passing | test_excel_export.py committed | Exported file structure matches spec |
| Day 72 (Sep 15) | Write tests for Google Sheets sync and conflict-handling logic | Sync tests passing | test_sheets_sync.py committed | Conflict scenarios verified as handled correctly |
| Day 73 (Sep 16) | Write frontend tests for ExportSettings and SyncStatusDashboard | Frontend tests passing | ExportSettings.test.jsx committed | Settings and status display covered |
| Day 74 (Sep 17) | Manual QA - full export-sync-backup-restore cycle with real data | Full cycle QA report written | qa_report_excel_sync.md committed | All bugs logged with severity |
| Day 75 (Sep 18) | Update USAGE.md with Excel Automation and Google Sheets Sync docs Also run the weekly team sync: Week 15 retrospective on Excel Automation progress | Docs updated Week 15 retro completed | USAGE.md updated; retro-week15.md committed | Reviewed by project lead Blockers logged as GitHub Issues |

✅ WEEK COMPLETED WHEN Excel export, Google Sheets auto-sync, sync-status tracking and conflict handling all working, with data integrity validated end-to-end.

# WEEK 16

Days 76-80 (Sep 19 – Sep 23)  —  Excel Automation - Backup & Archive System

SPRINT GOAL Data is safely backed up and restorable, and the archive system keeps historical placement data organized and accessible.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 76 (Sep 19) | Build automated backup scheduling API - daily/weekly snapshot creation | Backup scheduling API working | backup_scheduler endpoint committed | Snapshots created automatically on schedule |
| Day 77 (Sep 20) | Build backup storage integration - versioned snapshots in object storage | Backup storage working | backup_storage_client.py committed | Snapshots retrievable by date |
| Day 78 (Sep 21) | Build restore-from-backup API with rollback safety checks | Restore API working safely | restore_backup endpoint committed | Restore requires confirmation, logs the action |
| Day 79 (Sep 22) | Build archive system API - move stale listings/data to archive tables | Archive system API working | archive_data endpoint committed | Archived records excluded from active queries |
| Day 80 (Sep 23) | Build archive retrieval API for historical reporting needs Also run the weekly team sync: demo backup, restore, and archive system end-to-end | Archive retrieval API working Backup/archive demo delivered | archive_retrieval endpoint committed; Demo notes in Wiki | Historical data retrievable without affecting live tables Team performs a live restore from backup |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 76 (Sep 19) | Build Backup Schedule settings UI - frequency, retention period | Backup settings UI functional | BackupScheduleSettings.jsx committed | Settings save and apply to scheduler |
| Day 77 (Sep 20) | Build Backup History list UI - browse and select snapshots | Backup history UI functional | BackupHistory.jsx committed | List shows all snapshots with timestamps |
| Day 78 (Sep 21) | Build Restore confirmation flow with clear warning messaging | Restore confirmation UI functional | RestoreConfirmation.jsx committed | User must explicitly confirm before restore executes |
| Day 79 (Sep 22) | Build Archive browsing UI - view archived listings/records | Archive browsing UI functional | ArchiveBrowser.jsx committed | Archived records viewable and searchable |
| Day 80 (Sep 23) | Build Data Health indicator - surface backup/sync/archive status at a glance Also run the weekly team sync: demo backup history and archive browsing UI | Data health indicator functional Backup/archive UI demo delivered | DataHealthIndicator.jsx committed; Demo notes in Wiki | Indicator accurately reflects system state Team validates restore confirmation UX |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 76 (Sep 19) | Build archive-candidate detection - identify stale/expired listings automatically | Archive detection logic working | archive_candidate_detector.py committed | Correctly flags expired test listings |
| Day 77 (Sep 20) | Build backup integrity verification - checksum/validation on each snapshot | Backup verification working | backup_integrity_check.py committed | Corrupted snapshot detected in test scenario |
| Day 78 (Sep 21) | Build historical trend analytics using archived data (multi-year placement trends) | Historical trend analytics working | historical_trends.py committed | Trend chart data spans archived + live records correctly |
| Day 79 (Sep 22) | Optimize archive query performance for large historical datasets | Archive query performance improved | Performance benchmark documented | Historical queries return under target latency |
| Day 80 (Sep 23) | Document archive lifecycle - when data moves from active to archived Also run the weekly team sync: present historical trend analytics from archived data | Archive lifecycle documented Historical analytics demo delivered | archive_lifecycle.md committed; Demo notes in Wiki | Reviewed and approved by project lead Team reviews multi-year trend accuracy |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 76 (Sep 19) | Write tests for backup scheduling, storage, and restore APIs | Backup/restore tests passing | test_backup_restore.py committed | Restore correctness verified against known snapshot |
| Day 77 (Sep 20) | Write tests for archive system - archiving, retrieval, exclusion from live queries | Archive tests passing | test_archive_system.py committed | Archived records confirmed excluded from live queries |
| Day 78 (Sep 21) | Write frontend tests for BackupHistory and ArchiveBrowser | Frontend tests passing | BackupHistory.test.jsx committed | Snapshot listing and restore flow covered |
| Day 79 (Sep 22) | Manual QA - simulate data-loss scenario and verify full recovery | Disaster-recovery QA report written | qa_report_disaster_recovery.md committed | Full recovery confirmed from backup |
| Day 80 (Sep 23) | Update USAGE.md with Backup, Restore and Archive documentation Also run the weekly team sync: Week 16 retrospective, Excel Automation sign-off | Docs updated Excel Automation sign-off | USAGE.md updated; retro-week16.md committed | Reviewed by project lead Team formally signs off on Excel Automation MVP |

✅ WEEK COMPLETED WHEN Automated backups, safe restore, and a working archive system are all verified, including a simulated disaster-recovery drill. Excel Automation MVP signed off.

# WEEK 17

Days 81-85 (Sep 24 – Sep 28)  —  Analytics Dashboard

SPRINT GOAL Every role (Student, Coordinator, Company, Super Admin) has an accurate, real-time analytics dashboard suited to their needs.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 81 (Sep 24) | Build platform-wide analytics aggregation API - growth, active jobs, revenue | Platform analytics API working | platform_analytics endpoint committed | Numbers match manually verified totals |
| Day 82 (Sep 25) | Build college-growth and company-growth analytics API for Super Admin | Growth analytics API working | growth_analytics endpoint committed | Growth trend matches historical record counts |
| Day 83 (Sep 26) | Build department-performance analytics API for College Admin/Coordinator | Department analytics API working | department_performance endpoint committed | Metrics scoped correctly per department |
| Day 84 (Sep 27) | Build company hiring-report analytics API - views, applicants, conversion | Hiring report API working | hiring_report endpoint committed | Conversion rates match manual calculation |
| Day 85 (Sep 28) | Optimize analytics queries with materialized views/caching for dashboard speed Also run the weekly team sync: demo full analytics stack across all 4 roles | Analytics query performance optimized Analytics demo delivered | Materialized views committed; Demo notes in Wiki | Dashboard loads under target latency with real data volume Team validates numbers across all dashboards |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 81 (Sep 24) | Build Super Admin Analytics Dashboard - platform growth, revenue charts | Super Admin analytics UI functional | SuperAdminAnalytics.jsx committed | Charts render live platform data correctly |
| Day 82 (Sep 25) | Build College Analytics Dashboard - department performance, placement rates | College analytics UI functional | CollegeAnalytics.jsx committed | Charts scoped correctly to logged-in college |
| Day 83 (Sep 26) | Build Company Analytics Dashboard - views, applicants, hiring funnel | Company analytics UI functional | CompanyAnalytics.jsx committed | Funnel chart matches backend data |
| Day 84 (Sep 27) | Build Student Analytics widgets - application success rate, profile strength | Student analytics widgets functional | StudentAnalyticsWidgets.jsx committed | Widgets reflect accurate personal data |
| Day 85 (Sep 28) | Integrate a charting library (recharts) consistently across all dashboards Also run the weekly team sync: demo all 4 analytics dashboards to the team | Consistent charting library integrated Full analytics UI demo delivered | Charting components standardized; Demo notes in Wiki | All dashboards use consistent chart styling Team confirms visual consistency and accuracy |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 81 (Sep 24) | Build predictive analytics POC - forecast placement trends for next quarter | Predictive analytics POC working | placement_forecast_poc.py committed | Forecast reasonably tracks historical pattern on test data |
| Day 82 (Sep 25) | Build anomaly detection for analytics data (sudden spikes/drops) | Anomaly detection working | analytics_anomaly_detection.py committed | Flags 3 seeded anomalies correctly |
| Day 83 (Sep 26) | Build insight-generation logic - auto-written summary of key analytics trends | Insight generation working | insight_generator.py committed | Generates coherent summary from test dataset |
| Day 84 (Sep 27) | Optimize recommendation-engine analytics feed (data used across dashboards) | Recommendation analytics feed optimized | recommendation_analytics_feed.py committed | Feed refreshes without performance degradation |
| Day 85 (Sep 28) | Document all analytics metrics - definitions, formulas, data sources Also run the weekly team sync: present predictive analytics and insight-generation results | Analytics metrics glossary documented AI analytics demo delivered | analytics_metrics_glossary.md committed; Demo notes in Wiki | Reviewed and approved by project lead Team reviews forecast and insight quality |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 81 (Sep 24) | Write tests validating platform, growth, and department analytics accuracy | Analytics API tests passing | test_analytics_api.py committed | Computed metrics match fixture data exactly |
| Day 82 (Sep 25) | Write frontend tests for all 4 analytics dashboards | Frontend analytics tests passing | Analytics dashboard tests committed | Chart rendering and data binding covered |
| Day 83 (Sep 26) | Manual QA - cross-check every dashboard metric against raw DB queries | Analytics accuracy QA report written | qa_report_analytics_accuracy.md committed | All discrepancies logged and resolved |
| Day 84 (Sep 27) | Performance test analytics endpoints under realistic data volume | Analytics performance test completed | performance_test_analytics.md committed | Response times meet target under load |
| Day 85 (Sep 28) | Update USAGE.md and metrics glossary with analytics documentation Also run the weekly team sync: Week 17 retrospective, Analytics Dashboard sign-off | Docs updated Analytics sign-off | USAGE.md, analytics_metrics_glossary.md updated; retro-week17.md committed | Reviewed by project lead Team formally signs off on Analytics MVP |

✅ WEEK COMPLETED WHEN All 4 role-specific analytics dashboards are live, accurate against raw data, performant under load, and include predictive insight generation. Analytics MVP signed off.

# WEEK 18

Days 86-90 (Sep 29 – Oct 3)  —  Full-Platform Testing & Hardening

SPRINT GOAL The complete platform undergoes full regression, security, and performance testing before deployment, with all critical bugs resolved.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 86 (Sep 29) | Fix all backend bugs identified in Week 1-17 code reviews and QA reports | Backend bug backlog cleared | Bug-fix PRs merged | All P0/P1 backend bugs closed |
| Day 87 (Sep 30) | Run security audit - SQL injection, auth bypass, rate limiting on all APIs | Security audit completed | security_audit_report.md committed | No critical vulnerabilities found or all resolved |
| Day 88 (Oct 1) | Implement API rate limiting across all public-facing endpoints | Rate limiting implemented platform-wide | rate_limiting middleware committed | Excessive requests correctly throttled in test |
| Day 89 (Oct 2) | Run database performance tuning - indexes, query optimization on hot paths | DB performance tuned | DB indexes and query fixes committed | Slow queries improved to under target latency |
| Day 90 (Oct 3) | Conduct load testing on core APIs (auth, search, recommendations) Also run the weekly team sync: review full backend hardening results with team | Load testing completed Hardening demo delivered | load_test_report.md committed; Demo notes in Wiki | APIs handle target concurrent user load Team confirms backend is production-ready |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 86 (Sep 29) | Fix all frontend bugs identified in Week 1-17 code reviews and QA reports | Frontend bug backlog cleared | Bug-fix PRs merged | All P0/P1 frontend bugs closed |
| Day 87 (Sep 30) | Run accessibility audit - keyboard navigation, screen reader labels, contrast | Accessibility audit completed | accessibility_audit_report.md committed | Critical accessibility issues resolved |
| Day 88 (Oct 1) | Optimize frontend bundle size and page load performance (code splitting) | Frontend performance optimized | Bundle optimization committed | Lighthouse performance score meets target |
| Day 89 (Oct 2) | Cross-browser testing - Chrome, Firefox, Safari, Edge compatibility check | Cross-browser testing completed | cross_browser_report.md committed | No blocking issues on any major browser |
| Day 90 (Oct 3) | Responsive design pass - verify all pages work on tablet/mobile widths Also run the weekly team sync: review full frontend hardening results with team | Responsive design verified Frontend hardening demo delivered | Responsive fixes committed; Demo notes in Wiki | All key pages usable on mobile viewport Team confirms frontend is production-ready |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 86 (Sep 29) | Fix AI/recommendation bugs and quality issues identified across Weeks 1-17 | AI bug backlog cleared | AI bug-fix PRs merged | All P0/P1 AI-related bugs closed |
| Day 87 (Sep 30) | Run bias/fairness check on recommendation and fit-scoring algorithms | Fairness audit completed | fairness_audit_report.md committed | No systematic bias found across test demographics |
| Day 88 (Oct 1) | Optimize AI service response latency for production load | AI latency optimized | AI performance benchmark documented | Response times meet target under concurrent load |
| Day 89 (Oct 2) | Verify human-verification-only policy is enforced everywhere AI is used | Policy compliance verified | policy_compliance_check.md committed | No AI action bypasses human approval anywhere in system |
| Day 90 (Oct 3) | Finalize AI service documentation - all models, prompts, and data sources Also run the weekly team sync: review AI hardening and policy compliance results | AI documentation finalized AI hardening demo delivered | AI_SERVICE_DOCS.md committed; Demo notes in Wiki | Reviewed and approved by project lead Team confirms AI service is production-ready |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 86 (Sep 29) | Run full regression test suite across backend, frontend, and AI service | Full regression suite executed | regression_test_report.md committed | 100% of critical-path tests passing |
| Day 87 (Sep 30) | Execute complete RBAC test matrix across all 7 roles one final time | Final RBAC verification completed | final_rbac_verification.md committed | All role/permission combinations confirmed correct |
| Day 88 (Oct 1) | Conduct end-to-end user-journey testing for all 4 portals | E2E journey testing completed | e2e_journey_report.md committed | All critical user journeys complete without errors |
| Day 89 (Oct 2) | Coordinate bug bash - all 4 members test the live staging environment together | Bug bash session completed | bug_bash_notes.md committed | All discovered issues logged and triaged |
| Day 90 (Oct 3) | Compile final test coverage report across the whole platform Also run the weekly team sync: Week 18 retrospective, full-platform testing sign-off | Final coverage report published Testing sign-off | final_coverage_report.md committed; retro-week18.md committed | Coverage % documented for all 3 codebases Team formally signs off - platform ready for deployment |

✅ WEEK COMPLETED WHEN Full regression, security, performance and accessibility testing complete. All P0/P1 bugs resolved across backend, frontend and AI service. Platform signed off as deployment-ready.

# WEEK 19

Days 91-95 (Oct 4 – Oct 8)  —  Production Deployment

SPRINT GOAL IIB India is deployed to production with monitoring, CI/CD, and rollback safety in place.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 91 (Oct 4) | Set up production infrastructure - Docker containers, reverse proxy, SSL | Production infrastructure provisioned | Production docker-compose/infra committed | HTTPS site reachable with valid certificate |
| Day 92 (Oct 5) | Set up production database with automated backups and connection pooling | Production DB configured | Production DB config committed | Backups scheduled, connection pool sized correctly |
| Day 93 (Oct 6) | Build production CI/CD pipeline - automated deploy on merge to main | Production CI/CD pipeline working | deploy.yml committed | Merge to main triggers successful deployment |
| Day 94 (Oct 7) | Set up application monitoring and alerting (uptime, error rate, latency) | Monitoring and alerting configured | Monitoring dashboard committed | Test alert fires correctly on simulated error spike |
| Day 95 (Oct 8) | Build rollback procedure - revert to previous stable release quickly Also run the weekly team sync: demo production deployment and monitoring dashboard | Rollback procedure documented and tested Deployment demo delivered | rollback_procedure.md committed; Demo notes in Wiki | Test rollback completes within target time Team confirms production site is live and monitored |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 91 (Oct 4) | Build and optimize production frontend build (minification, asset compression) | Production build optimized | Production build config committed | Build size and load time meet target |
| Day 92 (Oct 5) | Set up CDN for static asset delivery | CDN configured | CDN configuration committed | Assets served from CDN with correct cache headers |
| Day 93 (Oct 6) | Configure frontend environment variables for production API endpoints | Production frontend config set | Production .env committed (secrets excluded) | Frontend correctly targets production backend |
| Day 94 (Oct 7) | Run final visual QA pass on production build across key pages | Production visual QA completed | visual_qa_report.md committed | No visual regressions found on production build |
| Day 95 (Oct 8) | Set up frontend error tracking (e.g. Sentry) for production issues Also run the weekly team sync: demo production frontend performance and monitoring | Error tracking configured Frontend deployment demo delivered | Error tracking integration committed; Demo notes in Wiki | Test error appears correctly in tracking dashboard Team confirms frontend production quality |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 91 (Oct 4) | Deploy AI service to production with proper resource allocation | AI service deployed to production | AI production deployment committed | Production /ai/health returns 200 |
| Day 92 (Oct 5) | Set up AI model/prompt version tracking for production monitoring | AI version tracking configured | AI version tracking committed | Current model/prompt versions visible in monitoring |
| Day 93 (Oct 6) | Set up AI output monitoring - track quality/error signals in production | AI output monitoring configured | AI monitoring dashboard committed | Dashboard reflects live AI request outcomes |
| Day 94 (Oct 7) | Load test AI service under production-representative concurrent request volume | AI load test completed | ai_load_test_report.md committed | AI service handles target load within latency budget |
| Day 95 (Oct 8) | Prepare AI service rollback plan in case of production quality regression Also run the weekly team sync: demo AI service production readiness | AI rollback plan documented AI deployment demo delivered | ai_rollback_plan.md committed; Demo notes in Wiki | Reviewed and approved by project lead Team confirms AI service is production-ready |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 91 (Oct 4) | Write and execute production smoke test suite immediately post-deploy | Production smoke tests passing | smoke_test_production.py committed | All critical paths verified working on production |
| Day 92 (Oct 5) | Verify all monitoring/alerting fires correctly using simulated incidents | Monitoring verification completed | monitoring_verification_report.md committed | All simulated incidents triggered correct alerts |
| Day 93 (Oct 6) | Conduct final security scan on the live production environment | Production security scan completed | production_security_scan.md committed | No critical vulnerabilities found on live site |
| Day 94 (Oct 7) | Write incident response runbook - who does what if production breaks | Incident runbook published | INCIDENT_RUNBOOK.md committed | Reviewed and understood by all team members |
| Day 95 (Oct 8) | Update all documentation to reflect final production URLs/configuration Also run the weekly team sync: Week 19 retrospective, production deployment sign-off | Documentation finalized for production Deployment sign-off | README.md, USAGE.md updated; retro-week19.md committed | All doc links and instructions point to production Team formally signs off - platform live in production |

✅ WEEK COMPLETED WHEN IIB India is live in production with CI/CD, monitoring, alerting, rollback procedures and a verified incident-response runbook. Deployment formally signed off.

# WEEK 20

Days 96-100 (Oct 9 – Oct 13)  —  Final Demo & Project Closure

SPRINT GOAL The team delivers a polished, rehearsed, end-to-end demo of IIB India and formally closes out the 100-day sprint.

Gaurav Bhosale — Project Lead & Backend Architecture

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 96 (Oct 9) | Final backend code review - clean up debug code, unused endpoints, TODOs | Backend code cleaned and finalized | Cleanup PR merged | No debug prints or dead code remain |
| Day 97 (Oct 10) | Prepare backend architecture walkthrough for the final demo presentation | Architecture walkthrough prepared | Architecture slides/notes committed | Walkthrough rehearsed and timed |
| Day 98 (Oct 11) | Fix any last-minute bugs found during demo rehearsals | Final bugs resolved | Final bug-fix PRs merged | Demo rehearsal runs with zero backend errors |
| Day 99 (Oct 12) | Merge all remaining backend branches into main, tag final release | Final release tagged on main | v1.0.0 tag created | main branch matches production exactly |
| Day 100 (Oct 13) | Prepare post-launch backend roadmap - next 90 days of planned improvements Also run the weekly team sync: Final sign-off - confirm all 13 MVP feature areas are complete and stable | Post-launch roadmap drafted Final backend sign-off delivered | post_launch_roadmap.md committed; Final checklist signed | Reviewed and approved by team All backend MVP features verified stable |

Amey Nadkar — Frontend Lead & UI/UX

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 96 (Oct 9) | Final frontend polish - consistent spacing, animations, micro-interactions | Frontend polish completed | Final UI polish PR merged | UI feels cohesive and professional across all pages |
| Day 97 (Oct 10) | Prepare live demo script - exact click-path through all 4 portals | Demo script prepared | demo_script.md committed | Script covers a coherent under-5-minute story |
| Day 98 (Oct 11) | Rehearse full live demo with the team, time it, fix rough edges | Demo rehearsal completed | Rehearsal notes committed | Demo runs smoothly under time target |
| Day 99 (Oct 12) | Prepare demo fallback - recorded video backup in case of live issues | Demo backup video recorded | demo_backup.mp4 saved | Video covers full feature set as fallback |
| Day 100 (Oct 13) | Merge all remaining frontend branches into main, verify final build Also run the weekly team sync: Final sign-off - confirm frontend experience is demo-ready across all roles | Final frontend release verified Final frontend sign-off delivered | Final frontend build verified on main; Final checklist signed | Production build matches rehearsed demo exactly All frontend MVP features verified stable |

Dheeraj Sarfare — AI & Resume Intelligence

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 96 (Oct 9) | Final AI feature review - verify recommendation/resume/career tools are stable | AI feature review completed | AI stability checklist committed | All AI features perform consistently in rehearsal |
| Day 97 (Oct 10) | Prepare AI feature walkthrough narrative for the final demo | AI walkthrough narrative prepared | AI demo notes committed | Narrative explains AI value clearly to non-technical audience |
| Day 98 (Oct 11) | Fix any last-minute AI quality issues found during demo rehearsals | Final AI issues resolved | Final AI fix PRs merged | AI outputs consistent across rehearsal runs |
| Day 99 (Oct 12) | Merge all remaining AI service branches into main, tag final release | Final AI release tagged on main | AI v1.0.0 tag created | main branch AI service matches production exactly |
| Day 100 (Oct 13) | Prepare post-launch AI roadmap - planned model/data improvements Also run the weekly team sync: Final sign-off - confirm all AI features are complete, stable and policy-compliant | Post-launch AI roadmap drafted Final AI sign-off delivered | post_launch_ai_roadmap.md committed; Final checklist signed | Reviewed and approved by team Human-verification-only policy confirmed intact platform-wide |

Aditee Talekar — Testing, Documentation & QA

| Day | Task | Expected Output | Deliverable | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| Day 96 (Oct 9) | Run final full regression suite across the entire platform one last time | Final regression suite executed | final_regression_report.md committed | 100% critical-path tests passing before demo |
| Day 97 (Oct 10) | Compile the complete 100-Day Milestone Report summarizing all deliverables | 100-Day Milestone Report compiled | milestone_report_100day.md committed | Report covers all 20 weeks and 13 MVP features |
| Day 98 (Oct 11) | Finalize all documentation - README, USAGE, CONTRIBUTING, ROLES, runbooks | All documentation finalized | Full docs set committed | New team member could onboard from docs alone |
| Day 99 (Oct 12) | Coordinate final demo rehearsal timing and Q&A preparation with team | Demo Q&A prep completed | qa_prep_notes.md committed | Team can answer likely judge/stakeholder questions |
| Day 100 (Oct 13) | Verify every one of the 13 MVP features against the original feature list Also run the weekly team sync: Day 100 final milestone review and formal project sign-off | Full feature checklist verified Day 100 milestone review completed | final_feature_checklist.md committed; Day 100 milestone report committed to GitHub | All 13 core modules confirmed present and working All 4 team members formally sign off on project completion |

✅ WEEK COMPLETED WHEN All code merged to main and tagged v1.0.0, full regression suite passing, live demo rehearsed and backed up, complete documentation published, and all 13 MVP features formally verified. Project ADAG - IIB India sprint complete.

# 100-Day Summary — What Each Member Delivers

| Team Member | Role | Day 100 Deliverables |
| --- | --- | --- |
| Gaurav Bhosale | Project Lead & Backend Architecture | Backend architecture, database design, authentication & RBAC, all core APIs, production deployment & infrastructure, CI/CD pipeline |
| Amey Nadkar | Frontend Lead & UI/UX | React application, shared UI kit, all portal dashboards (Student/College/Company/Admin), responsive design, production frontend build |
| Dheeraj Sarfare | AI & Resume Intelligence | Resume parsing & scoring engine, unified recommendation engine, AI Career Assistant (roadmap, cover letter, coach), analytics intelligence, AI service deployment |
| Aditee Talekar | Testing, QA & Documentation | Full test suites (unit/integration/e2e), RBAC verification matrix, security & performance QA, complete documentation set, 100-Day Milestone Report |

✅ WEEK COMPLETED WHEN All code merged to main and tagged v1.0.0, full regression suite passing, live demo rehearsed with backup recording, complete documentation published, and all 13 MVP feature areas formally verified across Student, College, Company, and Super Admin roles.

IIB INDIA — Discover. Verify. Place.

Team ADAG  |  100-Day Product Development Sprint  |  2026