## Overview
3
IIB India — Team ADAG — 100-Day Sprint Overview (Sunday–Friday Weeks)
Total: 100 working days across 17 weeks (16 full 6-day weeks + 1 final 4-day week). Only Saturday is off.
| Week | Days | Phase(s) Covered | Dates
| Week 1 | 6 | Documentation, Research & Planning Foundation → Documentation, Research & Planning Foundation (Part 2) | Sun Jul 5 – Fri Jul 10
| Week 2 | 6 | Documentation, Research & Planning Foundation (Part 2) → Authentication Core | Sun Jul 12 – Fri Jul 17
| Week 3 | 6 | Authentication Core → Role-Based Access Control (RBAC) | Sun Jul 19 – Fri Jul 24
| Week 4 | 6 | Role-Based Access Control (RBAC) → Student Portal - Profile & Discovery | Sun Jul 26 – Fri Jul 31
| Week 5 | 6 | Student Portal - Profile & Discovery → Student Portal - Applications & Career Tools | Sun Aug 2 – Fri Aug 7
| Week 6 | 6 | Company Portal - Profile & Job Management → Company Portal - Recruiter Workflow | Sun Aug 9 – Fri Aug 14
| Week 7 | 6 | Company Portal - Recruiter Workflow → College Portal - Admin & Coordinator Core | Sun Aug 16 – Fri Aug 21
| Week 8 | 6 | College Portal - Admin & Coordinator Core → College Portal - Student Tracking & Reports | Sun Aug 23 – Fri Aug 28
| Week 9 | 6 | College Portal - Student Tracking & Reports → Resume Intelligence - Upload & Parsing | Sun Aug 30 – Fri Sep 4
| Week 10 | 6 | Resume Intelligence - Upload & Parsing → Resume Intelligence - Builder & Premium Tools | Sun Sep 6 – Fri Sep 11
| Week 11 | 6 | AI Recommendation Engine - Core → AI Career Assistant & Premium Intelligence | Sun Sep 13 – Fri Sep 18
| Week 12 | 6 | AI Career Assistant & Premium Intelligence → Excel Automation - Export & Sync | Sun Sep 20 – Fri Sep 25
| Week 13 | 6 | Excel Automation - Export & Sync → Excel Automation - Backup & Archive System | Sun Sep 27 – Fri Oct 2
| Week 14 | 6 | Excel Automation - Backup & Archive System → Analytics Dashboard | Sun Oct 4 – Fri Oct 9
| Week 15 | 6 | Analytics Dashboard → Full-Platform Testing & Hardening | Sun Oct 11 – Fri Oct 16
| Week 16 | 6 | Production Deployment → Final Demo & Project Closure | Sun Oct 18 – Fri Oct 23
| Week 17 | 4 | Final Demo & Project Closure | Sun Oct 25 – Wed Oct 28
| TOTAL | 100

## Week 1
IIB — Team ADAG — Week 1 Timeline (Sun Jul 5 – Fri Jul 10)
Phase(s) this week: Documentation, Research & Planning Foundation → Documentation, Research & Planning Foundation (Part 2) ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-07-05 | Project Lead & Backend Architecture | Research competitor & reference platforms (LinkedIn, Internshala, Naukri) focusing on backend architecture and multi-tenant patterns for colleges/companies/students. | Expected Output: Competitor & architecture research notes | Gaurav Bhosale | FALSE | Documentation, Research & Planning Foundation | Deliverable: competitor_research.md ¦ Acceptance: Covers 3+ platforms with concrete architecture takeaways
| Frontend Lead & UI/UX | Research existing job/internship portal UI/UX (LinkedIn, Internshala, Indeed) - navigation and discovery patterns. | Expected Output: UI/UX pattern research notes | Amey Nadkar | FALSE | Documentation, Research & Planning Foundation | Deliverable: ui_research_notes.md ¦ Acceptance: Covers 3+ reference products with annotated screenshots or notes
| AI & Resume Intelligence | Research resume parsing approaches and libraries (spaCy, pyresparser, LLM-based extraction) and compare accuracy/cost trade-offs. | Expected Output: Resume parsing comparison notes | Dheeraj Sarfare | FALSE | Documentation, Research & Planning Foundation | Deliverable: resume_parsing_research.md ¦ Acceptance: At least 3 approaches compared with a recommendation
| Testing, Documentation & QA | Draft the Project Vision & Problem Statement document (vision, problem statement, target users, value proposition). | Expected Output: Vision document v1 | Aditee Talekar | FALSE | Documentation, Research & Planning Foundation | Deliverable: vision_statement.md ¦ Acceptance: Reviewed and agreed by the whole team
2026-07-06 | Project Lead & Backend Architecture | Research and compare backend tech stack options (FastAPI vs Django, PostgreSQL vs MySQL, hosting/deployment choices). | Expected Output: Tech stack comparison document | Gaurav Bhosale | FALSE | Documentation, Research & Planning Foundation | Deliverable: tech_stack_comparison.md ¦ Acceptance: Pros/cons listed with a final recommendation and rationale
| Frontend Lead & UI/UX | Explore modern dashboard design systems for the Student/College/Company portals and shortlist a design language (Tailwind, shadcn/ui, etc.). | Expected Output: Design system shortlist document | Amey Nadkar | FALSE | Documentation, Research & Planning Foundation | Deliverable: design_system_options.md ¦ Acceptance: At least 2 options compared with a recommendation
| AI & Resume Intelligence | Research recommendation-engine approaches (rule-based scoring vs ML/embeddings) with a focus on solving cold-start. | Expected Output: Recommendation approach research doc | Dheeraj Sarfare | FALSE | Documentation, Research & Planning Foundation | Deliverable: recommendation_approach.md ¦ Acceptance: Launch approach chosen and justified
| Testing, Documentation & QA | Research data-privacy and compliance considerations for storing student, college, and company data. | Expected Output: Privacy research notes | Aditee Talekar | FALSE | Documentation, Research & Planning Foundation | Deliverable: privacy_notes.md ¦ Acceptance: Notes reviewed and flagged items assigned owners
2026-07-07 | Project Lead & Backend Architecture | Document the high-level system architecture and draft the multi-tenant data model approach (colleges, companies, students, roles). | Expected Output: Architecture overview + draft ER sketch | Gaurav Bhosale | FALSE | Documentation, Research & Planning Foundation | Deliverable: architecture_overview.md ¦ Acceptance: Reviewed and approved by the team
| Frontend Lead & UI/UX | Research wireframing approach and document the navigation flow for all 4 portals (Student, College, Company, Super Admin). | Expected Output: Draft navigation flow diagrams | Amey Nadkar | FALSE | Documentation, Research & Planning Foundation | Deliverable: navigation_flows.md ¦ Acceptance: Every portal has a documented top-level navigation flow
| AI & Resume Intelligence | Research the feasibility of aggregating and summarizing company reviews (Glassdoor, AmbitionBox, Indeed) using AI. | Expected Output: Review-aggregation research notes | Dheeraj Sarfare | FALSE | Documentation, Research & Planning Foundation | Deliverable: review_aggregation_research.md ¦ Acceptance: Notes cover data-source feasibility and summarization approach
| Testing, Documentation & QA | Research testing strategy and tooling options (pytest, Jest, end-to-end frameworks) suited to the chosen stack. | Expected Output: Testing strategy research document | Aditee Talekar | FALSE | Documentation, Research & Planning Foundation | Deliverable: testing_strategy_research.md ¦ Acceptance: A recommended tool per layer (unit/integration/E2E) is documented
2026-07-08 | Project Lead & Backend Architecture | Research authentication & RBAC approaches (JWT vs session-based, refresh-token strategy) suited to the platform's 7 roles. | Expected Output: Auth approach research note | Gaurav Bhosale | FALSE | Documentation, Research & Planning Foundation | Deliverable: auth_approach.md ¦ Acceptance: Approach chosen and justified in writing
| Frontend Lead & UI/UX | Research accessibility and responsive-design guidelines relevant to the platform's target users. | Expected Output: Accessibility guideline notes | Amey Nadkar | FALSE | Documentation, Research & Planning Foundation | Deliverable: accessibility_notes.md ¦ Acceptance: Notes reviewed and agreed as the team's baseline standard
| AI & Resume Intelligence | Document the AI microservice architecture plan, including its API contract boundary with the backend. | Expected Output: AI service architecture document | Dheeraj Sarfare | FALSE | Documentation, Research & Planning Foundation | Deliverable: ai_service_architecture.md ¦ Acceptance: Reviewed and approved by project lead
| Testing, Documentation & QA | Draft team responsibilities, success metrics, and documentation standards (README/CONTRIBUTING plan). | Expected Output: Team charter draft | Aditee Talekar | FALSE | Documentation, Research & Planning Foundation | Deliverable: team_charter.md ¦ Acceptance: Every team member's responsibilities are named
2026-07-09 | Project Lead & Backend Architecture | Write the API design standards & naming-convention document; finalize the multi-repo structure plan. | Expected Output: API standards document | Gaurav Bhosale | FALSE | Documentation, Research & Planning Foundation | Deliverable: api_standards.md ¦ Acceptance: Team sign-off recorded
| Frontend Lead & UI/UX | Draft the shared UI component inventory (buttons, tables, modals, forms) required across the platform. | Expected Output: Component inventory document | Amey Nadkar | FALSE | Documentation, Research & Planning Foundation | Deliverable: component_inventory.md ¦ Acceptance: Inventory covers every screen type identified in the navigation flows
| AI & Resume Intelligence | Research skill-taxonomy design and embedding-model options for resume-to-listing matching. | Expected Output: Skill-matching research notes | Dheeraj Sarfare | FALSE | Documentation, Research & Planning Foundation | Deliverable: skill_matching_research.md ¦ Acceptance: Notes name a candidate taxonomy source and embedding model
| Testing, Documentation & QA | Compile Week 1 research findings from all four members into a single consolidated Research & Planning report. | Expected Output: Consolidated Week 1 research report | Aditee Talekar | FALSE | Documentation, Research & Planning Foundation | Deliverable: week1_research_report.md ¦ Acceptance: Report references every document produced this week
2026-07-10 | Project Lead & Backend Architecture | Research and document the Node.js + Express.js project structure (routes/services/repositories layering) and error-handling conventions to standardize before coding begins. | Expected Output: Backend project structure & conventions document | Gaurav Bhosale | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: backend_structure.md ¦ Acceptance: Layering, naming, and folder conventions agreed and written down
| Frontend Lead & UI/UX | Research React.js project architecture (folder structure, state management choice, routing strategy) and document conventions. | Expected Output: Frontend architecture document | Amey Nadkar | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: frontend_structure.md ¦ Acceptance: State management and routing approach chosen and justified
| AI & Resume Intelligence | Research Google Gemini API integration patterns, prompt-engineering best practices, and structured-output (JSON mode) reliability. | Expected Output: Gemini integration research notes | Dheeraj Sarfare | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: gemini_integration_research.md ¦ Acceptance: Notes cover prompt design, JSON-mode reliability, and error handling
| Testing, Documentation & QA | Research CI/CD pipeline tooling (GitHub Actions, Docker builds) and document the testing-gate strategy for pull requests. | Expected Output: CI/CD & testing-gate research document | Aditee Talekar | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: cicd_testing_gate.md ¦ Acceptance: Pipeline stages and required checks documented

## Week 2
IIB — Team ADAG — Week 2 Timeline (Sun Jul 12 – Fri Jul 17)
Phase(s) this week: Documentation, Research & Planning Foundation (Part 2) → Authentication Core ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-07-12 | Project Lead & Backend Architecture | Research Redis caching strategies (cache-aside, TTL policy, invalidation patterns) suited to the platform's read-heavy endpoints. | Expected Output: Redis caching strategy document | Gaurav Bhosale | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: caching_strategy.md ¦ Acceptance: Cache-key naming convention and invalidation rules documented
| Frontend Lead & UI/UX | Document the shared UI component library plan (design tokens, theming, Tailwind config) building on Week 1's component inventory. | Expected Output: UI kit plan document | Amey Nadkar | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: ui_kit_plan.md ¦ Acceptance: Design tokens and theming approach documented
| AI & Resume Intelligence | Document the AI cost-control and rate-limit strategy (caching, batching, quota handling) for Gemini calls across the platform. | Expected Output: AI cost & rate-limit strategy document | Dheeraj Sarfare | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: ai_cost_strategy.md ¦ Acceptance: Caching and quota-handling approach documented
| Testing, Documentation & QA | Write the new-developer environment setup guide (local Docker setup, env variables, seed data). | Expected Output: Developer setup guide | Aditee Talekar | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: dev_setup_guide.md ¦ Acceptance: A new team member can follow it to get the project running locally
2026-07-13 | Project Lead & Backend Architecture | Research background job design with BullMQ (queues, retries, concurrency limits) for email, exports, and AI calls. | Expected Output: Background job architecture notes | Gaurav Bhosale | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: background_jobs.md ¦ Acceptance: Queue list and retry/backoff policy documented
| Frontend Lead & UI/UX | Research code-splitting and performance-budget strategy for a large multi-portal React app. | Expected Output: Performance strategy research notes | Amey Nadkar | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: performance_strategy.md ¦ Acceptance: Notes cover route-level code-splitting and a target bundle-size budget
| AI & Resume Intelligence | Research Node.js-based scraping tooling (Puppeteer, Cheerio, Playwright) for future listing-ingestion use by Super Admin. | Expected Output: Scraper tooling comparison notes | Dheeraj Sarfare | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: scraper_tooling_research.md ¦ Acceptance: At least 2 tools compared with a recommendation
| Testing, Documentation & QA | Research a security and compliance checklist (OWASP basics, data-privacy considerations) relevant to the new stack. | Expected Output: Security checklist research document | Aditee Talekar | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: security_checklist.md ¦ Acceptance: Checklist covers auth, input validation, and data handling at minimum
2026-07-14 | Project Lead & Backend Architecture | Document the CI/CD and deployment plan across Docker and Vercel/Render options, including environment variable and secrets-management strategy. | Expected Output: CI/CD & deployment plan document | Gaurav Bhosale | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: deployment_plan.md ¦ Acceptance: Both Docker and Vercel/Render paths documented with a recommended default
| Frontend Lead & UI/UX | Research frontend testing strategy (component tests, E2E) and shortlist tooling. | Expected Output: Frontend testing strategy document | Amey Nadkar | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: frontend_testing_strategy.md ¦ Acceptance: Tooling recommendation documented per test layer
| AI & Resume Intelligence | Document the AI response caching strategy (content-hash based) to control latency and Gemini API cost. | Expected Output: AI caching strategy document | Dheeraj Sarfare | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: ai_caching_strategy.md ¦ Acceptance: Reviewed and approved by project lead
| Testing, Documentation & QA | Refine the sprint ceremony schedule and Definition of Done to reflect the finalized tech stack. | Expected Output: Updated Definition of Done document | Aditee Talekar | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: definition_of_done.md ¦ Acceptance: Reviewed and agreed by the whole team
2026-07-15 | Project Lead & Backend Architecture | Finalize the MySQL schema migration and seeding strategy using Prisma, including a rollback approach. | Expected Output: Migration & seeding strategy document | Gaurav Bhosale | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: migration_strategy.md ¦ Acceptance: Reviewed and approved by the team
| Frontend Lead & UI/UX | Document the Vercel deployment/build pipeline plan for the frontend, including preview-deployment workflow. | Expected Output: Frontend deployment plan | Amey Nadkar | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: frontend_deployment_plan.md ¦ Acceptance: Reviewed and approved by the team
| AI & Resume Intelligence | Research safety and moderation approach for AI-generated outputs (resume feedback, review summaries). | Expected Output: AI safety & moderation research notes | Dheeraj Sarfare | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: ai_safety_research.md ¦ Acceptance: Notes name concrete safeguards for at least 2 AI-powered features
| Testing, Documentation & QA | Compile Week 2 research findings from all four members into a consolidated Research & Planning report. | Expected Output: Consolidated Week 2 research report | Aditee Talekar | FALSE | Documentation, Research & Planning Foundation (Part 2) | Deliverable: week2_research_report.md ¦ Acceptance: Report references every document produced this week
2026-07-16 | Project Lead & Backend Architecture | Implement user registration endpoint with email verification token generation | Expected Output: POST /auth/register working end-to-end | Gaurav Bhosale | FALSE | Authentication Core | Deliverable: Registration endpoint committed ¦ Acceptance: New user row created, verification email queued
| Frontend Lead & UI/UX | Build Sign Up page with form validation (email, password strength) | Expected Output: Sign Up page functional | Amey Nadkar | FALSE | Authentication Core | Deliverable: SignUp.jsx committed ¦ Acceptance: Invalid inputs show inline errors
| AI & Resume Intelligence | Design user-skill and user-preference data schema for future recommendations | Expected Output: User preference schema documented | Dheeraj Sarfare | FALSE | Authentication Core | Deliverable: user_preference_schema.json committed ¦ Acceptance: Schema approved for backend integration
| Testing, Documentation & QA | Write unit tests for registration, login, and password hashing logic | Expected Output: Auth unit tests passing | Aditee Talekar | FALSE | Authentication Core | Deliverable: test_auth.py committed ¦ Acceptance: 10+ auth test cases passing in CI
2026-07-17 | Project Lead & Backend Architecture | Implement login endpoint with JWT access + refresh token issuance | Expected Output: POST /auth/login returns valid tokens | Gaurav Bhosale | FALSE | Authentication Core | Deliverable: Login endpoint committed ¦ Acceptance: Tokens verified via jwt.io decode
| Frontend Lead & UI/UX | Build Login page with remember-me and forgot-password entry point | Expected Output: Login page functional | Amey Nadkar | FALSE | Authentication Core | Deliverable: Login.jsx committed ¦ Acceptance: Successful login redirects to dashboard
| AI & Resume Intelligence | Research OAuth/social-login feasibility (Google) for external students | Expected Output: Feasibility report written | Dheeraj Sarfare | FALSE | Authentication Core | Deliverable: oauth_feasibility.md committed ¦ Acceptance: Decision logged - build now or defer
| Testing, Documentation & QA | Write RBAC-focused test matrix execution for auth endpoints | Expected Output: RBAC auth tests documented | Aditee Talekar | FALSE | Authentication Core | Deliverable: rbac_auth_tests.md committed ¦ Acceptance: Each role's access verified against matrix

## Week 3
IIB — Team ADAG — Week 3 Timeline (Sun Jul 19 – Fri Jul 24)
Phase(s) this week: Authentication Core → Role-Based Access Control (RBAC) ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-07-19 | Project Lead & Backend Architecture | Implement password hashing with bcrypt/argon2 and password policy validation | Expected Output: Passwords hashed, weak passwords rejected | Gaurav Bhosale | FALSE | Authentication Core | Deliverable: Password utils committed ¦ Acceptance: Plain-text password never persisted
| Frontend Lead & UI/UX | Wire login/signup forms to backend auth endpoints via API client | Expected Output: Forms submit and handle responses | Amey Nadkar | FALSE | Authentication Core | Deliverable: Auth API integration committed ¦ Acceptance: Error and success states both handled
| AI & Resume Intelligence | Build skill-taxonomy tagging function to auto-tag user-entered skills | Expected Output: Skill tagging function working | Dheeraj Sarfare | FALSE | Authentication Core | Deliverable: tag_skills.py committed ¦ Acceptance: Correctly tags 20 test skill inputs
| Testing, Documentation & QA | Security review - check for JWT secret handling, token expiry settings | Expected Output: Security checklist completed | Aditee Talekar | FALSE | Authentication Core | Deliverable: security_review_auth.md committed ¦ Acceptance: No secrets in repo, expiry configured correctly
2026-07-20 | Project Lead & Backend Architecture | Build refresh-token rotation endpoint with revocation on reuse detection | Expected Output: POST /auth/refresh rotates tokens safely | Gaurav Bhosale | FALSE | Authentication Core | Deliverable: Refresh flow committed ¦ Acceptance: Reused old token is rejected
| Frontend Lead & UI/UX | Build protected route wrapper redirecting unauthenticated users to login | Expected Output: Protected routes enforce auth | Amey Nadkar | FALSE | Authentication Core | Deliverable: ProtectedRoute component committed ¦ Acceptance: Unauthenticated access redirects correctly
| AI & Resume Intelligence | Prototype resume-to-skill extraction using the parsing pipeline from Week 2 | Expected Output: Skills extracted from real resumes | Dheeraj Sarfare | FALSE | Authentication Core | Deliverable: resume_to_skills.py committed ¦ Acceptance: Extracts skills from 5 sample resumes
| Testing, Documentation & QA | Write frontend tests for Login/SignUp form validation | Expected Output: Frontend auth tests passing | Aditee Talekar | FALSE | Authentication Core | Deliverable: Login.test.jsx, SignUp.test.jsx committed ¦ Acceptance: Validation edge cases covered
2026-07-21 | Project Lead & Backend Architecture | Implement email verification confirm endpoint and account activation logic Also run the weekly team sync: demo full registration-to-login flow to team | Expected Output: Account activates only after verification Auth flow demo delivered | Gaurav Bhosale | FALSE | Authentication Core | Deliverable: Verify-email endpoint committed; Demo notes in Wiki ¦ Acceptance: Unverified accounts blocked from login Team completes signup+login live
| Frontend Lead & UI/UX | Build token refresh interceptor - silently refresh expired access tokens Also run the weekly team sync: demo full auth UI flow including token refresh | Expected Output: Silent refresh working Auth UI demo delivered | Amey Nadkar | FALSE | Authentication Core | Deliverable: Axios interceptor updated; Demo notes in Wiki ¦ Acceptance: Expired token triggers refresh, not logout Team confirms smooth login experience
| AI & Resume Intelligence | Document AI service authentication approach (service-to-service token) Also run the weekly team sync: present skill tagging progress to team | Expected Output: AI auth approach documented Skill tagging demo delivered | Dheeraj Sarfare | FALSE | Authentication Core | Deliverable: ai_auth_design.md committed; Demo notes in Wiki ¦ Acceptance: Approved by backend lead Team reviews tagging accuracy
| Testing, Documentation & QA | Document password reset and account recovery user flow Also run the weekly team sync: present auth test coverage and security review | Expected Output: Recovery flow documented Test coverage demo delivered | Aditee Talekar | FALSE | Authentication Core | Deliverable: password_recovery_flow.md committed; Demo notes in Wiki ¦ Acceptance: Flow diagram reviewed by team Team signs off on auth security
2026-07-22 | Project Lead & Backend Architecture | Implement role and permission tables with many-to-many mapping | Expected Output: Role/permission schema migrated | Gaurav Bhosale | FALSE | Role-Based Access Control (RBAC) | Deliverable: roles, permissions tables committed ¦ Acceptance: Query returns correct permissions per role
| Frontend Lead & UI/UX | Build role-aware navigation - sidebar/menu changes based on logged-in role | Expected Output: Role-based nav rendering correctly | Amey Nadkar | FALSE | Role-Based Access Control (RBAC) | Deliverable: RoleNav component committed ¦ Acceptance: Each of 7 roles sees correct menu
| AI & Resume Intelligence | Design department-wise data model to support college analytics later | Expected Output: Department schema documented | Dheeraj Sarfare | FALSE | Role-Based Access Control (RBAC) | Deliverable: department_schema.json committed ¦ Acceptance: Supports multi-department colleges
| Testing, Documentation & QA | Write RBAC integration tests covering all 7 roles against all endpoints | Expected Output: Full RBAC test suite passing | Aditee Talekar | FALSE | Role-Based Access Control (RBAC) | Deliverable: test_rbac.py committed ¦ Acceptance: All role/endpoint combinations verified
2026-07-23 | Project Lead & Backend Architecture | Build FastAPI dependency for role-based endpoint protection | Expected Output: require_role() dependency working | Gaurav Bhosale | FALSE | Role-Based Access Control (RBAC) | Deliverable: rbac_dependency.py committed ¦ Acceptance: Unauthorized role receives 403
| Frontend Lead & UI/UX | Build College Admin dashboard shell with placement coordinator management UI | Expected Output: College Admin shell functional | Amey Nadkar | FALSE | Role-Based Access Control (RBAC) | Deliverable: CollegeAdminDashboard.jsx committed ¦ Acceptance: Admin can view/invite coordinators
| AI & Resume Intelligence | Research approach for company review aggregation (Glassdoor/AmbitionBox/Indeed) | Expected Output: Aggregation approach documented | Dheeraj Sarfare | FALSE | Role-Based Access Control (RBAC) | Deliverable: review_aggregation_design.md committed ¦ Acceptance: Legal/ToS considerations noted
| Testing, Documentation & QA | Write test cases for invite/accept flows (college and company) | Expected Output: Invite flow tests passing | Aditee Talekar | FALSE | Role-Based Access Control (RBAC) | Deliverable: test_invites.py committed ¦ Acceptance: Edge cases - expired invite, reused token
2026-07-24 | Project Lead & Backend Architecture | Implement Super Admin bootstrap script for initial platform setup | Expected Output: Super Admin account creatable via CLI | Gaurav Bhosale | FALSE | Role-Based Access Control (RBAC) | Deliverable: bootstrap_admin.py committed ¦ Acceptance: First admin account created successfully
| Frontend Lead & UI/UX | Build Company Admin dashboard shell with recruiter management UI | Expected Output: Company Admin shell functional | Amey Nadkar | FALSE | Role-Based Access Control (RBAC) | Deliverable: CompanyAdminDashboard.jsx committed ¦ Acceptance: Admin can view/invite recruiters
| AI & Resume Intelligence | Build data normalization utility for inconsistent job title/skill naming | Expected Output: Normalization function working | Dheeraj Sarfare | FALSE | Role-Based Access Control (RBAC) | Deliverable: normalize_data.py committed ¦ Acceptance: Normalizes 20 test variants correctly
| Testing, Documentation & QA | Perform manual QA pass on all 4 role-specific dashboard shells | Expected Output: QA report on dashboards | Aditee Talekar | FALSE | Role-Based Access Control (RBAC) | Deliverable: qa_report_dashboards.md committed ¦ Acceptance: All bugs logged as GitHub Issues

## Week 4
IIB — Team ADAG — Week 4 Timeline (Sun Jul 26 – Fri Jul 31)
Phase(s) this week: Role-Based Access Control (RBAC) → Student Portal - Profile & Discovery ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-07-26 | Project Lead & Backend Architecture | Build College Admin invite flow for Placement Coordinator accounts | Expected Output: Invite + accept flow working | Gaurav Bhosale | FALSE | Role-Based Access Control (RBAC) | Deliverable: College invite endpoints committed ¦ Acceptance: Invited coordinator can activate account
| Frontend Lead & UI/UX | Build Super Admin shell - platform-wide college/company management view | Expected Output: Super Admin shell functional | Amey Nadkar | FALSE | Role-Based Access Control (RBAC) | Deliverable: SuperAdminDashboard.jsx committed ¦ Acceptance: Admin can list all colleges/companies
| AI & Resume Intelligence | Build duplicate-detection logic for job/internship listings | Expected Output: Duplicate detection POC working | Dheeraj Sarfare | FALSE | Role-Based Access Control (RBAC) | Deliverable: dedupe_poc.py committed ¦ Acceptance: Correctly flags 5 duplicate test listings
| Testing, Documentation & QA | Update RBAC matrix doc with any changes discovered during implementation | Expected Output: RBAC matrix v2 published | Aditee Talekar | FALSE | Role-Based Access Control (RBAC) | Deliverable: rbac_matrix.md updated ¦ Acceptance: Matches actual implemented behavior
2026-07-27 | Project Lead & Backend Architecture | Build Company Admin invite flow for Recruiter accounts Also run the weekly team sync: demo full RBAC enforcement across all 7 roles | Expected Output: Recruiter invite flow working RBAC demo delivered | Gaurav Bhosale | FALSE | Role-Based Access Control (RBAC) | Deliverable: Company invite endpoints committed; Demo notes in Wiki ¦ Acceptance: Invited recruiter can activate account Each role tested live against matrix
| Frontend Lead & UI/UX | Build access-denied / 403 UI page with helpful messaging Also run the weekly team sync: demo all role-specific dashboard shells | Expected Output: 403 page implemented Dashboard shells demo delivered | Amey Nadkar | FALSE | Role-Based Access Control (RBAC) | Deliverable: AccessDenied.jsx committed; Demo notes in Wiki ¦ Acceptance: Unauthorized route shows friendly message Team confirms UI matches role matrix
| AI & Resume Intelligence | Document AI service role-awareness (what each role can request from AI) Also run the weekly team sync: present data normalization and dedup progress | Expected Output: AI-role permission doc written Normalization demo delivered | Dheeraj Sarfare | FALSE | Role-Based Access Control (RBAC) | Deliverable: ai_role_permissions.md committed; Demo notes in Wiki ¦ Acceptance: Reviewed and approved by team Team reviews accuracy on sample data
| Testing, Documentation & QA | Write documentation - How Roles Work in IIB India (for stakeholders) Also run the weekly team sync: present full RBAC test results and sign-off | Expected Output: Roles documentation published RBAC sign-off demo delivered | Aditee Talekar | FALSE | Role-Based Access Control (RBAC) | Deliverable: ROLES.md committed; Demo notes in Wiki ¦ Acceptance: Reviewed by project lead Team formally signs off on RBAC
2026-07-28 | Project Lead & Backend Architecture | Build student profile API - skills, education, projects, certificates, interests | Expected Output: CRUD endpoints for student profile | Gaurav Bhosale | FALSE | Student Portal - Profile & Discovery | Deliverable: student_profile router committed ¦ Acceptance: Profile persists and returns correctly
| Frontend Lead & UI/UX | Build student profile page - editable sections for skills/education/projects | Expected Output: Profile page functional | Amey Nadkar | FALSE | Student Portal - Profile & Discovery | Deliverable: StudentProfile.jsx committed ¦ Acceptance: Edits save and persist on reload
| AI & Resume Intelligence | Build skill-based recommendation scoring using Week 1-4 embedding POC | Expected Output: Recommendation scores generated per student | Dheeraj Sarfare | FALSE | Student Portal - Profile & Discovery | Deliverable: skill_recommender.py committed ¦ Acceptance: Top-5 recommendations look relevant on test data
| Testing, Documentation & QA | Write API tests for student profile CRUD and listings endpoints | Expected Output: Profile/listings tests passing | Aditee Talekar | FALSE | Student Portal - Profile & Discovery | Deliverable: test_student_api.py committed ¦ Acceptance: All CRUD paths covered including edge cases
2026-07-29 | Project Lead & Backend Architecture | Build job/internship listing model and CRUD API (draft state) | Expected Output: Listings CRUD working | Gaurav Bhosale | FALSE | Student Portal - Profile & Discovery | Deliverable: listings router committed ¦ Acceptance: Create/read/update/archive all functional
| Frontend Lead & UI/UX | Build personalized student dashboard - recommended, recently added, closing soon | Expected Output: Dashboard sections rendering | Amey Nadkar | FALSE | Student Portal - Profile & Discovery | Deliverable: StudentDashboard.jsx committed ¦ Acceptance: All 3 sections show live data
| AI & Resume Intelligence | Integrate recommendation scoring into a callable AI service endpoint | Expected Output: POST /ai/recommend/jobs working | Dheeraj Sarfare | FALSE | Student Portal - Profile & Discovery | Deliverable: recommend endpoint committed ¦ Acceptance: Returns ranked job IDs with scores
| Testing, Documentation & QA | Write frontend tests for StudentProfile and SearchPage components | Expected Output: Frontend tests passing | Aditee Talekar | FALSE | Student Portal - Profile & Discovery | Deliverable: StudentProfile.test.jsx committed ¦ Acceptance: Form validation and search rendering covered
2026-07-30 | Project Lead & Backend Architecture | Build search API with keyword search across jobs/internships/companies | Expected Output: Search endpoint returning ranked results | Gaurav Bhosale | FALSE | Student Portal - Profile & Discovery | Deliverable: search router committed ¦ Acceptance: Keyword search returns relevant results
| Frontend Lead & UI/UX | Build job/internship search page with keyword search bar | Expected Output: Search page functional | Amey Nadkar | FALSE | Student Portal - Profile & Discovery | Deliverable: SearchPage.jsx committed ¦ Acceptance: Typing query returns matching results
| AI & Resume Intelligence | Build closing-soon and trending logic (deadline proximity + view count) | Expected Output: Trending/closing-soon logic working | Dheeraj Sarfare | FALSE | Student Portal - Profile & Discovery | Deliverable: trending_logic.py committed ¦ Acceptance: Correctly ranks test listings by urgency
| Testing, Documentation & QA | Manual QA pass on filter combinations across all filter types | Expected Output: Filter QA report written | Aditee Talekar | FALSE | Student Portal - Profile & Discovery | Deliverable: qa_report_filters.md committed ¦ Acceptance: All bugs logged as GitHub Issues
2026-07-31 | Project Lead & Backend Architecture | Build filter API - domain, location, salary, stipend, experience, work mode | Expected Output: Filter query params supported | Gaurav Bhosale | FALSE | Student Portal - Profile & Discovery | Deliverable: Filter logic committed ¦ Acceptance: Combined filters return correct subset
| Frontend Lead & UI/UX | Build filter sidebar - domain, location, salary, stipend, experience, mode | Expected Output: Filter sidebar functional | Amey Nadkar | FALSE | Student Portal - Profile & Discovery | Deliverable: FilterSidebar.jsx committed ¦ Acceptance: Selecting filters updates result list
| AI & Resume Intelligence | Build resume-based recommendation stub (feeds resume skills into recommender) | Expected Output: Resume-based recommendations stubbed | Dheeraj Sarfare | FALSE | Student Portal - Profile & Discovery | Deliverable: resume_recommend_stub.py committed ¦ Acceptance: Accepts resume ID, returns job matches
| Testing, Documentation & QA | Write test cases validating recommendation endpoint response structure | Expected Output: Recommendation API tests passing | Aditee Talekar | FALSE | Student Portal - Profile & Discovery | Deliverable: test_recommend_api.py committed ¦ Acceptance: Response schema validated automatically

## Week 5
IIB — Team ADAG — Week 5 Timeline (Sun Aug 2 – Fri Aug 7)
Phase(s) this week: Student Portal - Profile & Discovery → Student Portal - Applications & Career Tools ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-08-02 | Project Lead & Backend Architecture | Add pagination and sorting to listings endpoints Also run the weekly team sync: demo listings, search and filter APIs | Expected Output: Paginated responses working API demo delivered | Gaurav Bhosale | FALSE | Student Portal - Profile & Discovery | Deliverable: Pagination utility committed; Demo notes in Wiki ¦ Acceptance: Page size and sort order respected Team validates search relevance
| Frontend Lead & UI/UX | Build job/internship listing card component with key details Also run the weekly team sync: demo student dashboard and search experience | Expected Output: Listing card reusable component Student UI demo delivered | Amey Nadkar | FALSE | Student Portal - Profile & Discovery | Deliverable: ListingCard.jsx committed; Demo notes in Wiki ¦ Acceptance: Card shows title, company, salary, deadline Team confirms UX is intuitive
| AI & Resume Intelligence | Write evaluation script comparing recommendation quality across test profiles Also run the weekly team sync: present recommendation scoring results to team | Expected Output: Evaluation report generated Recommendation demo delivered | Dheeraj Sarfare | FALSE | Student Portal - Profile & Discovery | Deliverable: eval_recommendations.py committed; Demo notes in Wiki ¦ Acceptance: Report shared with team for review Team reviews relevance and approves
| Testing, Documentation & QA | Document Student Portal feature set for USAGE.md Also run the weekly team sync: present Week 5 test coverage summary | Expected Output: Student portal docs published Test summary demo delivered | Aditee Talekar | FALSE | Student Portal - Profile & Discovery | Deliverable: USAGE.md updated; Demo notes in Wiki ¦ Acceptance: Covers profile, search, filters, recommendations Coverage % shared with team
2026-08-03 | Project Lead & Backend Architecture | Build apply-to-job/internship API with duplicate application prevention | Expected Output: POST /applications working | Gaurav Bhosale | FALSE | Student Portal - Applications & Career Tools | Deliverable: applications router committed ¦ Acceptance: Duplicate apply attempt is rejected
| Frontend Lead & UI/UX | Build Apply button + application confirmation modal on listing pages | Expected Output: Apply flow functional | Amey Nadkar | FALSE | Student Portal - Applications & Career Tools | Deliverable: ApplyModal.jsx committed ¦ Acceptance: Successful apply shows confirmation
| AI & Resume Intelligence | Build company review aggregation pipeline from configured public sources | Expected Output: Aggregation pipeline working on sample data | Dheeraj Sarfare | FALSE | Student Portal - Applications & Career Tools | Deliverable: review_aggregator.py committed ¦ Acceptance: Aggregates reviews from 3 sources correctly
| Testing, Documentation & QA | Write tests for apply/bookmark/status-tracking endpoints | Expected Output: Application API tests passing | Aditee Talekar | FALSE | Student Portal - Applications & Career Tools | Deliverable: test_applications_api.py committed ¦ Acceptance: Duplicate-apply and status-flow cases covered
2026-08-04 | Project Lead & Backend Architecture | Build bookmark/save-for-later API for jobs and internships | Expected Output: Bookmark CRUD working | Gaurav Bhosale | FALSE | Student Portal - Applications & Career Tools | Deliverable: bookmarks router committed ¦ Acceptance: Bookmarks persist per user
| Frontend Lead & UI/UX | Build Save/Bookmark toggle on listing cards and detail pages | Expected Output: Bookmark toggle functional | Amey Nadkar | FALSE | Student Portal - Applications & Career Tools | Deliverable: BookmarkToggle.jsx committed ¦ Acceptance: State persists across sessions
| AI & Resume Intelligence | Build salary insights computation - average/range per role and company | Expected Output: Salary insights computed correctly | Dheeraj Sarfare | FALSE | Student Portal - Applications & Career Tools | Deliverable: salary_insights.py committed ¦ Acceptance: Matches manually verified sample data
| Testing, Documentation & QA | Write frontend tests for ApplyModal and ApplicationTracker | Expected Output: Frontend tests passing | Aditee Talekar | FALSE | Student Portal - Applications & Career Tools | Deliverable: ApplyModal.test.jsx committed ¦ Acceptance: Apply and tracking flows verified
2026-08-05 | Project Lead & Backend Architecture | Build application status tracking API - applied, shortlisted, selected, rejected | Expected Output: Status tracking working | Gaurav Bhosale | FALSE | Student Portal - Applications & Career Tools | Deliverable: application_status endpoint committed ¦ Acceptance: Status updates reflect in history
| Frontend Lead & UI/UX | Build Application Tracker page - grouped by status with timeline view | Expected Output: Tracker page functional | Amey Nadkar | FALSE | Student Portal - Applications & Career Tools | Deliverable: ApplicationTracker.jsx committed ¦ Acceptance: Applications grouped and timelined correctly
| AI & Resume Intelligence | Improve recommendation ranking using application/bookmark signals as feedback | Expected Output: Feedback-aware ranking implemented | Dheeraj Sarfare | FALSE | Student Portal - Applications & Career Tools | Deliverable: feedback_ranking.py committed ¦ Acceptance: Ranking shifts appropriately with new signals
| Testing, Documentation & QA | Manual QA - full student journey from signup to application tracking | Expected Output: End-to-end QA report written | Aditee Talekar | FALSE | Student Portal - Applications & Career Tools | Deliverable: qa_report_student_journey.md committed ¦ Acceptance: All bugs logged with severity
2026-08-06 | Project Lead & Backend Architecture | Build application history endpoint with timeline of status changes | Expected Output: History endpoint returning timeline | Gaurav Bhosale | FALSE | Student Portal - Applications & Career Tools | Deliverable: application_history endpoint committed ¦ Acceptance: Timeline ordered correctly by date
| Frontend Lead & UI/UX | Build Company Profile page - reviews, salary insights, interview experiences | Expected Output: Company profile page functional | Amey Nadkar | FALSE | Student Portal - Applications & Career Tools | Deliverable: CompanyProfile.jsx committed ¦ Acceptance: All sections render live data
| AI & Resume Intelligence | Build skill-gap analysis stub - compares student skills to target roles | Expected Output: Skill-gap stub working | Dheeraj Sarfare | FALSE | Student Portal - Applications & Career Tools | Deliverable: skill_gap_stub.py committed ¦ Acceptance: Returns missing-skill list for test profile
| Testing, Documentation & QA | Write tests validating company review/salary aggregation accuracy | Expected Output: Aggregation tests passing | Aditee Talekar | FALSE | Student Portal - Applications & Career Tools | Deliverable: test_review_aggregation.py committed ¦ Acceptance: Matches expected sample outputs
2026-08-07 | Project Lead & Backend Architecture | Build company profile API - reviews, salary insights aggregation fields Also run the weekly team sync: demo apply/bookmark/tracking flow end-to-end | Expected Output: Company profile API working Applications demo delivered | Gaurav Bhosale | FALSE | Student Portal - Applications & Career Tools | Deliverable: company_profile router committed; Demo notes in Wiki ¦ Acceptance: Returns aggregated review/salary data Team completes an application live
| Frontend Lead & UI/UX | Build Career section - company reviews and salary insights UI Also run the weekly team sync: demo full student application journey to team | Expected Output: Career tools UI functional Full journey demo delivered | Amey Nadkar | FALSE | Student Portal - Applications & Career Tools | Deliverable: CareerInsights.jsx committed; Demo notes in Wiki ¦ Acceptance: Reviews and insights display correctly Team walks through apply-to-track flow
| AI & Resume Intelligence | Write data quality checks for aggregated review/salary data Also run the weekly team sync: present company insights and skill-gap progress | Expected Output: Data quality checks passing AI insights demo delivered | Dheeraj Sarfare | FALSE | Student Portal - Applications & Career Tools | Deliverable: data_quality_checks.py committed; Demo notes in Wiki ¦ Acceptance: Flags malformed/outlier records Team reviews data accuracy
| Testing, Documentation & QA | Update USAGE.md with application tracking and career tools sections Also run the weekly team sync: Week 6 retrospective and Student Portal sign-off | Expected Output: Docs updated Student Portal sign-off | Aditee Talekar | FALSE | Student Portal - Applications & Career Tools | Deliverable: USAGE.md updated; retro-week6.md committed ¦ Acceptance: Reviewed by project lead Team formally signs off on Student Portal MVP

## Week 6
IIB — Team ADAG — Week 6 Timeline (Sun Aug 9 – Fri Aug 14)
Phase(s) this week: Company Portal - Profile & Job Management → Company Portal - Recruiter Workflow ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-08-09 | Project Lead & Backend Architecture | Build company profile management API - branding, verification documents | Expected Output: Company profile CRUD working | Gaurav Bhosale | FALSE | Company Portal - Profile & Job Management | Deliverable: company_admin router committed ¦ Acceptance: Profile updates persist correctly
| Frontend Lead & UI/UX | Build Company Profile management page - branding, documents, branches | Expected Output: Company profile page functional | Amey Nadkar | FALSE | Company Portal - Profile & Job Management | Deliverable: CompanyProfilePage.jsx committed ¦ Acceptance: Admin can edit and save profile
| AI & Resume Intelligence | Design company analytics data pipeline - views, applicants, shortlisted, selected | Expected Output: Analytics pipeline design documented | Dheeraj Sarfare | FALSE | Company Portal - Profile & Job Management | Deliverable: company_analytics_design.md committed ¦ Acceptance: Approved by project lead
| Testing, Documentation & QA | Write tests for company profile, branch, and recruiter management APIs | Expected Output: Company API tests passing | Aditee Talekar | FALSE | Company Portal - Profile & Job Management | Deliverable: test_company_api.py committed ¦ Acceptance: CRUD and permission edge cases covered
2026-08-10 | Project Lead & Backend Architecture | Build branch management API for multi-branch companies | Expected Output: Branch CRUD working | Gaurav Bhosale | FALSE | Company Portal - Profile & Job Management | Deliverable: branches router committed ¦ Acceptance: Branches linked correctly to parent company
| Frontend Lead & UI/UX | Build Branch Management UI - add/edit/remove branches | Expected Output: Branch management functional | Amey Nadkar | FALSE | Company Portal - Profile & Job Management | Deliverable: BranchManagement.jsx committed ¦ Acceptance: Branches list updates in real time
| AI & Resume Intelligence | Build view/impression tracking for job/internship listings | Expected Output: View tracking working | Dheeraj Sarfare | FALSE | Company Portal - Profile & Job Management | Deliverable: view_tracking.py committed ¦ Acceptance: View counts increment correctly on access
| Testing, Documentation & QA | Write tests for job creation, validation, and lifecycle endpoints | Expected Output: Job API tests passing | Aditee Talekar | FALSE | Company Portal - Profile & Job Management | Deliverable: test_job_api.py committed ¦ Acceptance: Invalid listing rejection verified
2026-08-11 | Project Lead & Backend Architecture | Build recruiter management API - add/remove/permissions | Expected Output: Recruiter management working | Gaurav Bhosale | FALSE | Company Portal - Profile & Job Management | Deliverable: recruiter_management endpoints committed ¦ Acceptance: Admin can add/remove recruiters
| Frontend Lead & UI/UX | Build Recruiter Management UI - invite, remove, assign permissions | Expected Output: Recruiter management functional | Amey Nadkar | FALSE | Company Portal - Profile & Job Management | Deliverable: RecruiterManagement.jsx committed ¦ Acceptance: Admin can manage recruiter list
| AI & Resume Intelligence | Build applicant funnel computation - applied to shortlisted to selected | Expected Output: Funnel computation working | Dheeraj Sarfare | FALSE | Company Portal - Profile & Job Management | Deliverable: applicant_funnel.py committed ¦ Acceptance: Funnel numbers match test data
| Testing, Documentation & QA | Write frontend tests for JobCreationForm and RecruiterManagement | Expected Output: Frontend tests passing | Aditee Talekar | FALSE | Company Portal - Profile & Job Management | Deliverable: JobCreationForm.test.jsx committed ¦ Acceptance: Validation and submission flows covered
2026-08-12 | Project Lead & Backend Architecture | Build job/internship creation API with validation (salary, deadline, requirements) | Expected Output: Job creation API working | Gaurav Bhosale | FALSE | Company Portal - Profile & Job Management | Deliverable: job_creation endpoint committed ¦ Acceptance: Invalid listings rejected with clear errors
| Frontend Lead & UI/UX | Build Job/Internship creation form with validation and preview | Expected Output: Job creation form functional | Amey Nadkar | FALSE | Company Portal - Profile & Job Management | Deliverable: JobCreationForm.jsx committed ¦ Acceptance: Form validates before submission, shows preview
| AI & Resume Intelligence | Build hiring trend computation across time periods for a company | Expected Output: Hiring trend data generated | Dheeraj Sarfare | FALSE | Company Portal - Profile & Job Management | Deliverable: hiring_trends.py committed ¦ Acceptance: Trend chart data matches manual calculation
| Testing, Documentation & QA | Manual QA - company admin journey from signup to job posted | Expected Output: Company journey QA report written | Aditee Talekar | FALSE | Company Portal - Profile & Job Management | Deliverable: qa_report_company_journey.md committed ¦ Acceptance: All bugs logged with severity
2026-08-13 | Project Lead & Backend Architecture | Build listing edit/archive/delete API with audit trail Also run the weekly team sync: demo company profile and job creation flow | Expected Output: Listing lifecycle API working Company API demo delivered | Gaurav Bhosale | FALSE | Company Portal - Profile & Job Management | Deliverable: listing_lifecycle endpoints committed; Demo notes in Wiki ¦ Acceptance: Audit log records every change Team creates a job listing live
| Frontend Lead & UI/UX | Build listings management table - edit, archive, delete actions Also run the weekly team sync: demo Company Portal management screens | Expected Output: Listings table functional Company Portal demo delivered | Amey Nadkar | FALSE | Company Portal - Profile & Job Management | Deliverable: ListingsTable.jsx committed; Demo notes in Wiki ¦ Acceptance: Actions update listing state correctly Team walks through full job posting flow
| AI & Resume Intelligence | Integrate skill-taxonomy tagging into job creation for better matching Also run the weekly team sync: present company analytics pipeline progress | Expected Output: Job listings auto-tagged with skills Analytics demo delivered | Dheeraj Sarfare | FALSE | Company Portal - Profile & Job Management | Deliverable: job_auto_tagging.py committed; Demo notes in Wiki ¦ Acceptance: Tags match manually reviewed sample jobs Team reviews funnel accuracy
| Testing, Documentation & QA | Document Company Portal feature set in USAGE.md Also run the weekly team sync: Week 7 retrospective on Company Portal progress | Expected Output: Docs updated Week 7 retro completed | Aditee Talekar | FALSE | Company Portal - Profile & Job Management | Deliverable: USAGE.md updated; retro-week7.md committed ¦ Acceptance: Reviewed by project lead Blockers logged as GitHub Issues
2026-08-14 | Project Lead & Backend Architecture | Build applicant listing API for recruiters - filter by job/status | Expected Output: Applicant listing API working | Gaurav Bhosale | FALSE | Company Portal - Recruiter Workflow | Deliverable: recruiter_applicants router committed ¦ Acceptance: Filters return correct applicant subsets
| Frontend Lead & UI/UX | Build Applicants view for recruiters - list with filters and search | Expected Output: Applicants view functional | Amey Nadkar | FALSE | Company Portal - Recruiter Workflow | Deliverable: ApplicantsView.jsx committed ¦ Acceptance: Filter/search returns correct results
| AI & Resume Intelligence | Build candidate-job fit scoring for recruiters (skills match %) | Expected Output: Fit scoring working per candidate | Dheeraj Sarfare | FALSE | Company Portal - Recruiter Workflow | Deliverable: candidate_fit_score.py committed ¦ Acceptance: Scores align with manual review on test set
| Testing, Documentation & QA | Write tests for applicant listing, shortlist/reject, and status transition APIs | Expected Output: Recruiter API tests passing | Aditee Talekar | FALSE | Company Portal - Recruiter Workflow | Deliverable: test_recruiter_api.py committed ¦ Acceptance: Invalid status transitions verified as blocked

## Week 7
IIB — Team ADAG — Week 7 Timeline (Sun Aug 16 – Fri Aug 21)
Phase(s) this week: Company Portal - Recruiter Workflow → College Portal - Admin & Coordinator Core ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-08-16 | Project Lead & Backend Architecture | Build resume download API with access-controlled signed URLs | Expected Output: Resume download working securely | Gaurav Bhosale | FALSE | Company Portal - Recruiter Workflow | Deliverable: resume_download endpoint committed ¦ Acceptance: Only authorized recruiter can download
| Frontend Lead & UI/UX | Build candidate detail panel - resume preview, profile summary | Expected Output: Candidate detail panel functional | Amey Nadkar | FALSE | Company Portal - Recruiter Workflow | Deliverable: CandidateDetail.jsx committed ¦ Acceptance: Resume preview renders correctly
| AI & Resume Intelligence | Build applicant ranking API sorted by fit score for a job | Expected Output: Ranked applicant list API working | Dheeraj Sarfare | FALSE | Company Portal - Recruiter Workflow | Deliverable: rank_applicants endpoint committed ¦ Acceptance: Top candidates match expected ranking
| Testing, Documentation & QA | Write tests for interview scheduling and offer status APIs | Expected Output: Scheduling/offer tests passing | Aditee Talekar | FALSE | Company Portal - Recruiter Workflow | Deliverable: test_interviews_api.py committed ¦ Acceptance: Edge cases - overlapping interviews handled
2026-08-17 | Project Lead & Backend Architecture | Build shortlist/reject candidate API with status transition rules | Expected Output: Shortlist/reject API working | Gaurav Bhosale | FALSE | Company Portal - Recruiter Workflow | Deliverable: candidate_status endpoint committed ¦ Acceptance: Invalid transitions blocked (e.g. rejected to selected)
| Frontend Lead & UI/UX | Build Shortlist/Reject action buttons with confirmation dialogs | Expected Output: Shortlist/reject actions functional | Amey Nadkar | FALSE | Company Portal - Recruiter Workflow | Deliverable: CandidateActions.jsx committed ¦ Acceptance: Actions update status and list instantly
| AI & Resume Intelligence | Build notification content generation for status-change emails (templated) | Expected Output: Notification templates generated | Dheeraj Sarfare | FALSE | Company Portal - Recruiter Workflow | Deliverable: notification_templates.py committed ¦ Acceptance: Templates render correctly with real data
| Testing, Documentation & QA | Write frontend tests for ApplicantsView and InterviewScheduler | Expected Output: Frontend tests passing | Aditee Talekar | FALSE | Company Portal - Recruiter Workflow | Deliverable: ApplicantsView.test.jsx committed ¦ Acceptance: Filtering and scheduling flows covered
2026-08-18 | Project Lead & Backend Architecture | Build interview scheduling API - date, time, mode, interviewer | Expected Output: Interview scheduling API working | Gaurav Bhosale | FALSE | Company Portal - Recruiter Workflow | Deliverable: interviews router committed ¦ Acceptance: Interview record created and retrievable
| Frontend Lead & UI/UX | Build Interview Scheduler UI - calendar picker, mode, interviewer selection | Expected Output: Interview scheduler functional | Amey Nadkar | FALSE | Company Portal - Recruiter Workflow | Deliverable: InterviewScheduler.jsx committed ¦ Acceptance: Scheduled interview appears in candidate timeline
| AI & Resume Intelligence | Improve hiring-trend analytics with company-hiring seasonality patterns | Expected Output: Seasonality analytics added | Dheeraj Sarfare | FALSE | Company Portal - Recruiter Workflow | Deliverable: hiring_seasonality.py committed ¦ Acceptance: Trend chart reflects seasonal pattern on test data
| Testing, Documentation & QA | Manual QA - full recruiter journey from applicant list to offer | Expected Output: Recruiter journey QA report written | Aditee Talekar | FALSE | Company Portal - Recruiter Workflow | Deliverable: qa_report_recruiter_journey.md committed ¦ Acceptance: All bugs logged with severity
2026-08-19 | Project Lead & Backend Architecture | Build offer/selection status API - mark selected, offer released, PPO Also run the weekly team sync: demo full recruiter candidate management flow | Expected Output: Offer status API working Recruiter flow demo delivered | Gaurav Bhosale | FALSE | Company Portal - Recruiter Workflow | Deliverable: offer_status endpoint committed; Demo notes in Wiki ¦ Acceptance: Status changes reflected in student's tracker Team completes shortlist-to-offer flow live
| Frontend Lead & UI/UX | Build Communication panel - send message/email to candidate, bulk notify Also run the weekly team sync: demo recruiter candidate management UI | Expected Output: Communication panel functional Recruiter UI demo delivered | Amey Nadkar | FALSE | Company Portal - Recruiter Workflow | Deliverable: CommunicationPanel.jsx committed; Demo notes in Wiki ¦ Acceptance: Message send confirms and logs correctly Team validates recruiter workflow usability
| AI & Resume Intelligence | Write documentation on candidate fit-scoring methodology for transparency Also run the weekly team sync: present candidate fit-scoring results to team | Expected Output: Fit-scoring methodology documented Fit-scoring demo delivered | Dheeraj Sarfare | FALSE | Company Portal - Recruiter Workflow | Deliverable: fit_scoring_methodology.md committed; Demo notes in Wiki ¦ Acceptance: Reviewed and approved by project lead Team reviews scoring fairness and accuracy
| Testing, Documentation & QA | Update USAGE.md and RBAC matrix with recruiter workflow details Also run the weekly team sync: Week 8 retrospective, Company Portal sign-off | Expected Output: Docs updated Company Portal sign-off | Aditee Talekar | FALSE | Company Portal - Recruiter Workflow | Deliverable: USAGE.md, rbac_matrix.md updated; retro-week8.md committed ¦ Acceptance: Reviewed by project lead Team formally signs off on Company Portal MVP
2026-08-20 | Project Lead & Backend Architecture | Build department management API - create/edit departments per college | Expected Output: Department CRUD working | Gaurav Bhosale | FALSE | College Portal - Admin & Coordinator Core | Deliverable: departments router committed ¦ Acceptance: Departments correctly scoped per college
| Frontend Lead & UI/UX | Build Department Management UI for College Admin | Expected Output: Department management functional | Amey Nadkar | FALSE | College Portal - Admin & Coordinator Core | Deliverable: DepartmentManagement.jsx committed ¦ Acceptance: Admin can create/edit departments
| AI & Resume Intelligence | Build department-wise student search index for Placement Coordinators | Expected Output: Department search index working | Dheeraj Sarfare | FALSE | College Portal - Admin & Coordinator Core | Deliverable: department_search_index.py committed ¦ Acceptance: Search returns correct department subset
| Testing, Documentation & QA | Write tests for department management and coordinator creation APIs | Expected Output: Department/coordinator tests passing | Aditee Talekar | FALSE | College Portal - Admin & Coordinator Core | Deliverable: test_department_api.py committed ¦ Acceptance: RBAC boundaries verified for College Admin
2026-08-21 | Project Lead & Backend Architecture | Build Placement Coordinator account creation API (by College Admin) | Expected Output: Coordinator creation API working | Gaurav Bhosale | FALSE | College Portal - Admin & Coordinator Core | Deliverable: coordinator_management endpoint committed ¦ Acceptance: New coordinator can activate and log in
| Frontend Lead & UI/UX | Build Placement Coordinator account creation UI for College Admin | Expected Output: Coordinator creation UI functional | Amey Nadkar | FALSE | College Portal - Admin & Coordinator Core | Deliverable: CoordinatorManagement.jsx committed ¦ Acceptance: Admin can invite and view coordinators
| AI & Resume Intelligence | Build department performance metrics (placement rate, avg package) | Expected Output: Department metrics computed | Dheeraj Sarfare | FALSE | College Portal - Admin & Coordinator Core | Deliverable: department_metrics.py committed ¦ Acceptance: Metrics match manually verified sample data
| Testing, Documentation & QA | Write tests for review queue, approval, and pin/archive APIs | Expected Output: Review workflow tests passing | Aditee Talekar | FALSE | College Portal - Admin & Coordinator Core | Deliverable: test_review_workflow.py committed ¦ Acceptance: Only coordinator role can approve, verified

## Week 8
IIB — Team ADAG — Week 8 Timeline (Sun Aug 23 – Fri Aug 28)
Phase(s) this week: College Portal - Admin & Coordinator Core → College Portal - Student Tracking & Reports ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-08-23 | Project Lead & Backend Architecture | Build listing review queue API - pending jobs/internships for approval | Expected Output: Review queue API working | Gaurav Bhosale | FALSE | College Portal - Admin & Coordinator Core | Deliverable: review_queue endpoint committed ¦ Acceptance: Only unapproved listings appear in queue
| Frontend Lead & UI/UX | Build Listing Review Queue UI for Placement Coordinator | Expected Output: Review queue UI functional | Amey Nadkar | FALSE | College Portal - Admin & Coordinator Core | Deliverable: ReviewQueue.jsx committed ¦ Acceptance: Pending listings display with detail preview
| AI & Resume Intelligence | Build auto-flagging for suspicious/spam listings before human review | Expected Output: Auto-flagging POC working | Dheeraj Sarfare | FALSE | College Portal - Admin & Coordinator Core | Deliverable: spam_flagging_poc.py committed ¦ Acceptance: Flags 3 seeded spam listings correctly
| Testing, Documentation & QA | Write frontend tests for ReviewQueue and ApprovalActions | Expected Output: Frontend tests passing | Aditee Talekar | FALSE | College Portal - Admin & Coordinator Core | Deliverable: ReviewQueue.test.jsx committed ¦ Acceptance: Approve/reject flows covered
2026-08-24 | Project Lead & Backend Architecture | Build approve/reject/edit listing API restricted to Placement Coordinator role | Expected Output: Approval API working with RBAC | Gaurav Bhosale | FALSE | College Portal - Admin & Coordinator Core | Deliverable: listing_approval endpoint committed ¦ Acceptance: Only Placement Coordinator role can approve
| Frontend Lead & UI/UX | Build Approve/Reject/Edit action UI with reason/comment field | Expected Output: Approval actions functional | Amey Nadkar | FALSE | College Portal - Admin & Coordinator Core | Deliverable: ApprovalActions.jsx committed ¦ Acceptance: Reject requires a reason before submitting
| AI & Resume Intelligence | Note: flagging is advisory only - final approval always by Placement Coordinator | Expected Output: Advisory-only behavior documented and enforced | Dheeraj Sarfare | FALSE | College Portal - Admin & Coordinator Core | Deliverable: Flag confidence never bypasses human review ¦ Acceptance: Verified flagged listings still require manual approval
| Testing, Documentation & QA | Manual QA - full College Admin to Coordinator approval journey | Expected Output: College journey QA report written | Aditee Talekar | FALSE | College Portal - Admin & Coordinator Core | Deliverable: qa_report_college_journey.md committed ¦ Acceptance: All bugs logged with severity
2026-08-25 | Project Lead & Backend Architecture | Build pin/archive listing API for coordinators Also run the weekly team sync: demo department setup and coordinator approval flow | Expected Output: Pin/archive API working College Portal demo delivered | Gaurav Bhosale | FALSE | College Portal - Admin & Coordinator Core | Deliverable: listing_pin endpoint committed; Demo notes in Wiki ¦ Acceptance: Pinned listings sort to top of student view Team approves a test listing live
| Frontend Lead & UI/UX | Build Pin/Archive toggle controls on listing cards for coordinators Also run the weekly team sync: demo College Portal review workflow to team | Expected Output: Pin/archive controls functional Review workflow demo delivered | Amey Nadkar | FALSE | College Portal - Admin & Coordinator Core | Deliverable: PinArchiveControls.jsx committed; Demo notes in Wiki ¦ Acceptance: Pinned listings show a visual badge Team validates coordinator UX
| AI & Resume Intelligence | Build search intelligence improvements for coordinator student search (fuzzy match) Also run the weekly team sync: present department metrics and spam-flagging to team | Expected Output: Fuzzy search working for student search AI progress demo delivered | Dheeraj Sarfare | FALSE | College Portal - Admin & Coordinator Core | Deliverable: fuzzy_search.py committed; Demo notes in Wiki ¦ Acceptance: Handles common name misspellings correctly Team confirms human-verification-only policy is respected
| Testing, Documentation & QA | Update RBAC matrix and USAGE.md with College Portal details Also run the weekly team sync: Week 9 retrospective on College Portal progress | Expected Output: Docs updated Week 9 retro completed | Aditee Talekar | FALSE | College Portal - Admin & Coordinator Core | Deliverable: rbac_matrix.md, USAGE.md updated; retro-week9.md committed ¦ Acceptance: Reviewed by project lead Blockers logged as GitHub Issues
2026-08-26 | Project Lead & Backend Architecture | Build student tracking API for coordinators - placement/internship status | Expected Output: Student tracking API working | Gaurav Bhosale | FALSE | College Portal - Student Tracking & Reports | Deliverable: student_tracking endpoint committed ¦ Acceptance: Status reflects real application data
| Frontend Lead & UI/UX | Build Student Tracking dashboard for Placement Coordinators | Expected Output: Student tracking UI functional | Amey Nadkar | FALSE | College Portal - Student Tracking & Reports | Deliverable: StudentTracking.jsx committed ¦ Acceptance: Status badges reflect live data
| AI & Resume Intelligence | Build placement-rate and package analytics for department reports | Expected Output: Analytics feeding into reports correctly | Dheeraj Sarfare | FALSE | College Portal - Student Tracking & Reports | Deliverable: placement_analytics.py committed ¦ Acceptance: Numbers match manual verification
| Testing, Documentation & QA | Write tests for student tracking and report generation APIs | Expected Output: Tracking/report tests passing | Aditee Talekar | FALSE | College Portal - Student Tracking & Reports | Deliverable: test_reports_api.py committed ¦ Acceptance: Generated report content verified against fixtures
2026-08-27 | Project Lead & Backend Architecture | Build department-wise and college-wide report generation API (Excel/CSV) | Expected Output: Report generation API working | Gaurav Bhosale | FALSE | College Portal - Student Tracking & Reports | Deliverable: reports router committed ¦ Acceptance: Generated file opens correctly with expected columns
| Frontend Lead & UI/UX | Build Reports page - export Excel/CSV, department and time-range filters | Expected Output: Reports UI functional | Amey Nadkar | FALSE | College Portal - Student Tracking & Reports | Deliverable: ReportsPage.jsx committed ¦ Acceptance: Export button downloads correctly filtered file
| AI & Resume Intelligence | Build data export formatting logic - clean Excel with proper headers | Expected Output: Formatted Excel export working | Dheeraj Sarfare | FALSE | College Portal - Student Tracking & Reports | Deliverable: excel_export_formatter.py committed ¦ Acceptance: Exported file has correct headers and formatting
| Testing, Documentation & QA | Write tests for College Admin settings and notification APIs | Expected Output: Settings/notification tests passing | Aditee Talekar | FALSE | College Portal - Student Tracking & Reports | Deliverable: test_college_settings.py committed ¦ Acceptance: Settings persistence verified
2026-08-28 | Project Lead & Backend Architecture | Build monthly and annual report scheduling/aggregation API | Expected Output: Scheduled report aggregation working | Gaurav Bhosale | FALSE | College Portal - Student Tracking & Reports | Deliverable: report_scheduler.py committed ¦ Acceptance: Monthly report matches manually summed data
| Frontend Lead & UI/UX | Build College Admin Settings page - branding, notifications, access control | Expected Output: Settings page functional | Amey Nadkar | FALSE | College Portal - Student Tracking & Reports | Deliverable: CollegeSettings.jsx committed ¦ Acceptance: Changes save and reflect across portal
| AI & Resume Intelligence | Build anomaly detection for reporting data (missing/duplicate records) | Expected Output: Anomaly detection POC working | Dheeraj Sarfare | FALSE | College Portal - Student Tracking & Reports | Deliverable: report_anomaly_detection.py committed ¦ Acceptance: Flags 3 seeded anomalies correctly
| Testing, Documentation & QA | Manual QA - verify Excel/CSV report content matches actual DB data | Expected Output: Report accuracy QA completed | Aditee Talekar | FALSE | College Portal - Student Tracking & Reports | Deliverable: qa_report_accuracy.md committed ¦ Acceptance: Spot-checked 10 records match exactly

## Week 9
IIB — Team ADAG — Week 9 Timeline (Sun Aug 30 – Fri Sep 4)
Phase(s) this week: College Portal - Student Tracking & Reports → Resume Intelligence - Upload & Parsing ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-08-30 | Project Lead & Backend Architecture | Build College Admin settings API - branding, notifications, access control | Expected Output: College settings API working | Gaurav Bhosale | FALSE | College Portal - Student Tracking & Reports | Deliverable: college_settings endpoint committed ¦ Acceptance: Settings persist and apply correctly
| Frontend Lead & UI/UX | Build Notification Center UI for coordinators and students | Expected Output: Notification center functional | Amey Nadkar | FALSE | College Portal - Student Tracking & Reports | Deliverable: NotificationCenter.jsx committed ¦ Acceptance: New events appear without page refresh
| AI & Resume Intelligence | Support Aditee with cross-platform data validation for report accuracy | Expected Output: Validation script shared with QA | Dheeraj Sarfare | FALSE | College Portal - Student Tracking & Reports | Deliverable: report_validation_helper.py committed ¦ Acceptance: QA confirms validation logic is correct
| Testing, Documentation & QA | Write frontend tests for ReportsPage and NotificationCenter | Expected Output: Frontend tests passing | Aditee Talekar | FALSE | College Portal - Student Tracking & Reports | Deliverable: ReportsPage.test.jsx committed ¦ Acceptance: Export and notification flows covered
2026-08-31 | Project Lead & Backend Architecture | Build notification API - student selected, internship started events Also run the weekly team sync: demo student tracking and report generation | Expected Output: Notification triggers working Reports demo delivered | Gaurav Bhosale | FALSE | College Portal - Student Tracking & Reports | Deliverable: notifications router committed; Demo notes in Wiki ¦ Acceptance: Event triggers correct notification record Team generates a sample report live
| Frontend Lead & UI/UX | Build resume view access for coordinators within student tracking Also run the weekly team sync: demo College Admin settings and notifications | Expected Output: Resume view functional Settings demo delivered | Amey Nadkar | FALSE | College Portal - Student Tracking & Reports | Deliverable: ResumeViewPanel.jsx committed; Demo notes in Wiki ¦ Acceptance: Coordinator can preview student resume Team validates notification delivery
| AI & Resume Intelligence | Document data pipeline from raw application data to final report Also run the weekly team sync: present report analytics accuracy results | Expected Output: Data pipeline documented Analytics demo delivered | Dheeraj Sarfare | FALSE | College Portal - Student Tracking & Reports | Deliverable: report_data_pipeline.md committed; Demo notes in Wiki ¦ Acceptance: Diagram reviewed by team Team confirms report numbers are trustworthy
| Testing, Documentation & QA | Update USAGE.md with reporting and notification features Also run the weekly team sync: Week 10 retrospective, College Portal sign-off | Expected Output: Docs updated College Portal sign-off | Aditee Talekar | FALSE | College Portal - Student Tracking & Reports | Deliverable: USAGE.md updated; retro-week10.md committed ¦ Acceptance: Reviewed by project lead Team formally signs off on College Portal MVP
2026-09-01 | Project Lead & Backend Architecture | Build resume upload API with file-type/size validation and storage | Expected Output: Resume upload API working | Gaurav Bhosale | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: resume_upload endpoint committed ¦ Acceptance: Only PDF/DOCX under size limit accepted
| Frontend Lead & UI/UX | Build Resume Upload UI with drag-and-drop and progress indicator | Expected Output: Upload UI functional | Amey Nadkar | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: ResumeUpload.jsx committed ¦ Acceptance: Upload shows progress and success state
| AI & Resume Intelligence | Productionize resume parsing pipeline - robust error handling for malformed files | Expected Output: Production-grade parser deployed | Dheeraj Sarfare | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: resume_parser_v2.py committed ¦ Acceptance: Handles 10 malformed test files gracefully
| Testing, Documentation & QA | Write tests for resume upload, versioning, and parsing-trigger APIs | Expected Output: Resume API tests passing | Aditee Talekar | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: test_resume_api.py committed ¦ Acceptance: Invalid file types rejected in tests
2026-09-02 | Project Lead & Backend Architecture | Build resume versioning API - store and list multiple versions per student | Expected Output: Resume versioning API working | Gaurav Bhosale | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: resume_versions endpoint committed ¦ Acceptance: Multiple versions retrievable in order
| Frontend Lead & UI/UX | Build Resume Version History UI - view/switch between versions | Expected Output: Version history UI functional | Amey Nadkar | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: ResumeVersions.jsx committed ¦ Acceptance: Switching versions updates displayed data
| AI & Resume Intelligence | Build resume scoring algorithm - completeness, keyword relevance, formatting | Expected Output: Scoring algorithm working | Dheeraj Sarfare | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: resume_scoring.py committed ¦ Acceptance: Scores align with manual review on test set
| Testing, Documentation & QA | Build a test corpus of 30 diverse resumes for parsing accuracy testing | Expected Output: Test resume corpus assembled | Aditee Talekar | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: test_resumes/ committed ¦ Acceptance: Corpus covers varied formats and layouts
2026-09-03 | Project Lead & Backend Architecture | Build API to trigger AI parsing service on upload and store results | Expected Output: Parsing trigger + storage working | Gaurav Bhosale | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: resume_parse_trigger endpoint committed ¦ Acceptance: Parsed data saved against correct resume version
| Frontend Lead & UI/UX | Build Resume Score display - visual breakdown of scoring factors | Expected Output: Score display functional | Amey Nadkar | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: ResumeScoreCard.jsx committed ¦ Acceptance: Score and factors render clearly
| AI & Resume Intelligence | Build resume-to-profile field mapping (skills, education, experience, projects) | Expected Output: Field mapping working accurately | Dheeraj Sarfare | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: resume_field_mapping.py committed ¦ Acceptance: Maps correctly on 10 diverse test resumes
| Testing, Documentation & QA | Run parsing accuracy evaluation against test corpus, report results | Expected Output: Parsing accuracy report generated | Aditee Talekar | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: parsing_accuracy_report.md committed ¦ Acceptance: Accuracy % documented per field type
2026-09-04 | Project Lead & Backend Architecture | Build resume score storage and retrieval API | Expected Output: Resume score API working | Gaurav Bhosale | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: resume_score endpoint committed ¦ Acceptance: Score persists and returns with resume
| Frontend Lead & UI/UX | Build profile auto-fill review screen after resume parsing | Expected Output: Auto-fill review UI functional | Amey Nadkar | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: AutoFillReview.jsx committed ¦ Acceptance: Student can confirm/edit parsed fields
| AI & Resume Intelligence | Build ATS-compatibility check logic (formatting/parsing risk detection) | Expected Output: ATS check logic working | Dheeraj Sarfare | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: ats_check.py committed ¦ Acceptance: Correctly flags 5 seeded ATS-risk resumes
| Testing, Documentation & QA | Write frontend tests for ResumeUpload and ResumeScoreCard | Expected Output: Frontend tests passing | Aditee Talekar | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: ResumeUpload.test.jsx committed ¦ Acceptance: Upload and score display flows covered

## Week 10
IIB — Team ADAG — Week 10 Timeline (Sun Sep 6 – Fri Sep 11)
Phase(s) this week: Resume Intelligence - Upload & Parsing → Resume Intelligence - Builder & Premium Tools ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-09-06 | Project Lead & Backend Architecture | Build endpoint to fetch structured resume data for profile auto-fill Also run the weekly team sync: demo resume upload-to-parsing-to-score pipeline | Expected Output: Auto-fill API working Pipeline demo delivered | Gaurav Bhosale | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: resume_autofill endpoint committed; Demo notes in Wiki ¦ Acceptance: Profile fields populate from parsed resume Team uploads a real resume live
| Frontend Lead & UI/UX | Build Resume Templates gallery UI (selection screen) Also run the weekly team sync: demo resume upload and scoring experience | Expected Output: Templates gallery functional Resume UX demo delivered | Amey Nadkar | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: ResumeTemplates.jsx committed; Demo notes in Wiki ¦ Acceptance: Templates preview correctly before selection Team validates upload flow smoothness
| AI & Resume Intelligence | Optimize parsing pipeline performance for concurrent uploads Also run the weekly team sync: present resume scoring and ATS check accuracy | Expected Output: Parsing performance improved AI accuracy demo delivered | Dheeraj Sarfare | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: Performance benchmark documented; Demo notes in Wiki ¦ Acceptance: Handles 20 concurrent uploads under target latency Team reviews scoring fairness
| Testing, Documentation & QA | Update USAGE.md with Resume Intelligence features Also run the weekly team sync: Week 11 retrospective on parsing accuracy | Expected Output: Docs updated Week 11 retro completed | Aditee Talekar | FALSE | Resume Intelligence - Upload & Parsing | Deliverable: USAGE.md updated; retro-week11.md committed ¦ Acceptance: Reviewed by project lead Accuracy gaps logged as GitHub Issues
2026-09-07 | Project Lead & Backend Architecture | Build resume builder save/draft API - structured sections stored as JSON | Expected Output: Resume builder draft API working | Gaurav Bhosale | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: resume_builder endpoint committed ¦ Acceptance: Draft saves and reloads correctly
| Frontend Lead & UI/UX | Build Resume Builder UI - section-by-section editable form | Expected Output: Resume builder UI functional | Amey Nadkar | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: ResumeBuilder.jsx committed ¦ Acceptance: Sections save incrementally without data loss
| AI & Resume Intelligence | Build AI resume optimization logic - suggest phrasing, quantify achievements | Expected Output: Optimization logic working | Dheeraj Sarfare | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: resume_optimizer.py committed ¦ Acceptance: Suggestions improve clarity on 10 test resumes
| Testing, Documentation & QA | Write tests for resume builder save/draft and export APIs | Expected Output: Builder API tests passing | Aditee Talekar | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: test_resume_builder_api.py committed ¦ Acceptance: Draft persistence verified across sessions
2026-09-08 | Project Lead & Backend Architecture | Build resume export API - generate PDF/DOCX from builder data | Expected Output: Resume export API working | Gaurav Bhosale | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: resume_export endpoint committed ¦ Acceptance: Exported file matches builder content
| Frontend Lead & UI/UX | Build live resume preview pane synced with builder input | Expected Output: Live preview functional | Amey Nadkar | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: ResumePreview.jsx committed ¦ Acceptance: Preview updates in real time as user types
| AI & Resume Intelligence | Build resume-template content mapping (fill template with structured data) | Expected Output: Template mapping working | Dheeraj Sarfare | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: template_mapper.py committed ¦ Acceptance: Maps correctly across 5 template types
| Testing, Documentation & QA | Write tests for premium gating middleware across all premium endpoints | Expected Output: Premium gating tests passing | Aditee Talekar | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: test_premium_gate.py committed ¦ Acceptance: Non-premium access correctly blocked in all cases
2026-09-09 | Project Lead & Backend Architecture | Build premium feature gating middleware (subscription/entitlement check) | Expected Output: Premium gating working | Gaurav Bhosale | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: premium_gate dependency committed ¦ Acceptance: Non-premium users blocked from premium endpoints
| Frontend Lead & UI/UX | Build template selection and switching within the builder | Expected Output: Template switching functional | Amey Nadkar | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: TemplateSwitcher.jsx committed ¦ Acceptance: Switching preserves entered content
| AI & Resume Intelligence | Build resume comparison scoring - before/after optimization score delta | Expected Output: Comparison scoring working | Dheeraj Sarfare | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: optimization_score_delta.py committed ¦ Acceptance: Score improves consistently after optimization
| Testing, Documentation & QA | Write frontend tests for ResumeBuilder and OptimizationResults | Expected Output: Frontend tests passing | Aditee Talekar | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: ResumeBuilder.test.jsx committed ¦ Acceptance: Section editing and preview sync covered
2026-09-10 | Project Lead & Backend Architecture | Build AI Resume Optimization request/response API (premium) | Expected Output: Optimization API working | Gaurav Bhosale | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: resume_optimize endpoint committed ¦ Acceptance: Returns improved resume suggestions
| Frontend Lead & UI/UX | Build Premium upsell UI - paywall screen for AI optimization | Expected Output: Premium upsell UI functional | Amey Nadkar | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: PremiumUpsell.jsx committed ¦ Acceptance: Non-premium users see clear upgrade path
| AI & Resume Intelligence | Build AI Cover Letter Generator - resume + job description to cover letter | Expected Output: Cover letter generator working | Dheeraj Sarfare | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: cover_letter_generator.py committed ¦ Acceptance: Generates coherent letter from test inputs
| Testing, Documentation & QA | Evaluate AI-optimized resumes for quality/tone consistency across 10 samples | Expected Output: Optimization quality report written | Aditee Talekar | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: optimization_quality_report.md committed ¦ Acceptance: Findings shared with Dheeraj for tuning
2026-09-11 | Project Lead & Backend Architecture | Build resume template metadata API - list, preview, categories Also run the weekly team sync: demo resume builder and premium optimization flow | Expected Output: Template metadata API working Builder demo delivered | Gaurav Bhosale | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: resume_templates endpoint committed; Demo notes in Wiki ¦ Acceptance: Templates filterable by category Team builds and exports a resume live
| Frontend Lead & UI/UX | Build AI Resume Optimization results UI - before/after comparison Also run the weekly team sync: demo full resume builder and premium experience | Expected Output: Optimization results UI functional Premium UX demo delivered | Amey Nadkar | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: OptimizationResults.jsx committed; Demo notes in Wiki ¦ Acceptance: Before/after shown side-by-side clearly Team validates premium upgrade flow
| AI & Resume Intelligence | Write prompt engineering documentation for resume optimization prompts Also run the weekly team sync: present AI optimization and cover letter generator results | Expected Output: Prompt docs published AI feature demo delivered | Dheeraj Sarfare | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: resume_prompts.md committed; Demo notes in Wiki ¦ Acceptance: Reviewed and approved by project lead Team reviews output quality
| Testing, Documentation & QA | Update USAGE.md with Resume Builder and Premium feature docs Also run the weekly team sync: Week 12 retrospective, Resume Intelligence sign-off | Expected Output: Docs updated Resume Intelligence sign-off | Aditee Talekar | FALSE | Resume Intelligence - Builder & Premium Tools | Deliverable: USAGE.md updated; retro-week12.md committed ¦ Acceptance: Reviewed by project lead Team formally signs off on Resume Intelligence MVP

## Week 11
IIB — Team ADAG — Week 11 Timeline (Sun Sep 13 – Fri Sep 18)
Phase(s) this week: AI Recommendation Engine - Core → AI Career Assistant & Premium Intelligence ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-09-13 | Project Lead & Backend Architecture | Build unified recommendation API gateway - single endpoint for all surfaces | Expected Output: Recommendation gateway API working | Gaurav Bhosale | FALSE | AI Recommendation Engine - Core | Deliverable: recommendation_gateway endpoint committed ¦ Acceptance: Serves student, external, and dashboard requests consistently
| Frontend Lead & UI/UX | Build Recommended Jobs/Internships section for College Student dashboard | Expected Output: Recommended section functional | Amey Nadkar | FALSE | AI Recommendation Engine - Core | Deliverable: RecommendedJobs.jsx committed ¦ Acceptance: Section populates with live recommendation data
| AI & Resume Intelligence | Consolidate skill-based, resume-based, and feedback-based scoring into one engine | Expected Output: Unified scoring engine implemented | Dheeraj Sarfare | FALSE | AI Recommendation Engine - Core | Deliverable: unified_recommender.py committed ¦ Acceptance: Single call returns blended score per listing
| Testing, Documentation & QA | Write tests for the unified recommendation gateway and caching layer | Expected Output: Gateway/cache tests passing | Aditee Talekar | FALSE | AI Recommendation Engine - Core | Deliverable: test_recommendation_gateway.py committed ¦ Acceptance: Cache hit/miss behavior verified
2026-09-14 | Project Lead & Backend Architecture | Build caching layer for recommendation results (Redis-backed) | Expected Output: Recommendation caching working | Gaurav Bhosale | FALSE | AI Recommendation Engine - Core | Deliverable: recommendation_cache.py committed ¦ Acceptance: Cache hit reduces response time measurably
| Frontend Lead & UI/UX | Build Recommended section for External Student dashboard | Expected Output: External recommendations functional | Amey Nadkar | FALSE | AI Recommendation Engine - Core | Deliverable: ExternalRecommended.jsx committed ¦ Acceptance: Section shows AI-recommended and trending items
| AI & Resume Intelligence | Tune recommendation weighting using Week 5-8 feedback signal data | Expected Output: Weighting tuned and validated | Dheeraj Sarfare | FALSE | AI Recommendation Engine - Core | Deliverable: recommender_weights.json committed ¦ Acceptance: Precision improves on held-out test set
| Testing, Documentation & QA | Build evaluation harness measuring recommendation precision/recall on test set | Expected Output: Evaluation harness built and running | Aditee Talekar | FALSE | AI Recommendation Engine - Core | Deliverable: eval_harness.py committed ¦ Acceptance: Metrics reproducible across runs
2026-09-15 | Project Lead & Backend Architecture | Build recommendation feedback API - track click-through and apply-through | Expected Output: Feedback tracking API working | Gaurav Bhosale | FALSE | AI Recommendation Engine - Core | Deliverable: recommendation_feedback endpoint committed ¦ Acceptance: Feedback events recorded correctly
| Frontend Lead & UI/UX | Build Trending Jobs/Internships widget for dashboards | Expected Output: Trending widget functional | Amey Nadkar | FALSE | AI Recommendation Engine - Core | Deliverable: TrendingWidget.jsx committed ¦ Acceptance: Widget reflects live trending data
| AI & Resume Intelligence | Build cold-start recommendation strategy for brand-new users | Expected Output: Cold-start strategy working | Dheeraj Sarfare | FALSE | AI Recommendation Engine - Core | Deliverable: cold_start_recommender.py committed ¦ Acceptance: New users receive reasonable recommendations immediately
| Testing, Documentation & QA | Write frontend tests for RecommendedJobs and TrendingWidget | Expected Output: Frontend tests passing | Aditee Talekar | FALSE | AI Recommendation Engine - Core | Deliverable: RecommendedJobs.test.jsx committed ¦ Acceptance: Data rendering and empty states covered
2026-09-16 | Project Lead & Backend Architecture | Build A/B testing scaffold for comparing recommendation strategies | Expected Output: A/B testing scaffold working | Gaurav Bhosale | FALSE | AI Recommendation Engine - Core | Deliverable: ab_testing.py committed ¦ Acceptance: Requests split correctly between variants
| Frontend Lead & UI/UX | Build recommendation feedback capture (click, apply) wired to backend | Expected Output: Feedback capture functional | Amey Nadkar | FALSE | AI Recommendation Engine - Core | Deliverable: Feedback tracking wired in UI ¦ Acceptance: Click/apply events recorded correctly in backend
| AI & Resume Intelligence | Build AI Skill Gap Analysis feature - target role vs current skills | Expected Output: Skill gap analysis working | Dheeraj Sarfare | FALSE | AI Recommendation Engine - Core | Deliverable: skill_gap_analysis.py committed ¦ Acceptance: Returns accurate missing-skill list for test profiles
| Testing, Documentation & QA | Manual QA - verify recommendations are relevant across 10 diverse test profiles | Expected Output: Relevance QA report written | Aditee Talekar | FALSE | AI Recommendation Engine - Core | Deliverable: qa_report_recommendations.md committed ¦ Acceptance: Findings shared with Dheeraj for tuning
2026-09-17 | Project Lead & Backend Architecture | Integrate recommendation engine with notification triggers (new match alerts) Also run the weekly team sync: demo unified recommendation gateway across all surfaces | Expected Output: Match-alert notifications working Gateway demo delivered | Gaurav Bhosale | FALSE | AI Recommendation Engine - Core | Deliverable: match_alert_trigger.py committed; Demo notes in Wiki ¦ Acceptance: New strong match triggers a notification Team validates consistent results across surfaces
| Frontend Lead & UI/UX | Build empty/loading states for recommendation sections Also run the weekly team sync: demo recommendation sections across dashboards | Expected Output: Empty/loading states functional Recommendations UI demo delivered | Amey Nadkar | FALSE | AI Recommendation Engine - Core | Deliverable: RecommendationStates.jsx committed; Demo notes in Wiki ¦ Acceptance: New users see helpful empty-state messaging Team confirms sections load correctly for all roles
| AI & Resume Intelligence | Build AI Learning Suggestions - courses/resources for skill gaps Also run the weekly team sync: present unified engine performance and skill-gap results | Expected Output: Learning suggestions working Engine performance demo delivered | Dheeraj Sarfare | FALSE | AI Recommendation Engine - Core | Deliverable: learning_suggestions.py committed; Demo notes in Wiki ¦ Acceptance: Suggestions relevant to identified skill gaps Team reviews precision/recall metrics
| Testing, Documentation & QA | Update USAGE.md with Recommendation Engine documentation Also run the weekly team sync: Week 13 retrospective on recommendation quality | Expected Output: Docs updated Week 13 retro completed | Aditee Talekar | FALSE | AI Recommendation Engine - Core | Deliverable: USAGE.md updated; retro-week13.md committed ¦ Acceptance: Reviewed by project lead Quality gaps logged as GitHub Issues
2026-09-18 | Project Lead & Backend Architecture | Build AI Career Roadmap API - stores and serves generated roadmaps per user | Expected Output: Career roadmap API working | Gaurav Bhosale | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: career_roadmap endpoint committed ¦ Acceptance: Roadmap persists and retrieves correctly
| Frontend Lead & UI/UX | Build AI Career Roadmap UI - visual timeline of suggested steps | Expected Output: Career roadmap UI functional | Amey Nadkar | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: CareerRoadmap.jsx committed ¦ Acceptance: Timeline renders roadmap steps clearly
| AI & Resume Intelligence | Build AI Career Roadmap generation logic - milestones based on target role | Expected Output: Roadmap generation working | Dheeraj Sarfare | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: career_roadmap_generator.py committed ¦ Acceptance: Roadmap logically sequenced for test target roles
| Testing, Documentation & QA | Write tests for career roadmap, cover letter, and entitlement APIs | Expected Output: Premium API tests passing | Aditee Talekar | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: test_premium_api.py committed ¦ Acceptance: Entitlement checks verified across endpoints

## Week 12
IIB — Team ADAG — Week 12 Timeline (Sun Sep 20 – Fri Sep 25)
Phase(s) this week: AI Career Assistant & Premium Intelligence → Excel Automation - Export & Sync ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-09-20 | Project Lead & Backend Architecture | Build AI Cover Letter API - generate and store cover letters per application | Expected Output: Cover letter API working | Gaurav Bhosale | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: cover_letter endpoint committed ¦ Acceptance: Generated letter linked to correct application
| Frontend Lead & UI/UX | Build AI Cover Letter Generator UI - input job, generate, edit, download | Expected Output: Cover letter UI functional | Amey Nadkar | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: CoverLetterGenerator.jsx committed ¦ Acceptance: Generated letter editable and downloadable
| AI & Resume Intelligence | Refine AI Cover Letter Generator with job-specific tone/keyword alignment | Expected Output: Cover letter quality improved | Dheeraj Sarfare | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: cover_letter_generator_v2.py committed ¦ Acceptance: Letters align to job keywords on test set
| Testing, Documentation & QA | Write tests for AI Career Coach session/context handling | Expected Output: Career coach tests passing | Aditee Talekar | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: test_career_coach.py committed ¦ Acceptance: Multi-turn context verified in test conversation
2026-09-21 | Project Lead & Backend Architecture | Build premium entitlement management API - upgrade/downgrade, feature flags | Expected Output: Entitlement API working | Gaurav Bhosale | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: entitlements endpoint committed ¦ Acceptance: Feature access updates immediately on upgrade
| Frontend Lead & UI/UX | Build AI Career Coach chat UI - conversational interface | Expected Output: Career coach chat UI functional | Amey Nadkar | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: CareerCoachChat.jsx committed ¦ Acceptance: Messages send/receive with conversation history
| AI & Resume Intelligence | Build AI Career Coach conversational logic with context/session memory | Expected Output: Career coach logic working | Dheeraj Sarfare | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: career_coach_engine.py committed ¦ Acceptance: Maintains context across 5-turn test conversation
| Testing, Documentation & QA | Write frontend tests for CareerRoadmap and CareerCoachChat | Expected Output: Frontend tests passing | Aditee Talekar | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: CareerRoadmap.test.jsx committed ¦ Acceptance: Rendering and chat interaction covered
2026-09-22 | Project Lead & Backend Architecture | Build AI Career Coach conversational API - session-based Q&A | Expected Output: Career coach API working | Gaurav Bhosale | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: career_coach endpoint committed ¦ Acceptance: Multi-turn conversation context preserved
| Frontend Lead & UI/UX | Build Premium Features hub page - overview of all premium tools | Expected Output: Premium hub page functional | Amey Nadkar | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: PremiumHub.jsx committed ¦ Acceptance: All premium features accessible from one place
| AI & Resume Intelligence | Build priority-recommendation logic - boosted relevance for premium users | Expected Output: Priority recommendation logic working | Dheeraj Sarfare | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: priority_recommender.py committed ¦ Acceptance: Premium users see measurably better-ranked results
| Testing, Documentation & QA | Manual QA - evaluate roadmap/cover-letter/coach quality across 10 personas | Expected Output: Quality QA report written | Aditee Talekar | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: qa_report_ai_assistant.md committed ¦ Acceptance: Findings shared with Dheeraj for tuning
2026-09-23 | Project Lead & Backend Architecture | Build priority-recommendation and advanced-analytics premium endpoints Also run the weekly team sync: demo AI Career Assistant premium feature set | Expected Output: Premium endpoints working Career Assistant demo delivered | Gaurav Bhosale | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: premium_features router committed; Demo notes in Wiki ¦ Acceptance: Only premium users receive advanced data Team walks through full premium journey
| Frontend Lead & UI/UX | Build unlimited job alerts settings UI (premium) Also run the weekly team sync: demo full AI Career Assistant UI experience | Expected Output: Job alerts settings functional Career Assistant UX demo delivered | Amey Nadkar | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: JobAlertsSettings.jsx committed; Demo notes in Wiki ¦ Acceptance: Alert preferences save and apply correctly Team validates premium UX quality
| AI & Resume Intelligence | Build advanced analytics computation for premium external students Also run the weekly team sync: present AI Career Assistant output quality | Expected Output: Advanced analytics working AI quality demo delivered | Dheeraj Sarfare | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: advanced_analytics.py committed; Demo notes in Wiki ¦ Acceptance: Metrics computed correctly on test accounts Team reviews roadmap and coach output quality
| Testing, Documentation & QA | Update USAGE.md with full Premium/AI Career Assistant documentation Also run the weekly team sync: Week 14 retrospective, Recommendation Engine sign-off | Expected Output: Docs updated Recommendation Engine sign-off | Aditee Talekar | FALSE | AI Career Assistant & Premium Intelligence | Deliverable: USAGE.md updated; retro-week14.md committed ¦ Acceptance: Reviewed by project lead Team formally signs off on full AI feature set
2026-09-24 | Project Lead & Backend Architecture | Build Excel export API using openpyxl with formatted headers/styling | Expected Output: Excel export API working | Gaurav Bhosale | FALSE | Excel Automation - Export & Sync | Deliverable: excel_export endpoint committed ¦ Acceptance: Exported file opens cleanly in Excel with formatting
| Frontend Lead & UI/UX | Build Excel/Sheets export settings UI - choose format, columns, filters | Expected Output: Export settings UI functional | Amey Nadkar | FALSE | Excel Automation - Export & Sync | Deliverable: ExportSettings.jsx committed ¦ Acceptance: Selected options reflected in exported file
| AI & Resume Intelligence | Build data transformation layer - normalize DB records into Excel/Sheets rows | Expected Output: Transformation layer working | Dheeraj Sarfare | FALSE | Excel Automation - Export & Sync | Deliverable: excel_data_transformer.py committed ¦ Acceptance: Output rows match expected schema on test data
| Testing, Documentation & QA | Write tests for Excel export API - verify structure, formatting, content | Expected Output: Excel export tests passing | Aditee Talekar | FALSE | Excel Automation - Export & Sync | Deliverable: test_excel_export.py committed ¦ Acceptance: Exported file structure matches spec
2026-09-25 | Project Lead & Backend Architecture | Build Google Sheets API integration - OAuth setup and write access | Expected Output: Google Sheets integration working | Gaurav Bhosale | FALSE | Excel Automation - Export & Sync | Deliverable: google_sheets_client.py committed ¦ Acceptance: Test data writes successfully to a live sheet
| Frontend Lead & UI/UX | Build Google Sheets connection UI - OAuth consent, link/unlink sheet | Expected Output: Sheets connection UI functional | Amey Nadkar | FALSE | Excel Automation - Export & Sync | Deliverable: GoogleSheetsConnect.jsx committed ¦ Acceptance: Coordinator can link and unlink a sheet
| AI & Resume Intelligence | Build deduplication logic before export to prevent duplicate rows | Expected Output: Dedup-before-export working | Dheeraj Sarfare | FALSE | Excel Automation - Export & Sync | Deliverable: export_dedup.py committed ¦ Acceptance: No duplicate rows in exported test file
| Testing, Documentation & QA | Write tests for Google Sheets sync and conflict-handling logic | Expected Output: Sync tests passing | Aditee Talekar | FALSE | Excel Automation - Export & Sync | Deliverable: test_sheets_sync.py committed ¦ Acceptance: Conflict scenarios verified as handled correctly

## Week 13
IIB — Team ADAG — Week 13 Timeline (Sun Sep 27 – Fri Oct 2)
Phase(s) this week: Excel Automation - Export & Sync → Excel Automation - Backup & Archive System ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-09-27 | Project Lead & Backend Architecture | Build auto-sync scheduler - periodic push of data to linked Google Sheet | Expected Output: Auto-sync scheduler working | Gaurav Bhosale | FALSE | Excel Automation - Export & Sync | Deliverable: auto_sync_scheduler.py committed ¦ Acceptance: Sheet updates automatically on schedule
| Frontend Lead & UI/UX | Build Sync Status Dashboard - last sync time, success/failure indicators | Expected Output: Sync dashboard functional | Amey Nadkar | FALSE | Excel Automation - Export & Sync | Deliverable: SyncStatusDashboard.jsx committed ¦ Acceptance: Dashboard reflects real sync status live
| AI & Resume Intelligence | Build data-integrity validation comparing DB source vs exported/synced data | Expected Output: Data integrity validation working | Dheeraj Sarfare | FALSE | Excel Automation - Export & Sync | Deliverable: data_integrity_check.py committed ¦ Acceptance: Validation catches 3 seeded mismatch cases
| Testing, Documentation & QA | Write frontend tests for ExportSettings and SyncStatusDashboard | Expected Output: Frontend tests passing | Aditee Talekar | FALSE | Excel Automation - Export & Sync | Deliverable: ExportSettings.test.jsx committed ¦ Acceptance: Settings and status display covered
2026-09-28 | Project Lead & Backend Architecture | Build sync-status tracking API - last synced time, success/failure state | Expected Output: Sync status API working | Gaurav Bhosale | FALSE | Excel Automation - Export & Sync | Deliverable: sync_status endpoint committed ¦ Acceptance: Status accurately reflects last sync attempt
| Frontend Lead & UI/UX | Build manual Sync Now trigger button with progress feedback | Expected Output: Manual sync trigger functional | Amey Nadkar | FALSE | Excel Automation - Export & Sync | Deliverable: SyncNowButton.jsx committed ¦ Acceptance: Triggering sync shows progress and completion
| AI & Resume Intelligence | Support Gaurav with conflict-resolution logic for concurrent sheet edits | Expected Output: Conflict-resolution logic reviewed and improved | Dheeraj Sarfare | FALSE | Excel Automation - Export & Sync | Deliverable: sync_conflict_handler.py updated ¦ Acceptance: Handles simultaneous edit test case correctly
| Testing, Documentation & QA | Manual QA - full export-sync-backup-restore cycle with real data | Expected Output: Full cycle QA report written | Aditee Talekar | FALSE | Excel Automation - Export & Sync | Deliverable: qa_report_excel_sync.md committed ¦ Acceptance: All bugs logged with severity
2026-09-29 | Project Lead & Backend Architecture | Build conflict handling for manual edits made directly in Google Sheets Also run the weekly team sync: demo Excel export and Google Sheets auto-sync | Expected Output: Conflict handling logic working Sync demo delivered | Gaurav Bhosale | FALSE | Excel Automation - Export & Sync | Deliverable: sync_conflict_handler.py committed; Demo notes in Wiki ¦ Acceptance: Manual edits are not silently overwritten Team verifies data appears correctly in live sheet
| Frontend Lead & UI/UX | Build backup/restore UI - list backups, restore to a selected point Also run the weekly team sync: demo sync status dashboard and manual sync controls | Expected Output: Backup/restore UI functional Sync UI demo delivered | Amey Nadkar | FALSE | Excel Automation - Export & Sync | Deliverable: BackupRestore.jsx committed; Demo notes in Wiki ¦ Acceptance: Restoring a backup updates data correctly Team validates sync status accuracy
| AI & Resume Intelligence | Document the full Excel/Sheets sync architecture for maintainability Also run the weekly team sync: present data integrity validation results | Expected Output: Sync architecture documented Integrity demo delivered | Dheeraj Sarfare | FALSE | Excel Automation - Export & Sync | Deliverable: excel_sync_architecture.md committed; Demo notes in Wiki ¦ Acceptance: Reviewed and approved by project lead Team confirms confidence in synced data accuracy
| Testing, Documentation & QA | Update USAGE.md with Excel Automation and Google Sheets Sync docs Also run the weekly team sync: Week 15 retrospective on Excel Automation progress | Expected Output: Docs updated Week 15 retro completed | Aditee Talekar | FALSE | Excel Automation - Export & Sync | Deliverable: USAGE.md updated; retro-week15.md committed ¦ Acceptance: Reviewed by project lead Blockers logged as GitHub Issues
2026-09-30 | Project Lead & Backend Architecture | Build automated backup scheduling API - daily/weekly snapshot creation | Expected Output: Backup scheduling API working | Gaurav Bhosale | FALSE | Excel Automation - Backup & Archive System | Deliverable: backup_scheduler endpoint committed ¦ Acceptance: Snapshots created automatically on schedule
| Frontend Lead & UI/UX | Build Backup Schedule settings UI - frequency, retention period | Expected Output: Backup settings UI functional | Amey Nadkar | FALSE | Excel Automation - Backup & Archive System | Deliverable: BackupScheduleSettings.jsx committed ¦ Acceptance: Settings save and apply to scheduler
| AI & Resume Intelligence | Build archive-candidate detection - identify stale/expired listings automatically | Expected Output: Archive detection logic working | Dheeraj Sarfare | FALSE | Excel Automation - Backup & Archive System | Deliverable: archive_candidate_detector.py committed ¦ Acceptance: Correctly flags expired test listings
| Testing, Documentation & QA | Write tests for backup scheduling, storage, and restore APIs | Expected Output: Backup/restore tests passing | Aditee Talekar | FALSE | Excel Automation - Backup & Archive System | Deliverable: test_backup_restore.py committed ¦ Acceptance: Restore correctness verified against known snapshot
2026-10-01 | Project Lead & Backend Architecture | Build backup storage integration - versioned snapshots in object storage | Expected Output: Backup storage working | Gaurav Bhosale | FALSE | Excel Automation - Backup & Archive System | Deliverable: backup_storage_client.py committed ¦ Acceptance: Snapshots retrievable by date
| Frontend Lead & UI/UX | Build Backup History list UI - browse and select snapshots | Expected Output: Backup history UI functional | Amey Nadkar | FALSE | Excel Automation - Backup & Archive System | Deliverable: BackupHistory.jsx committed ¦ Acceptance: List shows all snapshots with timestamps
| AI & Resume Intelligence | Build backup integrity verification - checksum/validation on each snapshot | Expected Output: Backup verification working | Dheeraj Sarfare | FALSE | Excel Automation - Backup & Archive System | Deliverable: backup_integrity_check.py committed ¦ Acceptance: Corrupted snapshot detected in test scenario
| Testing, Documentation & QA | Write tests for archive system - archiving, retrieval, exclusion from live queries | Expected Output: Archive tests passing | Aditee Talekar | FALSE | Excel Automation - Backup & Archive System | Deliverable: test_archive_system.py committed ¦ Acceptance: Archived records confirmed excluded from live queries
2026-10-02 | Project Lead & Backend Architecture | Build restore-from-backup API with rollback safety checks | Expected Output: Restore API working safely | Gaurav Bhosale | FALSE | Excel Automation - Backup & Archive System | Deliverable: restore_backup endpoint committed ¦ Acceptance: Restore requires confirmation, logs the action
| Frontend Lead & UI/UX | Build Restore confirmation flow with clear warning messaging | Expected Output: Restore confirmation UI functional | Amey Nadkar | FALSE | Excel Automation - Backup & Archive System | Deliverable: RestoreConfirmation.jsx committed ¦ Acceptance: User must explicitly confirm before restore executes
| AI & Resume Intelligence | Build historical trend analytics using archived data (multi-year placement trends) | Expected Output: Historical trend analytics working | Dheeraj Sarfare | FALSE | Excel Automation - Backup & Archive System | Deliverable: historical_trends.py committed ¦ Acceptance: Trend chart data spans archived + live records correctly
| Testing, Documentation & QA | Write frontend tests for BackupHistory and ArchiveBrowser | Expected Output: Frontend tests passing | Aditee Talekar | FALSE | Excel Automation - Backup & Archive System | Deliverable: BackupHistory.test.jsx committed ¦ Acceptance: Snapshot listing and restore flow covered

## Week 14
IIB — Team ADAG — Week 14 Timeline (Sun Oct 4 – Fri Oct 9)
Phase(s) this week: Excel Automation - Backup & Archive System → Analytics Dashboard ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-10-04 | Project Lead & Backend Architecture | Build archive system API - move stale listings/data to archive tables | Expected Output: Archive system API working | Gaurav Bhosale | FALSE | Excel Automation - Backup & Archive System | Deliverable: archive_data endpoint committed ¦ Acceptance: Archived records excluded from active queries
| Frontend Lead & UI/UX | Build Archive browsing UI - view archived listings/records | Expected Output: Archive browsing UI functional | Amey Nadkar | FALSE | Excel Automation - Backup & Archive System | Deliverable: ArchiveBrowser.jsx committed ¦ Acceptance: Archived records viewable and searchable
| AI & Resume Intelligence | Optimize archive query performance for large historical datasets | Expected Output: Archive query performance improved | Dheeraj Sarfare | FALSE | Excel Automation - Backup & Archive System | Deliverable: Performance benchmark documented ¦ Acceptance: Historical queries return under target latency
| Testing, Documentation & QA | Manual QA - simulate data-loss scenario and verify full recovery | Expected Output: Disaster-recovery QA report written | Aditee Talekar | FALSE | Excel Automation - Backup & Archive System | Deliverable: qa_report_disaster_recovery.md committed ¦ Acceptance: Full recovery confirmed from backup
2026-10-05 | Project Lead & Backend Architecture | Build archive retrieval API for historical reporting needs Also run the weekly team sync: demo backup, restore, and archive system end-to-end | Expected Output: Archive retrieval API working Backup/archive demo delivered | Gaurav Bhosale | FALSE | Excel Automation - Backup & Archive System | Deliverable: archive_retrieval endpoint committed; Demo notes in Wiki ¦ Acceptance: Historical data retrievable without affecting live tables Team performs a live restore from backup
| Frontend Lead & UI/UX | Build Data Health indicator - surface backup/sync/archive status at a glance Also run the weekly team sync: demo backup history and archive browsing UI | Expected Output: Data health indicator functional Backup/archive UI demo delivered | Amey Nadkar | FALSE | Excel Automation - Backup & Archive System | Deliverable: DataHealthIndicator.jsx committed; Demo notes in Wiki ¦ Acceptance: Indicator accurately reflects system state Team validates restore confirmation UX
| AI & Resume Intelligence | Document archive lifecycle - when data moves from active to archived Also run the weekly team sync: present historical trend analytics from archived data | Expected Output: Archive lifecycle documented Historical analytics demo delivered | Dheeraj Sarfare | FALSE | Excel Automation - Backup & Archive System | Deliverable: archive_lifecycle.md committed; Demo notes in Wiki ¦ Acceptance: Reviewed and approved by project lead Team reviews multi-year trend accuracy
| Testing, Documentation & QA | Update USAGE.md with Backup, Restore and Archive documentation Also run the weekly team sync: Week 16 retrospective, Excel Automation sign-off | Expected Output: Docs updated Excel Automation sign-off | Aditee Talekar | FALSE | Excel Automation - Backup & Archive System | Deliverable: USAGE.md updated; retro-week16.md committed ¦ Acceptance: Reviewed by project lead Team formally signs off on Excel Automation MVP
2026-10-06 | Project Lead & Backend Architecture | Build platform-wide analytics aggregation API - growth, active jobs, revenue | Expected Output: Platform analytics API working | Gaurav Bhosale | FALSE | Analytics Dashboard | Deliverable: platform_analytics endpoint committed ¦ Acceptance: Numbers match manually verified totals
| Frontend Lead & UI/UX | Build Super Admin Analytics Dashboard - platform growth, revenue charts | Expected Output: Super Admin analytics UI functional | Amey Nadkar | FALSE | Analytics Dashboard | Deliverable: SuperAdminAnalytics.jsx committed ¦ Acceptance: Charts render live platform data correctly
| AI & Resume Intelligence | Build predictive analytics POC - forecast placement trends for next quarter | Expected Output: Predictive analytics POC working | Dheeraj Sarfare | FALSE | Analytics Dashboard | Deliverable: placement_forecast_poc.py committed ¦ Acceptance: Forecast reasonably tracks historical pattern on test data
| Testing, Documentation & QA | Write tests validating platform, growth, and department analytics accuracy | Expected Output: Analytics API tests passing | Aditee Talekar | FALSE | Analytics Dashboard | Deliverable: test_analytics_api.py committed ¦ Acceptance: Computed metrics match fixture data exactly
2026-10-07 | Project Lead & Backend Architecture | Build college-growth and company-growth analytics API for Super Admin | Expected Output: Growth analytics API working | Gaurav Bhosale | FALSE | Analytics Dashboard | Deliverable: growth_analytics endpoint committed ¦ Acceptance: Growth trend matches historical record counts
| Frontend Lead & UI/UX | Build College Analytics Dashboard - department performance, placement rates | Expected Output: College analytics UI functional | Amey Nadkar | FALSE | Analytics Dashboard | Deliverable: CollegeAnalytics.jsx committed ¦ Acceptance: Charts scoped correctly to logged-in college
| AI & Resume Intelligence | Build anomaly detection for analytics data (sudden spikes/drops) | Expected Output: Anomaly detection working | Dheeraj Sarfare | FALSE | Analytics Dashboard | Deliverable: analytics_anomaly_detection.py committed ¦ Acceptance: Flags 3 seeded anomalies correctly
| Testing, Documentation & QA | Write frontend tests for all 4 analytics dashboards | Expected Output: Frontend analytics tests passing | Aditee Talekar | FALSE | Analytics Dashboard | Deliverable: Analytics dashboard tests committed ¦ Acceptance: Chart rendering and data binding covered
2026-10-08 | Project Lead & Backend Architecture | Build department-performance analytics API for College Admin/Coordinator | Expected Output: Department analytics API working | Gaurav Bhosale | FALSE | Analytics Dashboard | Deliverable: department_performance endpoint committed ¦ Acceptance: Metrics scoped correctly per department
| Frontend Lead & UI/UX | Build Company Analytics Dashboard - views, applicants, hiring funnel | Expected Output: Company analytics UI functional | Amey Nadkar | FALSE | Analytics Dashboard | Deliverable: CompanyAnalytics.jsx committed ¦ Acceptance: Funnel chart matches backend data
| AI & Resume Intelligence | Build insight-generation logic - auto-written summary of key analytics trends | Expected Output: Insight generation working | Dheeraj Sarfare | FALSE | Analytics Dashboard | Deliverable: insight_generator.py committed ¦ Acceptance: Generates coherent summary from test dataset
| Testing, Documentation & QA | Manual QA - cross-check every dashboard metric against raw DB queries | Expected Output: Analytics accuracy QA report written | Aditee Talekar | FALSE | Analytics Dashboard | Deliverable: qa_report_analytics_accuracy.md committed ¦ Acceptance: All discrepancies logged and resolved
2026-10-09 | Project Lead & Backend Architecture | Build company hiring-report analytics API - views, applicants, conversion | Expected Output: Hiring report API working | Gaurav Bhosale | FALSE | Analytics Dashboard | Deliverable: hiring_report endpoint committed ¦ Acceptance: Conversion rates match manual calculation
| Frontend Lead & UI/UX | Build Student Analytics widgets - application success rate, profile strength | Expected Output: Student analytics widgets functional | Amey Nadkar | FALSE | Analytics Dashboard | Deliverable: StudentAnalyticsWidgets.jsx committed ¦ Acceptance: Widgets reflect accurate personal data
| AI & Resume Intelligence | Optimize recommendation-engine analytics feed (data used across dashboards) | Expected Output: Recommendation analytics feed optimized | Dheeraj Sarfare | FALSE | Analytics Dashboard | Deliverable: recommendation_analytics_feed.py committed ¦ Acceptance: Feed refreshes without performance degradation
| Testing, Documentation & QA | Performance test analytics endpoints under realistic data volume | Expected Output: Analytics performance test completed | Aditee Talekar | FALSE | Analytics Dashboard | Deliverable: performance_test_analytics.md committed ¦ Acceptance: Response times meet target under load

## Week 15
IIB — Team ADAG — Week 15 Timeline (Sun Oct 11 – Fri Oct 16)
Phase(s) this week: Analytics Dashboard → Full-Platform Testing & Hardening ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-10-11 | Project Lead & Backend Architecture | Optimize analytics queries with materialized views/caching for dashboard speed Also run the weekly team sync: demo full analytics stack across all 4 roles | Expected Output: Analytics query performance optimized Analytics demo delivered | Gaurav Bhosale | FALSE | Analytics Dashboard | Deliverable: Materialized views committed; Demo notes in Wiki ¦ Acceptance: Dashboard loads under target latency with real data volume Team validates numbers across all dashboards
| Frontend Lead & UI/UX | Integrate a charting library (recharts) consistently across all dashboards Also run the weekly team sync: demo all 4 analytics dashboards to the team | Expected Output: Consistent charting library integrated Full analytics UI demo delivered | Amey Nadkar | FALSE | Analytics Dashboard | Deliverable: Charting components standardized; Demo notes in Wiki ¦ Acceptance: All dashboards use consistent chart styling Team confirms visual consistency and accuracy
| AI & Resume Intelligence | Document all analytics metrics - definitions, formulas, data sources Also run the weekly team sync: present predictive analytics and insight-generation results | Expected Output: Analytics metrics glossary documented AI analytics demo delivered | Dheeraj Sarfare | FALSE | Analytics Dashboard | Deliverable: analytics_metrics_glossary.md committed; Demo notes in Wiki ¦ Acceptance: Reviewed and approved by project lead Team reviews forecast and insight quality
| Testing, Documentation & QA | Update USAGE.md and metrics glossary with analytics documentation Also run the weekly team sync: Week 17 retrospective, Analytics Dashboard sign-off | Expected Output: Docs updated Analytics sign-off | Aditee Talekar | FALSE | Analytics Dashboard | Deliverable: USAGE.md, analytics_metrics_glossary.md updated; retro-week17.md committed ¦ Acceptance: Reviewed by project lead Team formally signs off on Analytics MVP
2026-10-12 | Project Lead & Backend Architecture | Fix all backend bugs identified in Week 1-17 code reviews and QA reports | Expected Output: Backend bug backlog cleared | Gaurav Bhosale | FALSE | Full-Platform Testing & Hardening | Deliverable: Bug-fix PRs merged ¦ Acceptance: All P0/P1 backend bugs closed
| Frontend Lead & UI/UX | Fix all frontend bugs identified in Week 1-17 code reviews and QA reports | Expected Output: Frontend bug backlog cleared | Amey Nadkar | FALSE | Full-Platform Testing & Hardening | Deliverable: Bug-fix PRs merged ¦ Acceptance: All P0/P1 frontend bugs closed
| AI & Resume Intelligence | Fix AI/recommendation bugs and quality issues identified across Weeks 1-17 | Expected Output: AI bug backlog cleared | Dheeraj Sarfare | FALSE | Full-Platform Testing & Hardening | Deliverable: AI bug-fix PRs merged ¦ Acceptance: All P0/P1 AI-related bugs closed
| Testing, Documentation & QA | Run full regression test suite across backend, frontend, and AI service | Expected Output: Full regression suite executed | Aditee Talekar | FALSE | Full-Platform Testing & Hardening | Deliverable: regression_test_report.md committed ¦ Acceptance: 100% of critical-path tests passing
2026-10-13 | Project Lead & Backend Architecture | Run security audit - SQL injection, auth bypass, rate limiting on all APIs | Expected Output: Security audit completed | Gaurav Bhosale | FALSE | Full-Platform Testing & Hardening | Deliverable: security_audit_report.md committed ¦ Acceptance: No critical vulnerabilities found or all resolved
| Frontend Lead & UI/UX | Run accessibility audit - keyboard navigation, screen reader labels, contrast | Expected Output: Accessibility audit completed | Amey Nadkar | FALSE | Full-Platform Testing & Hardening | Deliverable: accessibility_audit_report.md committed ¦ Acceptance: Critical accessibility issues resolved
| AI & Resume Intelligence | Run bias/fairness check on recommendation and fit-scoring algorithms | Expected Output: Fairness audit completed | Dheeraj Sarfare | FALSE | Full-Platform Testing & Hardening | Deliverable: fairness_audit_report.md committed ¦ Acceptance: No systematic bias found across test demographics
| Testing, Documentation & QA | Execute complete RBAC test matrix across all 7 roles one final time | Expected Output: Final RBAC verification completed | Aditee Talekar | FALSE | Full-Platform Testing & Hardening | Deliverable: final_rbac_verification.md committed ¦ Acceptance: All role/permission combinations confirmed correct
2026-10-14 | Project Lead & Backend Architecture | Implement API rate limiting across all public-facing endpoints | Expected Output: Rate limiting implemented platform-wide | Gaurav Bhosale | FALSE | Full-Platform Testing & Hardening | Deliverable: rate_limiting middleware committed ¦ Acceptance: Excessive requests correctly throttled in test
| Frontend Lead & UI/UX | Optimize frontend bundle size and page load performance (code splitting) | Expected Output: Frontend performance optimized | Amey Nadkar | FALSE | Full-Platform Testing & Hardening | Deliverable: Bundle optimization committed ¦ Acceptance: Lighthouse performance score meets target
| AI & Resume Intelligence | Optimize AI service response latency for production load | Expected Output: AI latency optimized | Dheeraj Sarfare | FALSE | Full-Platform Testing & Hardening | Deliverable: AI performance benchmark documented ¦ Acceptance: Response times meet target under concurrent load
| Testing, Documentation & QA | Conduct end-to-end user-journey testing for all 4 portals | Expected Output: E2E journey testing completed | Aditee Talekar | FALSE | Full-Platform Testing & Hardening | Deliverable: e2e_journey_report.md committed ¦ Acceptance: All critical user journeys complete without errors
2026-10-15 | Project Lead & Backend Architecture | Run database performance tuning - indexes, query optimization on hot paths | Expected Output: DB performance tuned | Gaurav Bhosale | FALSE | Full-Platform Testing & Hardening | Deliverable: DB indexes and query fixes committed ¦ Acceptance: Slow queries improved to under target latency
| Frontend Lead & UI/UX | Cross-browser testing - Chrome, Firefox, Safari, Edge compatibility check | Expected Output: Cross-browser testing completed | Amey Nadkar | FALSE | Full-Platform Testing & Hardening | Deliverable: cross_browser_report.md committed ¦ Acceptance: No blocking issues on any major browser
| AI & Resume Intelligence | Verify human-verification-only policy is enforced everywhere AI is used | Expected Output: Policy compliance verified | Dheeraj Sarfare | FALSE | Full-Platform Testing & Hardening | Deliverable: policy_compliance_check.md committed ¦ Acceptance: No AI action bypasses human approval anywhere in system
| Testing, Documentation & QA | Coordinate bug bash - all 4 members test the live staging environment together | Expected Output: Bug bash session completed | Aditee Talekar | FALSE | Full-Platform Testing & Hardening | Deliverable: bug_bash_notes.md committed ¦ Acceptance: All discovered issues logged and triaged
2026-10-16 | Project Lead & Backend Architecture | Conduct load testing on core APIs (auth, search, recommendations) Also run the weekly team sync: review full backend hardening results with team | Expected Output: Load testing completed Hardening demo delivered | Gaurav Bhosale | FALSE | Full-Platform Testing & Hardening | Deliverable: load_test_report.md committed; Demo notes in Wiki ¦ Acceptance: APIs handle target concurrent user load Team confirms backend is production-ready
| Frontend Lead & UI/UX | Responsive design pass - verify all pages work on tablet/mobile widths Also run the weekly team sync: review full frontend hardening results with team | Expected Output: Responsive design verified Frontend hardening demo delivered | Amey Nadkar | FALSE | Full-Platform Testing & Hardening | Deliverable: Responsive fixes committed; Demo notes in Wiki ¦ Acceptance: All key pages usable on mobile viewport Team confirms frontend is production-ready
| AI & Resume Intelligence | Finalize AI service documentation - all models, prompts, and data sources Also run the weekly team sync: review AI hardening and policy compliance results | Expected Output: AI documentation finalized AI hardening demo delivered | Dheeraj Sarfare | FALSE | Full-Platform Testing & Hardening | Deliverable: AI_SERVICE_DOCS.md committed; Demo notes in Wiki ¦ Acceptance: Reviewed and approved by project lead Team confirms AI service is production-ready
| Testing, Documentation & QA | Compile final test coverage report across the whole platform Also run the weekly team sync: Week 18 retrospective, full-platform testing sign-off | Expected Output: Final coverage report published Testing sign-off | Aditee Talekar | FALSE | Full-Platform Testing & Hardening | Deliverable: final_coverage_report.md committed; retro-week18.md committed ¦ Acceptance: Coverage % documented for all 3 codebases Team formally signs off - platform ready for deployment

## Week 16
IIB — Team ADAG — Week 16 Timeline (Sun Oct 18 – Fri Oct 23)
Phase(s) this week: Production Deployment → Final Demo & Project Closure ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-10-18 | Project Lead & Backend Architecture | Set up production infrastructure - Docker containers, reverse proxy, SSL | Expected Output: Production infrastructure provisioned | Gaurav Bhosale | FALSE | Production Deployment | Deliverable: Production docker-compose/infra committed ¦ Acceptance: HTTPS site reachable with valid certificate
| Frontend Lead & UI/UX | Build and optimize production frontend build (minification, asset compression) | Expected Output: Production build optimized | Amey Nadkar | FALSE | Production Deployment | Deliverable: Production build config committed ¦ Acceptance: Build size and load time meet target
| AI & Resume Intelligence | Deploy AI service to production with proper resource allocation | Expected Output: AI service deployed to production | Dheeraj Sarfare | FALSE | Production Deployment | Deliverable: AI production deployment committed ¦ Acceptance: Production /ai/health returns 200
| Testing, Documentation & QA | Write and execute production smoke test suite immediately post-deploy | Expected Output: Production smoke tests passing | Aditee Talekar | FALSE | Production Deployment | Deliverable: smoke_test_production.py committed ¦ Acceptance: All critical paths verified working on production
2026-10-19 | Project Lead & Backend Architecture | Set up production database with automated backups and connection pooling | Expected Output: Production DB configured | Gaurav Bhosale | FALSE | Production Deployment | Deliverable: Production DB config committed ¦ Acceptance: Backups scheduled, connection pool sized correctly
| Frontend Lead & UI/UX | Set up CDN for static asset delivery | Expected Output: CDN configured | Amey Nadkar | FALSE | Production Deployment | Deliverable: CDN configuration committed ¦ Acceptance: Assets served from CDN with correct cache headers
| AI & Resume Intelligence | Set up AI model/prompt version tracking for production monitoring | Expected Output: AI version tracking configured | Dheeraj Sarfare | FALSE | Production Deployment | Deliverable: AI version tracking committed ¦ Acceptance: Current model/prompt versions visible in monitoring
| Testing, Documentation & QA | Verify all monitoring/alerting fires correctly using simulated incidents | Expected Output: Monitoring verification completed | Aditee Talekar | FALSE | Production Deployment | Deliverable: monitoring_verification_report.md committed ¦ Acceptance: All simulated incidents triggered correct alerts
2026-10-20 | Project Lead & Backend Architecture | Build production CI/CD pipeline - automated deploy on merge to main | Expected Output: Production CI/CD pipeline working | Gaurav Bhosale | FALSE | Production Deployment | Deliverable: deploy.yml committed ¦ Acceptance: Merge to main triggers successful deployment
| Frontend Lead & UI/UX | Configure frontend environment variables for production API endpoints | Expected Output: Production frontend config set | Amey Nadkar | FALSE | Production Deployment | Deliverable: Production .env committed (secrets excluded) ¦ Acceptance: Frontend correctly targets production backend
| AI & Resume Intelligence | Set up AI output monitoring - track quality/error signals in production | Expected Output: AI output monitoring configured | Dheeraj Sarfare | FALSE | Production Deployment | Deliverable: AI monitoring dashboard committed ¦ Acceptance: Dashboard reflects live AI request outcomes
| Testing, Documentation & QA | Conduct final security scan on the live production environment | Expected Output: Production security scan completed | Aditee Talekar | FALSE | Production Deployment | Deliverable: production_security_scan.md committed ¦ Acceptance: No critical vulnerabilities found on live site
2026-10-21 | Project Lead & Backend Architecture | Set up application monitoring and alerting (uptime, error rate, latency) | Expected Output: Monitoring and alerting configured | Gaurav Bhosale | FALSE | Production Deployment | Deliverable: Monitoring dashboard committed ¦ Acceptance: Test alert fires correctly on simulated error spike
| Frontend Lead & UI/UX | Run final visual QA pass on production build across key pages | Expected Output: Production visual QA completed | Amey Nadkar | FALSE | Production Deployment | Deliverable: visual_qa_report.md committed ¦ Acceptance: No visual regressions found on production build
| AI & Resume Intelligence | Load test AI service under production-representative concurrent request volume | Expected Output: AI load test completed | Dheeraj Sarfare | FALSE | Production Deployment | Deliverable: ai_load_test_report.md committed ¦ Acceptance: AI service handles target load within latency budget
| Testing, Documentation & QA | Write incident response runbook - who does what if production breaks | Expected Output: Incident runbook published | Aditee Talekar | FALSE | Production Deployment | Deliverable: INCIDENT_RUNBOOK.md committed ¦ Acceptance: Reviewed and understood by all team members
2026-10-22 | Project Lead & Backend Architecture | Build rollback procedure - revert to previous stable release quickly Also run the weekly team sync: demo production deployment and monitoring dashboard | Expected Output: Rollback procedure documented and tested Deployment demo delivered | Gaurav Bhosale | FALSE | Production Deployment | Deliverable: rollback_procedure.md committed; Demo notes in Wiki ¦ Acceptance: Test rollback completes within target time Team confirms production site is live and monitored
| Frontend Lead & UI/UX | Set up frontend error tracking (e.g. Sentry) for production issues Also run the weekly team sync: demo production frontend performance and monitoring | Expected Output: Error tracking configured Frontend deployment demo delivered | Amey Nadkar | FALSE | Production Deployment | Deliverable: Error tracking integration committed; Demo notes in Wiki ¦ Acceptance: Test error appears correctly in tracking dashboard Team confirms frontend production quality
| AI & Resume Intelligence | Prepare AI service rollback plan in case of production quality regression Also run the weekly team sync: demo AI service production readiness | Expected Output: AI rollback plan documented AI deployment demo delivered | Dheeraj Sarfare | FALSE | Production Deployment | Deliverable: ai_rollback_plan.md committed; Demo notes in Wiki ¦ Acceptance: Reviewed and approved by project lead Team confirms AI service is production-ready
| Testing, Documentation & QA | Update all documentation to reflect final production URLs/configuration Also run the weekly team sync: Week 19 retrospective, production deployment sign-off | Expected Output: Documentation finalized for production Deployment sign-off | Aditee Talekar | FALSE | Production Deployment | Deliverable: README.md, USAGE.md updated; retro-week19.md committed ¦ Acceptance: All doc links and instructions point to production Team formally signs off - platform live in production
2026-10-23 | Project Lead & Backend Architecture | Final backend code review - clean up debug code, unused endpoints, TODOs | Expected Output: Backend code cleaned and finalized | Gaurav Bhosale | FALSE | Final Demo & Project Closure | Deliverable: Cleanup PR merged ¦ Acceptance: No debug prints or dead code remain
| Frontend Lead & UI/UX | Final frontend polish - consistent spacing, animations, micro-interactions | Expected Output: Frontend polish completed | Amey Nadkar | FALSE | Final Demo & Project Closure | Deliverable: Final UI polish PR merged ¦ Acceptance: UI feels cohesive and professional across all pages
| AI & Resume Intelligence | Final AI feature review - verify recommendation/resume/career tools are stable | Expected Output: AI feature review completed | Dheeraj Sarfare | FALSE | Final Demo & Project Closure | Deliverable: AI stability checklist committed ¦ Acceptance: All AI features perform consistently in rehearsal
| Testing, Documentation & QA | Run final full regression suite across the entire platform one last time | Expected Output: Final regression suite executed | Aditee Talekar | FALSE | Final Demo & Project Closure | Deliverable: final_regression_report.md committed ¦ Acceptance: 100% critical-path tests passing before demo

## Week 17
IIB — Team ADAG — Week 17 Timeline (Sun Oct 25 – Wed Oct 28) (final partial week — 4 days)
Phase(s) this week: Final Demo & Project Closure ¦ Week runs Sunday–Friday (Saturday off)
Date | Modules | Task | Sub-Task | Assignee | Status | Phase | Remark
2026-10-25 | Project Lead & Backend Architecture | Prepare backend architecture walkthrough for the final demo presentation | Expected Output: Architecture walkthrough prepared | Gaurav Bhosale | FALSE | Final Demo & Project Closure | Deliverable: Architecture slides/notes committed ¦ Acceptance: Walkthrough rehearsed and timed
| Frontend Lead & UI/UX | Prepare live demo script - exact click-path through all 4 portals | Expected Output: Demo script prepared | Amey Nadkar | FALSE | Final Demo & Project Closure | Deliverable: demo_script.md committed ¦ Acceptance: Script covers a coherent under-5-minute story
| AI & Resume Intelligence | Prepare AI feature walkthrough narrative for the final demo | Expected Output: AI walkthrough narrative prepared | Dheeraj Sarfare | FALSE | Final Demo & Project Closure | Deliverable: AI demo notes committed ¦ Acceptance: Narrative explains AI value clearly to non-technical audience
| Testing, Documentation & QA | Compile the complete 100-Day Milestone Report summarizing all deliverables | Expected Output: 100-Day Milestone Report compiled | Aditee Talekar | FALSE | Final Demo & Project Closure | Deliverable: milestone_report_100day.md committed ¦ Acceptance: Report covers all 20 weeks and 13 MVP features
2026-10-26 | Project Lead & Backend Architecture | Fix any last-minute bugs found during demo rehearsals | Expected Output: Final bugs resolved | Gaurav Bhosale | FALSE | Final Demo & Project Closure | Deliverable: Final bug-fix PRs merged ¦ Acceptance: Demo rehearsal runs with zero backend errors
| Frontend Lead & UI/UX | Rehearse full live demo with the team, time it, fix rough edges | Expected Output: Demo rehearsal completed | Amey Nadkar | FALSE | Final Demo & Project Closure | Deliverable: Rehearsal notes committed ¦ Acceptance: Demo runs smoothly under time target
| AI & Resume Intelligence | Fix any last-minute AI quality issues found during demo rehearsals | Expected Output: Final AI issues resolved | Dheeraj Sarfare | FALSE | Final Demo & Project Closure | Deliverable: Final AI fix PRs merged ¦ Acceptance: AI outputs consistent across rehearsal runs
| Testing, Documentation & QA | Finalize all documentation - README, USAGE, CONTRIBUTING, ROLES, runbooks | Expected Output: All documentation finalized | Aditee Talekar | FALSE | Final Demo & Project Closure | Deliverable: Full docs set committed ¦ Acceptance: New team member could onboard from docs alone
2026-10-27 | Project Lead & Backend Architecture | Merge all remaining backend branches into main, tag final release | Expected Output: Final release tagged on main | Gaurav Bhosale | FALSE | Final Demo & Project Closure | Deliverable: v1.0.0 tag created ¦ Acceptance: main branch matches production exactly
| Frontend Lead & UI/UX | Prepare demo fallback - recorded video backup in case of live issues | Expected Output: Demo backup video recorded | Amey Nadkar | FALSE | Final Demo & Project Closure | Deliverable: demo_backup.mp4 saved ¦ Acceptance: Video covers full feature set as fallback
| AI & Resume Intelligence | Merge all remaining AI service branches into main, tag final release | Expected Output: Final AI release tagged on main | Dheeraj Sarfare | FALSE | Final Demo & Project Closure | Deliverable: AI v1.0.0 tag created ¦ Acceptance: main branch AI service matches production exactly
| Testing, Documentation & QA | Coordinate final demo rehearsal timing and Q&A preparation with team | Expected Output: Demo Q&A prep completed | Aditee Talekar | FALSE | Final Demo & Project Closure | Deliverable: qa_prep_notes.md committed ¦ Acceptance: Team can answer likely judge/stakeholder questions
2026-10-28 | Project Lead & Backend Architecture | Prepare post-launch backend roadmap - next 90 days of planned improvements Also run the weekly team sync: Final sign-off - confirm all 13 MVP feature areas are complete and stable | Expected Output: Post-launch roadmap drafted Final backend sign-off delivered | Gaurav Bhosale | FALSE | Final Demo & Project Closure | Deliverable: post_launch_roadmap.md committed; Final checklist signed ¦ Acceptance: Reviewed and approved by team All backend MVP features verified stable
| Frontend Lead & UI/UX | Merge all remaining frontend branches into main, verify final build Also run the weekly team sync: Final sign-off - confirm frontend experience is demo-ready across all roles | Expected Output: Final frontend release verified Final frontend sign-off delivered | Amey Nadkar | FALSE | Final Demo & Project Closure | Deliverable: Final frontend build verified on main; Final checklist signed ¦ Acceptance: Production build matches rehearsed demo exactly All frontend MVP features verified stable
| AI & Resume Intelligence | Prepare post-launch AI roadmap - planned model/data improvements Also run the weekly team sync: Final sign-off - confirm all AI features are complete, stable and policy-compliant | Expected Output: Post-launch AI roadmap drafted Final AI sign-off delivered | Dheeraj Sarfare | FALSE | Final Demo & Project Closure | Deliverable: post_launch_ai_roadmap.md committed; Final checklist signed ¦ Acceptance: Reviewed and approved by team Human-verification-only policy confirmed intact platform-wide
| Testing, Documentation & QA | Verify every one of the 13 MVP features against the original feature list Also run the weekly team sync: Day 100 final milestone review and formal project sign-off | Expected Output: Full feature checklist verified Day 100 milestone review completed | Aditee Talekar | FALSE | Final Demo & Project Closure | Deliverable: final_feature_checklist.md committed; Day 100 milestone report committed to GitHub ¦ Acceptance: All 13 core modules confirmed present and working All 4 team members formally sign off on project completion